## Slide 1: Flow Time Problems Set 2 This is indeed Christine Cookies modified in MBPF 2nd Edition

## Slide 2
4.2 - Kristen and her roommate are in the business of baking custom cookies. As soon as she receives an order by phone, Kristen washes the bowl and mixes dough according to the customer's order - activities that take a total of 6 minutes. She then spoons the dough onto a tray that holds one dozen cookies (2 minutes). Her roommate then takes 1 minute to set the oven and place the tray in it. Cookies are baked in the oven for 9 minutes and allowed to cool outside for 5 minutes. The roommate then boxes the cookies (2 minutes) and collects payment from the customer (1 minute) a. Draw a flowchart for the process described here and determine theoretical flow time from the time of order until the time of payment collection. Assume no waiting over the course of the process b. suppose that each other consists of two dozen cookies. Assume that although the mixing bowl can accommodate dough for two dozen cookies at a time, the oven can accommodate only one tray of one dozen cookies at a time. As before, spooning each tray takes 2 minutes, and both trays must be cooled prior to boxing the cookies for customer pickup. Draw a modified flowchart and determine theoretical flow time. Consider the effect on flow time of the following possible alternatives to the system: 1. Buying a second oven that can bake one tray of one dozen cookies 2. Buying a second oven that can hold two trays of one dozen cookies each 3. Buying a faster convection oven that can bake one dozen cookies in 6 minutes instead of 9 minutes.

## Slide 3
Take
order
wash
mix
spoon
load
& set
cool
bake
unload
pack
get
pay
Problem 5.2: Flow unit = 1 order of 1 dozen.

## Slide 4
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
pack
2
5
get
pay
1/order
TFT = 6+2+1+9+5+2+1 = 26
Problem 4.2
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
pack
2
5
get
pay
1/order
a)

## Slide 5
wash
mix
spoon
cool
bake
u
l
pack
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
pack
2
5
get
pay
1/order
l
s
g
p
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26
Part (a): Gant Chart and the theoretical flow time for 1 doz orders

## Slide 6
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
pack
2
5
get
pay
1/order
Flow unit = 1 order of 2 dozen.
Certain activities can be performed in parallel.
For example, while the oven is baking the first dozen, You can spoon the dough for the second dozen into another tray. Therefore, the flow time of such an order is not simply the sum of the activity times.
A useful tool is a Gantt chart that shows the times during which different resources of interest are occupied for various activities.
The dough for the 2 dozen cookies is mixed by You in 6 minutes and subsequently you spoon dough for 1 dozen in 2 minutes.
Therefore in the 8th minute, the RM is ready to load the oven and set timer, which takes 1 minute. The oven starts baking the first dozen at the 9th minute and completes baking at the 18th minute. Meanwhile, You spoon the second dozen into another tray.
At the 18th minute, the RM unloads the first tray from the oven and loads the second tray into the oven and sets the timer. So the second dozen starts baking at the 19th minute.
While the second dozen bakes, the first dozen cookies cool and RM packs them into a bag, which takes a total of 7 minutes.
At the 28th minute the second dozen finishes baking at which time the RM unloads the tray.
After cooling for 5 minutes, the RM packs the second dozen in 2 minutes by the 35th minute.
Finally, payment for the order and delivery to customer takes place in the 36th minute.
The theoretical flow time for an order of 2 dozen cookies is 36 minutes.
Part (b): general explanations; mix can handle 2 doz, oven 1 doz

## Slide 7
wash
mix
spoon
cool
bake
u
l
pack
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
pack
2
5
get
pay
1/order
l
s
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30
spoon
l
s
bake
cool
u
l
Part (b): Gant Chart and the theoretical flow time for 2 doz orders

## Slide 8
cool
2
pack
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
pack
2
5
get
pay
1/order
g
p
31 32 33 34 35 36 37 38 39 40
Part (b): Gant Chart and the theoretical flow time for 2 doz orders (cont.)

## Slide 9
load
& set
bake
1
9
unlo-
ad
pack
2
Take
order
wash
mix
spoon
6/1-2 doz
2
spoon
2
cool
5
load
& set
bake
1
9
unlo-
ad
pack
2
cool
5
get
pay
1/order
Part (b): CPM

## Slide 10
load
& set
bake
1
9
unlo-
ad
pack
2
Take
order
wash
mix
spoon
6/1-2 doz
2
spoon
2
cool
5
load
& set
bake
1
9
unlo-
ad
pack
2
cool
5
get
pay
1/order
Part (b): CPM
0
0
0
6
6
8
8
8
10
9
9
10
18
18
18
18
18
23
23
25
19
25
28
28
28
28
33
33
35
35
35
36
18
19

## Slide 11
10
30
20
Max = 30
5
35
Forward Path
35
35

## Slide 12
load
& set
bake
1
9
unlo-
ad
pack
2
Take
order
wash
mix
spoon
6/1-2 doz
2
spoon
2
cool
5
load
& set
bake
1
9
unlo-
ad
pack
2
cool
5
get
pay
1/order
Part (b): CPM
0
0
0
6
6
8
8
8
10
9
9
10
18
18
18
18
18
23
23
25
19
25
28
28
28
28
33
33
35
35
35
36
36
35
35
35
33
33
28
28
28
28
19
19
18
33
33
28
18
18
18
9
9
8
18
16
8
6
6
0
0
0
18
18

## Slide 13
30
30
30
Min = 35
5
35
45
30
Backward Path

## Slide 14
wash
mix
spoon
cool
bake
u
l
pack
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
pack
2
5
get
pay
1/order
l
s
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29
spoon
l
s
bake
u
l
cool
g
p
Part (b1): theoretical flow time when buying a second oven with 1 doz capacity

## Slide 15
load
& set
bake
1
9
unlo-
ad
pack
2
Take
order
wash
mix
spoon
6/1-2 doz
2
spoon
2
cool
5
load
& set
bake
1
9
unlo-
ad
pack
2
cool
5
get
pay
1/order
Part (b1): CPM

## Slide 16
wash
mix
spoon
cool
bake
pack
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
pack
2
5
get
pay
1/order
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30
spoon
l
s
u
l
g
p
Part (b2): theoretical flow time when buying a large oven with 2 doz capacity
We do not need CPM since activities are sequential

## Slide 17
wash
mix
spoon
cool
bake
u
l
pack
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
pack
2
5
get
pay
1/order
l
s
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30
spoon
l
s
bake
u
l
cool
pack
g
p
Part (b3): theoretical flow time when buying a fast oven with 1 doz capacity
CPM is the same as the CPM for original case, just bake time is 6 min instead of 9 min.

## Slide 18
Trade-off Analysis
No Investment 36
Second Oven 28
Large Oven 30
Fast Ovens 30
The second oven
leads to the shortest flow time
Perhaps is cheaper than a large oven or 2 fast ovens

## Slide 19
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
box
2
5
get
paid
1/order
TFT = 6+2+1+9+5+2+1 = 26
Problem 4.2 Version2 - Both Boxed together: Part (a)

## Slide 20
wash
mix
spoon
cool
bake
u
l
box
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
box
2
5
get
paid
1/order
l
s
g
p
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26
Part (a): Gant Chart and the theoretical flow time for 1 doz orders

## Slide 21
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
box
2
5
get
paid
1/order
Flow unit = 1 order of 2 dozen.
Certain activities can be performed in parallel.
For example, while the oven is baking the first dozen, You can spoon the dough for the second dozen into another tray. Therefore, the flow time of such an order is not simply the sum of the activity times.
A useful tool is a Gantt chart that shows the times during which different resources of interest are occupied for various activities.
The dough for the 2 dozen cookies is mixed by You in 6 minutes and subsequently you spoon dough for 1 dozen in 2 minutes.
Therefore in the 8th minute, the RM is ready to load the oven and set timer, which takes 1 minute. The oven starts baking the first dozen at the 9th minute and completes baking at the 18th minute. Meanwhile, You spoon the second dozen into another tray.
At the 18th minute, the RM unloads the first tray from the oven and loads the second tray into the oven and sets the timer. So the second dozen starts baking at the 19th minute.
While the second dozen bakes, the first dozen cookies cool and RM packs them into a bag, which takes a total of 7 minutes.
At the 28th minute the second dozen finishes baking at which time the RM unloads the tray.
After cooling for 5 minutes, the RM packs the second dozen in 2 minutes by the 35th minute.
Finally, payment for the order and delivery to customer takes place in the 36th minute.
The theoretical flow time for an order of 2 dozen cookies is 36 minutes.
Part (b): general explanations; mix can handle 2 doz, oven 1 doz

## Slide 22
wash
mix
spoon
cool
bake
u
l
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
box
2
5
get
paid
1/order
l
s
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30
spoon
l
s
bake
cool
u
l
Part (b): Gant Chart and the theoretical flow time for 2 doz orders

## Slide 23
cool
2
box
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
box
2
5
get
paid
1/order
g
p
31 32 33 34 35 36 37 38 39 40
Part (b): Gant Chart and the theoretical flow time for 2 doz orders (cont.)

## Slide 24
load
& set
bake
1
9
unlo-
ad
Take
order
wash
mix
spoon
6/1-2 doz
2
spoon
2
cool
5
load
& set
bake
1
9
unlo-
ad
box
2
cool
5
Part (b): CPM
get
paid
1/order

## Slide 25
load
& set
bake
1
9
unlo-
ad
Take
order
wash
mix
spoon
6/1-2 doz
2
spoon
2
cool
5
load
& set
bake
1
9
unlo-
ad
box
2
cool
5
Part (b): CPM
0
0
0
6
6
8
8
8
10
9
9
10
18
18
18
18
18
23
19
28
28
28
28
33
33
35
35
36
18
19
23
get
paid
1/order

## Slide 26
10
30
20
Max = 30
5
35
Forward Path
35
35

## Slide 27
load
& set
bake
1
9
unlo-
ad
Take
order
wash
mix
spoon
6/1-2 doz
2
spoon
2
cool
5
load
& set
bake
1
9
unlo-
ad
box
2
cool
5
Part (b): CPM
0
0
0
6
6
8
8
8
10
9
9
10
18
18
18
18
18
23
19
28
28
28
28
33
33
35
36
35
35
33
33
28
28
28
28
19
19
18
33
28
18
18
18
9
9
8
18
16
8
6
6
0
0
0
18
18
get
paid
1/order
35
36

## Slide 28
30
30
30
Min = 35
5
35
45
30
Backward Path

## Slide 29
wash
mix
spoon
cool
bake
u
l
box
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
pack
2
5
get
pay
1/order
l
s
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29
spoon
l
s
bake
u
l
cool
g
p
Part (b1): theoretical flow time when buying a second oven with 1 doz capacity

## Slide 30
load
& set
bake
1
9
unlo-
ad
Take
order
wash
mix
spoon
6/1-2 doz
2
spoon
2
cool
5
load
& set
bake
1
9
unlo-
ad
box
2
cool
5
get
paid
1/order
Part (b1): CPM

## Slide 31
wash
mix
spoon
cool
bake
box
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
box
2
5
get
paid
1/order
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30
spoon
l
s
u
l
g
p
Part (b2): theoretical flow time when buying a large oven with 2 doz capacity
We do not need CPM since activities are sequential

## Slide 32
wash
mix
spoon
cool
bake
u
l
Take
order
wash
mix
spoon
load
& set
cool
bake
6/1-2 doz
2
1
9
unlo-
ad
box
2
5
get
paid
1/order
l
s
1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 20 21 22 23 24 25 26 27 28 29 30
spoon
l
s
bake
u
l
cool
box
g
p
Part (b3): theoretical flow time when buying a fast oven with 1 doz capacity
CPM is the same as the CPM for original case, just bake time is 6 min instead of 9 min.

## Slide 33
Trade-off Analysis
No Investment 36
Second Oven 28
Large Oven 28
Fast Ovens 30
The second oven
leads to the shortest flow time
Perhaps is cheaper than a large oven or 2 fast ovens