## Slide 1
Project Management
Ardavan Asef-Vaziri

## Slide 2: Project Networks

## Slide 3: Project Scheduling
From Action Plan and WBS to Gantt chart and project network.
Project Network
  Critical Path Method (CPM)- Late 1950s
  Dupont De Nemours Inc. developed the method
  Deterministic activity durations
Program Evaluation and Review Technique (PERT)
  U.S. Navy, Booz-Allen Hamilton, and Lockeheed Aircraft
  Probabilistic activity durations
Risk analysis: likelihood of completing the project on time, on budget, to specifications
  Statistics
  Simulation

## Slide 4: Draw Activity on Node Network
a:-
b:a
c:a
d:a
e: b
f:c
g:c
h:e,f
i: d,g
j: h,i
a
b
c
d
e
f
g
h
i
j

## Slide 5: Draw Activity on Node Network
A
Excavate
B
Lay Foundation
C
D
Rough Plumbing
Frame
E
F
G
Finish Exterior
HVAC
Rough Electric
H
Sheet Rock
Install Cabinets
I
J
Paint
K
Final Plumbing
L
Final Electric
M
Install
Flooring
Activity | Imm. Pred
A | --
B | A
C | B
D | B
E | D
F | D
G | D
H | C, E, F, G
I | H
J | H
K | I
L | J
M | K, L

## Slide 6: Critical Path Method (CPM)

## Slide 7: Critical Path Method
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
3/12/2024
5-1-7
Activity | Immediate Precedence | Duration
A1 | - | 4
A2 | - | 3
A3 | A1 | 6
A4 | A1 | 4
A5 | A2 | 2
A6 | A4, A5 | 3

## Slide 8: Critical Path Method: Paths
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
10
Critical Path is the longest path
11
8
How many path?
It is the shortest time to complete the project
3/12/2024

## Slide 9: Forward Path; Earliest Starts
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
0
0
0
0
0
0
4
3
3
4
4
3
4
4
10
8
5
5
8
10
8
11
11
11

## Slide 10: Forward Path
10
30
20
Max = 30
35
35
3/12/2024
35
5

## Slide 11: Backward Path; Latest Starts
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
0
0
0
0
0
0
4
3
3
4
4
3
4
4
10
8
5
5
8
10
8
11
11
11
11
11
11
11
5
5
8
8
8
8
8
4
6
4
6
6
3
3
4
0
0
11
3/12/2024

## Slide 12: Backward Path
30
30
30
Min = 35
35
45
30
3/12/2024
5

## Slide 13: Computing Slack Times
Task = duration
slack = xxxx
EST
EFT
LST
LFT
3/12/2024

## Slide 14: Critical Path, Slacks
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
0
0
4
3
3
4
4
10
8
5
8
11
11
11
11
5
8
8
8
4
6
6
3
4
0
11
3/12/2024

## Slide 15: Slack Times Example
Start
Finish
a=4
slack=
b=3
slack=
c=3
slack=
d=2
slack=
e=6
slack=
f=4
slack=
g=1
slack=
h=4
slack=
i=5
slack=
j=6
slack=
k=1
slack=
Task=dur
slack=xxx
EST
EFT
LFT
LST
3/12/2024
5-1-15
0
4
4
4
6
7
7
8
0
3
3
7
3
9
9
9
15
13
7
12
13
14
15

## Slide 16: Slack Times Example
Start
Finish
a=4
slack=
b=3
slack=
c=3
slack=
d=2
slack=
e=6
slack=
f=4
slack=
g=1
slack=
h=4
slack=
i=5
slack=
j=6
slack=
k=1
slack=
Task=dur
slack=xxx
EST
EFT
LFT
LST
3/12/2024
5-1-16
0
4
4
4
6
7
7
8
0
3
3
7
3
9
9
9
15
13
7
12
13
14
15

## Slide 17: Network Design- Technical Precedence
3/12/2024
STA
FIN
C
G
D
J
E
A
B
H
F
K
I

## Slide 18: Durations
3/12/2024
C
6
A
G
7
9
D
7
J
STA
5
FIN
E
4
B
H
2
8
F
K
7
6
I
2

## Slide 19: Forward Path- Convergence Points
3/12/2024
7
C
13
6
0
A
7
14
G
23
7
9
7
D
14
7
23
J
28
S
5
A
0
28
2
E
6
4
0
B
2
9
H
17
2
8
2
F
9
17
K
23
7
6
9
I
11
2
Max(C,D)
Max(E,F)
Max(E,G)
Max(H,I)
Max(J,K)

## Slide 20: Forward Path- Convergence Points
10
30
20
Max = 30
35
35
3/12/2024
35
5
35

## Slide 21: Forward Path- Divergence Points
3/12/2024
7
C
13
6
0
A
7
14
G
23
7
9
7
D
14
7
23
J
28
S
5
A
0
28
2
E
6
4
0
B
2
9
H
17
2
8
2
F
9
17
K
23
7
6
9
I
11
2
28
28
23
22
23
22
22
14
14
20
14
14
Min(H,J)
14
Min(H,I)
14
8
7
10
7
Min(C,D)
7
Min(E,F)
7
0
5

## Slide 22: Forward Path- Divergence Points
30
30
30
Min = 35
35
45
30
3/12/2024
5

## Slide 23: Critical Path and Slacks

## Slide 24: ProjMGT-RAND()

## Slide 25: Slack Times Example
Start
Finish
a=4
slack=
b=3
slack=
c=3
slack=
d=2
slack=
e=6
slack=
f=4
slack=
g=1
slack=
h=4
slack=
i=5
slack=
j=6
slack=
k=1
slack=
Task=dur
slack=xxx
EST
EFT
LFT
LST
3/12/2024
5-1-25
0
4
4
4
6
7
7
8
0
3
3
7
3
9
9
9
15
13
7
12
13
14
15

## Slide 26: Slack Times Example
5
8
Start
Finish
a=4
slack=
b=3
slack=
c=3
slack=
d=2
slack=
e=6
slack=
f=4
slack=
g=1
slack=
h=4
slack=
i=5
slack=
j=6
slack=
k=1
slack=
Task=dur
slack=xxx
EST
EFT
LFT
LST
3/12/2024
0
4
4
4
6
7
7
8
0
3
3
7
3
9
9
9
15
13
7
12
13
14
15
15
15
15
14
14
14
9
9
5
10
9
9
3
3
0
9
8
8
6
5
1
0
3
3
9
9
15
15
9
9
3
3
0

## Slide 27: Graphical Format
A
B
C
D
E
F
G
H
I
S
F
15
16
21
17
19
20
16
18
12
0
0
15
16
15
15
16
36
32
35
35
35
55
51
55
51
67
69
69
69
67
51
67
67
51
47
35
35
35
46
18
16
46
16
31
0

## Slide 28: Graphical Format
A
B
C
D
E
F
G
H
I
S
F
15
16
21
17
19
20
16
18
12
0
0
15
16
15
15
16
36
32
35
35
35
55
51
55
51
67
69
69
69
67
51
67
67
51
47
35
35
35
46
18
16
46
16
31
0

## Slide 29: Network & Critical Path Simulation

## Slide 31: Analysis of Projects Financial & Scoring

## Slide 32: Project Selection: Quantitative Methods
Financial Assessment Methods
  Payback period
  Discounted cash flow
    NPV
    IRR
    B/C
Scoring Methods
  Unweighted 0-1 factor method
  Weighted factor scoring method

## Slide 33: Payback Period
Number of years needed for the project to repay its initial fixed investment.
A project costs $100,000 and is expected to save the company $20,000 per year.
PP = $100,000 / $20,000 = 5 years
Shortcoming
  Ignores the time value of money, including interest rates and inflation.
  Ignores money earned after the payback period.

## Slide 34: Future Value (FV)
$100, put it in a bank. Interest rate = 10%. How much after 1 year. P = 100. F?
How much after 2 years?
How much after 3 years?
How much after N years
F = 100(1.1)N
F1 = 100 +0.1(100) = 100(1+0.1)
F2= 100(1+0.1) + 0.1(100(1+0.1)) =
F2= 100(1+0.1) (1+0.1) = 100(1.1)2
F3 = 100(1.1)2 + 0.1[100(1.1)2] =
F3 = 100(1.1)2 [1+0.1] = 100(1.1)2 [1.1] = 100(1.1)3

## Slide 35: Future Value (FV); Present Value (PV)
P: The initial vale
MARR: Minimum Acceptable Rate of Return
F= P(1+MARR)N
P = F/(1+MARR)N
P = F/(1+r)N
P = F(1+r)-N
r = the minimum acceptable rate of return
=FV(r, N,PMT,PV,0 EOY) =
=PV(r, N,PMT,FV,0 EOY) =

## Slide 36: Present Value Index Table

## Slide 37: Back to the PBP Example
The initial investment of a project at the end of year 0 is 10 million dollars. Depreciation is computed using straight-line method with accounting life of five years and zero salvage value. Net income before tax and depreciation is 3 million dollars per year. The tax rate is 40%. Compute net income after tax in Year 1. Compute net cash inflow in Year 1. At the end of year 7 we sell everything for 5 million dollars. Compute NPV and IRR.
Net Income Before Tax and Depreciation 3
Depreciation 2
Income Before Tax 1
Tax 0.4
Net Income After Tax 0.6
Cash Flow of Depreciation 2
Net cash flow per year 2.6
This is true for the first 5 yeas.

## Slide 38: Future Value (FV); Present Value (PV)
But after year 5 we do not have depreciation.
Therefore, the two million dollars depreciation is not a cost anymore. Our revenue will increases by
2(1-0.4) = 1.2 million dollars.
Net income after tax = 0.6+1.2 =1.8
You do not believe me?
Net Income Before Tax and Depreciation 3
Depreciation 0
Income Before Tax 3
Tax 0.4(3) =1.2
Net Income After Tax in Year 6 1.8
Net Income After Tax in Year 7 1.8+5(1-0.4) = 4.8

## Slide 39: Net Present Value (NPV)
I0 = the initial investment
Ft = the net cash flow in period t
r = the required rate of return
Important note: NPV function in excel assumes that the first cash flow is at the end of year 1.

## Slide 40: Internal Rate of Return (IRR)
The discount rate (r) that causes the NPV to be equal to zero.
The higher the IRR, the better.
In Excel “=IRR(Series,Guess)”
Compare IRR with MARR
MARR: Minimum Acceptable Rate of Return
Here it is not important where the first payment is – end of year 1 or end of year 0. The NPV for IRR is 0 everywhere.

## Slide 41: Your Mortgage; PMT and PPMT
$600,000 loan, 5% interest rate, 30 years fixed. What is your monthly payment? the money towards the principle in the first month? the money towards the principle in the last month, your cumulative principle at the end of the fifth year?
Your monthly payment
=PMT(monthly rate,#of months,pv,[fv], [type])
=PMT(0.05/12, 30*12, 600000)
Monthly Payment
($3,220.93)
=PMT(0.05/12,12*30,600000)
Pronciple Paid in month 1
($720.93)
=PPMT(0.05/12, 1, 30*12, 600000)
Principle paid in month 60
($921.37)
=PPMT(0.05/12, 60, 30*12, 600000)
Principle paid over the first 5 years
-49027.6075
=CUMPRINC(0.05/12,12*30,600000,1,60,0)

## Slide 42: Practice
The initial investment of a project at the end of year 0 is 10 million dollars. Depreciation is computed using straight-line method with accounting life of 4 years and accounting salvage value of 0. Total revenue is 6 million dollars per year. All expenses, excluding depreciation and tax are 2 million dollars per year. Useful life of the project (which differs from accounting life) is 7 years. At the end of the useful life the project is sold for 2 million dollars. Tax rate of operating income as well as capital gain is 30%. Compute profit per year during the accounting life of the project.
Revenue 6
Operating Expenses 2
Net Income Before Tax and Depreciation 4
Depreciation 2.5
Income Before Tax 1.5
Tax 0.3(1.5) = 0.45
Net Income After Tax (years 1-4) 1.05

## Slide 43: Practice: Net Income vs. Net Cash Inflow
Compute net cash inflow during the accounting life of the project.
Net Income After Tax 1.05
Depreciation 2.5
Net Cash Inflow (years 1-4) 3.55
Compute net cash inflow per year after accounting life is over and before the last year of the useful life of the project.
Net Income After Tax 1.05
Depreciation added to the profit 2.5
After Tax net income added 2.5(1-0.3) = 1.75
Total Net Income 1.05+1.75= 2.8
Net Cash Inflow (years 5-6) 2.8

## Slide 44: I Am Sure It Was Easy to Grasp
If it was not easy to grasp, you may look at it from a different perspective
Revenue 6
Operating Expenses 2
Net Income Before Tax and Depreciation 4
Tax 0.3(4) = 1.2
Net Income After Tax (years 1-4) 2.8
Compute net cash inflow in the last year of the useful life of the project.
Net Income After Tax 2.8
Project Sold 2
Capital Gain Tax 0.3(2) = 0.6
Net Capital Gain 1.4
Net Cash inflow 2.8+1.4= 4.2

## Slide 45: Practice: Net Income vs. Net Cash Inflow
What is the net cash flow of the project during its useful life. Compute NPV under 10% MARR and IRR.

## Slide 46: Profitability Models
Advantages
  Easy to use and understand
  Based on accounting data and forecasts
  Familiar and well understood
  Give a go/no-go indication
  Can be modified to include risk
Disadvantages
  Ignore non-monetary factors
  Discounting models (NPV, IRR) are biased to the short-term

## Slide 47: Weighted Scoring Model
Si = the total score of the ith project
sij = the score of the ith project on the jth criterion
wj = the weight or importance of the jth criterion

## Slide 48: Factor Rating Method For Location & Site Evaluation
A company wants to build a major warehouse in Europe. Four locations are being considered. The following table shows the important factors to bring into account along with the importance level (weight) of each factor. The attractiveness of each location relative to each factor is indicated on a 0-100 point scale. Find the best location.
Germany: 0.3(70)+0.3(60)+0.3(70)+0.1(80) = 21+18+21+8 = 68
France: 0.3(90)+0.3(70)+0.3(30)+0.1(50) = 27+21+9+5 = 62
Belgium: 0.3(50)+0.3(60)+0.3(70)+0.1(60) = 15+18+21+6 =60
Netherland: 0.3(50)+0.3(70)+0.3(70)+0.1(50) = 15+21+21+5 = 62

## Slide 49: Factor Rating Method For Location & Site Evaluation
In this example summation of the weight is NOT one (100%). We first need to normalize it to 100%. Scores were given in the range of 50 to 100.

## Slide 50: Learning Curves

## Slide 51: Learning Curves
Tn = the time required to complete the nth unit
T1 = the time required to complete the first unit
Time to produce nth unit with 85% learning (LR=0.85) when T1= 43
So, the 8th unit with 85% learning & T1=43:
r = (ln 8)/(ln 2) =
T8 = T1(LR)(ln 8)/(ln 2) = 43(.85)3 =

## Slide 52: Learning Curves
A firm has a project to produce 21 units of a new part for a customer.
The firm’s typical learning rate is 85%.
The first unit of the part that was produced (the prototype) required 43 hours to make.
Labor cost is $27 per hour.
Pricing policy is 3 times the total labor cost.
How much should customer be charged?

## Slide 53: Assignment Persons or Teams to Tasks

## Slide 54: Assignment of the Team to the Tasks – Can SOLVER in Excel Handle?

## Slide 55: Activity on Arrow

## Slide 56: Activity on Arrow Network
An Activity is an arc with two nodes at its beginning and its end
Task | Predecessor
a b c | -- a b
a
b
c
Task | Predecessor
a b c d | --- -- b a
a
b
d
c
Task | Predecessor
a b c d | --- a a a
a
b
d
c

## Slide 57: Activity on Arrow Network
Task | Predecessor
a b c d | --- -- -- a,b,c
a
b
d
c
Task | Predecessor
a b c d | --- a a b,c
a
b
d
c

## Slide 58: AoA: A Power Plant Construction Project
a
b
c
f
d
g
e
h
i
j

## Slide 59: Draw AOA
3/12/2024
Ardavan Asef-Vaziri
5-59
1
2
3
4
5
6
7
a = 6
b = 2
g = 9
h = 9
k = 6
d = 4
c = 5
e = 3
i = 4
f = 8
j = 7

## Slide 60: Program Evaluation and Review Technique (PERT)

## Slide 61: Activity Times in PERT
Optimistic (a)
  Activity duration to be ≤ a has 1% probability.  ≥ a has 99% probability
Pessimistic (b)
  Activity duration to be ≥ b has 1% probability  ≤ b has 99% probability
Most likely (m)
  The mode of the distribution
All possible task durations (or task costs) can be represented by statistical distributions

## Slide 62: Beta Distribution: The Probability Distribution of Activity Times
Mean = : TE = (a + 4m + b)/6
Standard deviation =  = (b-a)/6
Variance = 2 = [(b-a)/6]2

## Slide 63: 95% & 90% Levels
If we replace 99% with 95% level
  Activity duration to be ≤ a has 5% probability
  Activity duration to be ≥ b has 5% probability
  If we replace 99% with 90% level
  Activity duration to be ≤ a has 10% probability
  Activity duration to be ≥ b has 10% probability

## Slide 64: Probability of Completing the Critical Path on Time
We assume the various activities are statistically independent of each other
Individual variances (and mean) of the activities on a path can then be summed to find the variance (mean) of the path
Determine the mean and standard deviation of the critical path
Compute the probability of critical path being ≤ a
DCP = the desired completion date of the critical path
mCP= the sum of the TE for the activities on the critical path
2CP = the sum of the variances of the activities on the critical path
Given Z, the probability of having the standard normal variable being ≤ Z is the probability of completing the project in a time ≤ D

## Slide 65: Selecting Risk and Finding D
Find all paths in the network
Compute mean and standard deviation of each path
Compute the probability of completing each path in ≤ the given time
Calculate the probability that the entire project is completed within the specified time by multiplying these probabilities together

## Slide 66: Critical Path Method: Paths
A1
A3
A4
A6
A5
A2
4,1
3,0.5
6,2
4,1
2,0.5
3,1
E
S
10
The first number is the mean; the second is standard deviation.
11
8
Suppose all activities have beta distribution

## Slide 67: Probability of Completing CP in 12 days
DCP = the desired completion date of the critical path
mCP= 4+4+3 = 11
2CP = 12+12+12 = 3
CP = 1.73
Z= 0.58  P(z≤0.58) = 0.72
What is the probability of competing the critical path in a maximum of 12 days?

## Slide 68: Selecting Risk and Finding CP Time
With a probability of 90%, in how many days will the CP be completed?
From Standard Normal Table  Z 90% = 1.28

## Slide 69: Probability of Completing The Project in 12 days
mCP= 6+4 = 10
2CP = 12+22 = 5
CP = 2.24
Z= (12-10)/2.24 = 0.89  P(z≤0.89) = 0.81
The probability of completing the critical path in not more than 12 days was 0.72. We need to compute this probability for blue path and green path too, and then multiply these probabilities
mCP= 3+2+3 = 8
2CP = 0.52+0.52+12 = 1.22
CP = 1.1
Z= (12-8)/1.1 = 3.63  P(z≤3.63) ≈ 1
The probability of competing the Project in not more than 12 days is 0.72×0.81×1 = 0.58

## Slide 70: Problem- PERT
a
d
g
h
e
f
c
b
Activity | Immediate Predecessor | Optimistic Duration | Most Likely | Pessimistic Duration | Expected Duration te | Vt Variance
a | -- | 15 | 18 | 20 |  | 
b | -- | 20 | 20 | 22 |  | 
c | -- | 12 | 14 | 16 |  | 
d | a | 7 | 7 | 7 |  | 
e | b | 8 | 11 | 12 |  | 
f | c | 17 | 21 | 24 |  | 
g | b,d | 10 | 12 | 15 |  | 
h | e,f | 9 | 10 | 11 |  | 
Find the Critical path:
Compute expected duration of CP m cp=
Compute Standard deviation of critical path σcp =
Prob( TCP≤ 48)?, Prob(TCP ≤ 43)? , Prob(43 ≤TCP≤ 48)?
Find a completion date that you’re 80% sure you can meet.
Prob( TProject≤ 43)?

## Slide 71: Goldratt’s Critical Chain & Srinivansan’s Contributions

## Slide 72: Srinivasan’s Notes on Goldratt’s Critical Chain ritical Path Method
In 1997, Goldratt introduced the Critical Chain methodology to apply Theory of Constraints concepts to manage projects.
The Critical Chain methodology expands on the notion of a critical path and helps determine where buffers should be placed to prevent unplanned disruptions from delaying project completion.
To schedule work is also to schedule resource usage. Resource availability constrains all solutions to the scheduling problem.
Project management is fundamentally concerned with effectively trading off performance, cost, and time. Yet, to what extent is the need to make these trade-offs caused by human decisions and practices?
A project has four sets of activities that must be completed before a synchronization operation, represented by C4 can be completed.
Use historical data to obtain an estimate of the average time for each activity.
Sum these estimates to obtain the average time it takes each series of activities that must be completed before C4 can begin.

## Slide 73: The Critical Chain Concept
Feeding Buffer
Feeding Buffer
Feeding Buffer
Project Buffer
Start Date
A1
A2
B1
B2
C1
C2
C3
C4
D1
D2
Critical Chain
Completion Date
Time
An analysis reveals that the series of activities with the longest average time is C1-C2-C3.
This is the Critical Chain and the activities along the critical chain are termed critical activities.

## Slide 74: Estimating Task Times: 3 Project Scenario
The primary difference is the degree of interdependence across the paths.
  Scenario 1: there is only a single path
  Scenario 2: the path B-C-D-E is preceded by three activities A1, A2, & A3. The completion of path B-C-D-E depends on which of its three preceding tasks takes the longest
  Scenario 3: there are two completely independent paths each consisting of five tasks
All three tasks require 10 days to complete.
What completion time would you calculate for each project?
Project times are not known with certainty
Activities that take less than the expected time tend to cancel out the variability of activities that take more than the expected completion time for the project.

## Slide 75: The Critical Chain Concept

## Slide 76: Path Simulation

## Slide 77: Common Chain of Events
3/12/2024
Ardavan Asef-Vaziri
77
According to Goldratt, activities dealing with resource allocation lead to the following chain of events.
  Assuming that the activity times are known and that the paths are independent leads to underestimating the actual amount of time needed to complete the project.
  Because the time needed to complete the project is underestimated, project team members tend to inflate their time estimates.
  Inflated time estimates lead to work filling available time, workers not reporting that a task has been completed early, and the ever-present student syndrome.
  An important caveat than becomes that safety time is usually visible to project workers and is often misused.
  Misused safety time further complicates the task of prioritizing project activities.
  Hidden safety time further complicates the task of prioritizing project activities.
  The lack of clear priorities likely results in poor multitasking.
  Task durations increase as a result of poor multitasking.
  Uneven demand on resources- some overloaded and others underloaded- may also occur as a result of poor multitasking.
  In an effort to utilize all resources fully, more projects will be undertaken to make sure that no resources are underutilized.
  Adding more projects further increases poor multitasking.

## Slide 78: Critical Chain Project Management
3/12/2024
Ardavan Asef-Vaziri
78
Identify the critical chain: set of tasks that determine the overall duration of the project
Use deterministic CPM model with buffers to deal with uncertainty
Remove padding from activity estimates (otherwise, slack will be wasted). Estimate task durations at median.
Place project buffer after last task to protect customer’s completion schedule
Exploit constraining resource(s)
Avoid wasting slack times by encouraging early task completions
Have project team focus 100% effort on critical tasks
Work to your plan and avoid tampering
Carefully monitor and communicate buffer status

## Slide 79: Critical Chain Project Management
3/12/2024
Ardavan Asef-Vaziri
79

## Slide 80: Project Crashing

## Slide 81: Crashing
Crashing: shortening duration of activities. Because
  Some activities were delayed.
  Client is willing to pay more for earlier completion.
Crashing changes the schedule for remaining activities.
It has impact on schedules for all the subcontractors.
Often introduces unanticipated problems.
The faster an activity is completed, the more it costs.
There is always a lower bound on task duration.

## Slide 82: Linear Time / Cost Tradeoff
Time
Cost
Crash point
Normal point
Normal time
Crash time
Normal cost
Crash cost
Slope (bj) = increase in cost from reducing task duration by one time unit

## Slide 83: Crashing Algorithm
Assume each task can be crashed one day at a time (simplifying assumption, but not necessary)
Crash only critical activities. Crashing other activities can only increase cost without changing project duration
To decrease project duration by one day, the critical path or paths must decrease by one day.
  Find the critical path or paths
  If there is no other critical activity which could still be reduced, and shorten the critical path. Stop.
  Crash the cheapest critical activity (or combination of activities) to shorten the critical path (or paths) by one day.
  Go to 1

## Slide 84: Crashing 21 Days to 20 Days Network
Activities A,C, and F are on Critical Path. A and C are the least-cost choice. We crash A because it affects two paths. Lower A’s normal time by one day.
It now equals the crash time and cannot be shortened further.
The critical path is unchanged.
The critical time will be lowered to 20 days.
The cost of the project will be $400+30(A)= $430.

## Slide 85: Crashing 20 Days to 19 Days Network
Activities A,C, & F are still on the critical path.
A cannot be crashed any more. C is the least-cost choice.
Lower C’s normal time by one day. The critical path is unchanged
The critical time will be lowered to 19 days
The cost of the project will be $400+ 30(A) + 30(C) = $460

## Slide 86: Crashing 19 Days to 18 Days Network
All activities are now critical. 3 paths; ACF,EDG, and BEG. A cannot be crashed any more. The only way to crash ACF is to crash C or F. C is cheaper.
On ADG path, A and D cannot be crashed. The only way to crash ADG is to crash G. Crashing G crashes BEG path too.
The critical time will be lowered to 18 days
The cost of the project will be $400+ 30(A) + 30(C2) + 60(G) = $550

## Slide 87: Crashing 18 Days to 17 Days Network
All activities are critical. There are three paces ACF, ADG, and BEG.
Crash F and G by 1 at cost of 60 +40 = 100
The critical time has been lowered to 17 days
The cost of the project is $400+ 30(A) + 30(C2) + 60(G2)+40(F) = $650

## Slide 88: Crashing 17 Days to 16 Days Network
We can shorten the project to 16 days by crashing F and G by another day.
The cost of the project is $400+ 30(A) + 30(C2) + 60(G3)+40(F2) = $750
Activities A,C,F, and g have been crashed to their limits.
No further crashing will help so B,D, and E remain at their normal times and costs.

## Slide 89: Time-Cost Tradeoff

## Slide 90: Crash the Following Network. Prepare Cost-time Curve

## Slide 91: Crash the Following Network. Prepare Cost-time Curve

## Slide 92: Crash the Following Network. Prepare Cost-time Curve

## Slide 93: Crash the Following Network. Prepare Cost-time Curve

## Slide 94: Crash the Following Network. Prepare Cost-time Curve

## Slide 95: Crash the Following Network. Prepare Cost-time Curve

## Slide 96: Time-Cost Curve
Ardavan Asef-Vaziri
e+a
0 2 4 6 8 10
Total Duration (Days)
All crash
e(2)+a+d(2)+b
e(2)+a+d
e
All normal
$400
300
200
100

## Slide 97: Practice
The same example as we solved. Activity c either 0 or 2 but not 1. Solve it in the easiest way. Prepare Time-Cost Trade-off Curve