## Slide 1
Project Management
Ardavan Asef-Vaziri

## Slide 3: Project vs Process
Ardavan Asef-Vaziri

## Slide 4: PMI Definition
Project: A project is a unique temporary endeavor, with a set beginning and end.
Project Management: The application of knowledge, skills, tools and techniques to a broad range of activities in order to meet the requirements of a particular project.
Main Characteristics of Projects
  Unique (a one-of-a-kind output or deliverable)
  Temporary (specific start and finish)
Other Characteristics of Projects
  Multidisciplinary
  Complex
  Conflict
  Part of programs

## Slide 5: Goals and Trade-offs
The three goals of a project are:
  On time
  On budget
  To specification (including “quality” and “client satisfaction”)
The project manager meets the goals by making trade-offs.  shorten the project duration by using more resources.
An over determined project: has a fixed budget, fixed delivery time, and fixed specifications.
  No place for trade-offs. Is it good?

## Slide 6: Abilities Needed For Effective PM
Abilities Needed For Effective PM
  Conflict Resolution
  Creativity and Flexibility
  Ability to Adjust to Change
  Good Planning
  On time
  Negotiation
  In budget- replace Win-Lose by Win-Win

## Slide 7: Project Life Cycle: L-Shape and J-Shape
Resource allocation for S=shaped and J-shaped is quite different.

## Slide 8: Project Selection: Quantitative Methods
Financial Assessment Methods
  Payback period
  Discounted cash flow
    NPV
    IRR
    B/C
Scoring Methods
  Unweighted 0-1 factor method
  Weighted factor scoring method

## Slide 9: Payback Period
Number of years needed for the project to repay its initial fixed investment.
A project costs $100,000 and is expected to save the company $20,000 per year.
PP = $100,000 / $20,000 = 5 years
Shortcoming
  Ignores the time value of money, including interest rates and inflation.
  Ignores money earned after the payback period.

## Slide 10: Time Value of Money NPV-IRR

## Slide 11: Future Value (FV)
$100, put it in a bank. Interest rate = 10%. How much after 1 year. P = 100. F?
How much after 2 years?
How much after 3 years?
How much after N years
F = 100(1.1)N
F1 = 100 +0.1(100) = 100(1+0.1)
F2= 100(1+0.1) + 0.1(100(1+0.1)) =
F2= 100(1+0.1) (1+0.1) = 100(1.1)2
F3 = 100(1.1)2 + 0.1[100(1.1)2] =
F3 = 100(1.1)2 [1+0.1] = 100(1.1)2 [1.1] = 100(1.1)3

## Slide 12: Future Value (FV); Present Value (PV)
P: The initial vale
MARR: Minimum Acceptable Rate of Return
F= P(1+MARR)N
P = F/(1+MARR)N
P = F/(1+r)N
P = F(1+r)-N
r = the minimum acceptable rate of return
=FV(r, N,PMT,PV,0 EOY) =
=PV(r, N,PMT,FV,0 EOY) =

## Slide 13: Present Value Index Table

## Slide 14: Back to the PBP Example
The initial investment of a project at the end of year 0 is 10 million dollars. Depreciation is computed using straight-line method with accounting life of five years and zero salvage value. Net income before tax and depreciation is 3 million dollars per year. The tax rate is 40%. Compute net income after tax in Year 1. Compute net cash inflow in Year 1. At the end of year 7 we sell everything for 5 million dollars. Compute NPV and IRR.
Net Income Before Tax and Depreciation 3
Depreciation 2
Income Before Tax 1
Tax 0.4
Net Income After Tax 0.6
Cash Flow of Depreciation 2
Net cash flow per year 2.6
This is true for the first 5 yeas.

## Slide 15: Future Value (FV); Present Value (PV)
But after year 5 we do not have depreciation.
Therefore, the two million dollars depreciation is not a cost anymore.
Our revenue will increases by
2- 0.4(2) = 1.2 million dollars.
Net income after tax = 0.6+1.2 =1.8
Net Income Before Tax and Depreciation 3
Depreciation 0
Income Before Tax 3
Tax 0.4(3) =1.2
Net Income After Tax in Year 6 1.8
Net Income After Tax in Year 7 1.8+5-0.4(5) = 4.8

## Slide 16: Net Present Value (NPV)
I0 = the initial investment
Ft = the net cash flow in period t
r = the required rate of return
Important note: NPV function in excel assumes that the first cash flow is at the end of year 1.

## Slide 17: Internal Rate of Return (IRR)
The discount rate (r) that causes the NPV to be equal to zero.
The higher the IRR, the better.
In Excel “=IRR(Series,Guess)”
Compare IRR with MARR
Here it is not important where the first payment is – end of year 1 or end of year 0. The NPV for IRR is 0 everywhere.

## Slide 18: Your Mortgage; PMT and PPMT
100,000 loan
4% interest rate
30 years fixed
Your monthly payment
=PMT(monthly rate,#of months,pv,[fv], [type])
=PMT(0.04/12, 30*12, 100000)

## Slide 19: Practice
The initial investment of a project at the end of year 0 is 10 million dollars. Depreciation is computed using straight-line method with accounting life of 4 years and accounting salvage value of 0. Total revenue is 6 million dollars per year. All expenses, excluding depreciation and tax are 2 million dollars per year. Useful life of the project (which differs from accounting life) is 7 years. At the end of the useful life the project is sold for 2 million dollars. Tax rate of operating income as well as capital gain is 30%. Compute profit per year during the accounting life of the project.
Revenue 6
Operating Expenses 2
Net Income Before Tax and Depreciation 4
Depreciation 2.5
Income Before Tax 1.5
Tax 0.3(1.5) = 0.45
Net Income After Tax (years 1-4) 1.05

## Slide 20: Practice: Net Income vs. Net Cash Inflow
Compute net cash inflow during the accounting life of the project.
Net Income After Tax 1.05
Depreciation 2.5
Net Cash Inflow (years 1-4) 3.55
Compute net cash inflow per year after accounting life is over and before the last year of the useful life of the project.
Net Income After Tax 1.05
Depreciation added to the profit 2.5
Tax on the additional profit due to end of depreciation (0.3)(2.5) = 0.75
Net income added 2.5-0.75 = 1.75
Total Net Income 1.05+1.75= 2.8
Net Cash Inflow (years 5-6) 2.8

## Slide 21: I Am Sure It Was Easy to Grasp
If it was not easy to grasp, you may look at it from a different perspective
Revenue 6
Operating Expenses 2
Net Income Before Tax and Depreciation 4
Tax 0.3(4) = 1.2
Net Income After Tax (years 1-4) 2.8
Compute net cash inflow in the last year of the useful life of the project.
Net Income After Tax 2.8
Project Sold 2
Capital Gain Tax 0.3(2) = 0.6
Net Capital Gain 1.4
Net Cash inflow 2.8+1.4= 4.2

## Slide 22: Practice: Net Income vs. Net Cash Inflow
What is the net cash flow of the project during its useful life. Compute NPV under 10% MARR and IRR.

## Slide 23: Practice: Net Income vs. Net Cash Inflow
An investment at the end of year 0 has a depreciation life of 4 years and salvage value of 0. Depreciation is computed using straight line method and is 2.5 million dollars per year. Useful life of the project (which differs from accounting life) is 7 years. Other revenues and costs of the investment remain the same over the useful life of the investment. At the end of year 7, all the assets are sold for 2 million dollars. Tax rate of operating income as well as capital gain is 30%. The net income after depreciation and tax at the end of year 1 is 1.05 million dollars.
Compute the net cash flow in year 1.
1.05 + 2.5 = 3.55. It will remain the same in years 1-4
Compute the net cash flow in year 5.
1.05 + 2.5 – 0.3(2.5) = 2.8
1.05 + 0.7 (2.5) = 2.8
Compute the net cash flow in year 7
2.8 + 2 -0.3(2) = 2.8 + 0.7(2) = 2.8+1.4 = 4.2

## Slide 24: Internal Rate of Return (IRR)
The discount rate (r) that causes the NPV to be equal to zero
The higher the IRR, the better
In Excel “=IRR(Series,Guess)”
Compare IRR with MARR
Here it is not important where the first payment is – end of year 1 or end of year 0. The NPV for IRR is 0 everywhere.

## Slide 25: Profitability Index or B/C Ratio

## Slide 26: Present Value Index Table

## Slide 27: Profitability Models
Advantages
  Easy to use and understand
  Based on accounting data and forecasts
  Familiar and well understood
  Give a go/no-go indication
  Can be modified to include risk
Disadvantages
  Ignore non-monetary factors
  Discounting models (NPV, IRR) are biased to the short-term

## Slide 28: Scoring Models

## Slide 29: Weighted Scoring Model
Si = the total score of the ith project
sij = the score of the ith project on the jth criterion
wj = the weight or importance of the jth criterion

## Slide 30: Uncertainties Encountered in Project Management
Uncertainty in Project Management
  Time required to complete a project
  Availability of key resources
  Cost of resources
  Timing of solutions to technological problems
  Actions taken by Competitors and Complementors
  Actions taken by Government and Communities
Uncertainty cannot be eliminated, but if managed properly, it can be minimized.
This is why we need trade-offs.
Risk Analysis
  Estimate probabilities or distributions associated with key parameters
  Develop analytical or simulation model
  Analyze distribution of outcomes generated by the model

## Slide 31: Project Organization Project Manager, Organization, and Team

## Slide 32: Factors Increasing the Importance of Projects
Factors increasing the importance of projects
  Emphasis on time-to-market
  Need for specialized knowledge from a variety of areas
  Explosive rate of technological change
  Accountability and control
Who should be appointed as the PM?
  A technical expert?
  Someone with good organizational skills?

## Slide 33: Functional vs. Project Managers
Functional Manager
Expert in functional area
Full authority over employees
Competes for resources with other functional dept
Knows subordinates very well
Functional environment is fairly stable & people are comfortable in their jobs
Project Manager
May not be expert in any area
May have limited authority over employees
Competes for resources with other projects
May not have known subordinates very long
Project environment is temporary & people expect changes

## Slide 34: Roles a Project Manager
Manager: planning, organizing, staffing, budgeting, directing, and controlling.
Facilitator : facilitator vs. supervisor.
System Thinker: 2>1+1.
Communicator: with senior management, client, project team, vendors, functional managers.
Negotiator: with senior mgmt. for more human and capital resources, with functional manager to get a particular skills, with vendor for shorter lead time, with client about project changes (scope creep).
Politician: knows how to “get things done”, how to “work the system.”

## Slide 35: Facilitator vs. Supervisor
  Ensures that all resources and work are available when needed, problems are resolved, each task is properly concluded.
Resolves conflict with functional managers, the client and others. Manages conflicts by negotiation.
Assigns the responsibility for the planning and organization of tasks to team members.
Avoids Micromanagement which is one of the deadly managerial sins where s/he closely supervises and second-guesses (and instructs on) every decision a project member makes. The same is true for the relationship between the program manager and PM.

## Slide 36: Systems Engineering
The elephant was in a dark house; some Hindus had brought it for exhibition. In order to see it, many people were going, every one, into that darkness. As seeing it with the eye was impossible, each one was feeling it in the dark with the palm of his hand. The first approached the elephant, and happening to fall
Against his broad and sturdy side, at once began to bawl
"God bless me! but the elephant is very like a wall!"
The second, feeling of the tusk, cried, "Ho! what have we here
So very round and smooth and sharp? To me 'tis mighty clear
This wonder of an elephant is very like a spear!"
The third approached the animal, and happening to take
The squirming trunk within his hands, thus boldly up and spake
"I see," quoth he, "the elephant Is very like a snake!"

## Slide 37: Systems Engineering
The elephant was in a dark house; some Hindus had brought it for exhibition. In order to see it, many people were going, every one, into that darkness. As seeing it with the eye was impossible, each one was feeling it in the dark with the palm of his hand. The first approached the elephant, and happening to fall
Against his broad and sturdy side, at once began to bawl
"God bless me! but the elephant is very like a wall!"
The second, feeling of the tusk, cried, "Ho! what have we here
So very round and smooth and sharp? To me 'tis mighty clear
This wonder of an elephant is very like a spear!"
The third approached the animal, and happening to take
The squirming trunk within his hands, thus boldly up and spake
"I see," quoth he, "the elephant Is very like a snake!"

## Slide 38: Systems Engineering
The fourth reached out an eager hand, and felt about the knee.
"What most this wondrous beast is like, is mighty plain," quoth he;
" 'Tis clear enough the elephant is very like a tree!"
The fifth, who chanced to touch the ear, said: "E'en the blindest man
Can tell what this resembles most; Deny the fact who can
This marvel of an elephant , is very like a fan!"
The sixth no sooner had begun , about the beast to grope,
Than, seizing on the swinging tail , that fell within his scope,
"I see," quoth he, "the elephant Is very like a rope!“
Similarly, whenever anyone heard [a description of the elephant], he understood [it only in respect of] the part that he had touched.
On account of the [diverse] place [object] of view, their statements differed:
If there had been a candle in each one's hand, the difference would have gone out of their words.

## Slide 39: How To Develop Good PM Skills
Gain experience on the job
  work on project teams, manage small projects, work in different job areas to get breadth of experience
Seek out feedback from others; look for a mentor
Conduct a self-evaluation; learn from mistakes
Interview senior or star project managers
Participate in training programs
Join PMI, Toastmasters, other organizations
Read journals, magazines, books on Project Mgmt.
Volunteer with charities to gain some skills

## Slide 40: Project Manager Challenges
Dealing with many conflicts of opinions & interests
Handling job stress
Making goal tradeoffs when things go poorly
Staying within the budget
Meeting the project deadline
Achieving all desired project outcomes
Keeping all stakeholders happy
Time management
Balancing work time and family time (hrs/week)

## Slide 41: The Pure Project Organization
President
Project Manager
VP Marketing
VP
Manufacturing
VP
R&D
Manager
Project A
Manager
Project B
Marketing
Manufacturing
R&D
Human Resources
Marketing
Manufacturing
R&D
Human Resources

## Slide 42: Functional Project Organization
President
Manufacturing
Project
Marketing
R & D
Human Resources
Finance

## Slide 43: Matrix Project Organization
President
Program Manager
PM1
PM2
PM3
Manufacturing
3
1
0
Marketing
1 ½
4
1/2
Finance
½
¼
3
R&D
4
1 ½
1/2
Human Resources
½
¼
1
  Hard and soft matrix organization?

## Slide 44: Assignment of the Team to the Tasks – Can SOLVER in Excel Handle?

## Slide 45: Project Planning

## Slide 46: Matrix Project Organization
Project plan is a route map from project start to finish.
Project launch meeting sets the project scope, asks cooperation of others in the organization, demonstrates managerial commitment to the project, and initiates the project plan.
The Work Breakdown Structure, Linear Responsibility Chart, and Mind Mapping can be developed using the project plan.
Interface Coordination Map shows the ways in which different groups interact during the project life cycle.
Concurrent Engineering and Design Structure Matrix facilitate the task of integrating the work of various functional groups.
Participatory Management leads to empowered teams.

## Slide 47: Hierarchical Project Planning

## Slide 48: Project Action Plan

## Slide 49: Work Breakdown Structure (WBS)

## Slide 50: Linear Responsibility Chart (LRC)
The LRC is a matrix with project tasks listed in the rows and departments/individuals columns

## Slide 51: Mind Map
10K run to
raise $50K
for homeless
shelter
Transportation
Promotion
Prizes/recognition
Facilities
Safety
Refreshments
Clean-up
Route
Registration

## Slide 52: Mind Map – Second Level
52
Promotion
Investigate
past events
Interview
running
club
members
Print
Design
To schools
To sports
retailers
Prepare
mailing
Acquire
address
lists
Mail
promo
Monitor
airings
Purchase
air time
Produce
ads
TV and
radio ads
Mailings
Flyers
Research
Distribute

## Slide 53: Design Structure Matrix (DSM)
a
b
c
d
e
f
a
b
X
X
c
X
X
d
X
X
X
e
X
f
X
X
X
X -- information flow
a
b
c
d
e
f
a
b
X
O
c
X
O
d
X
X
e
X
f
X
X
X
X
tasks to be completed concurrently
X -- information flow
O -- potential rework situation

## Slide 54: Interface Map: Interdependencies Between Team Members
Program
manager
Project
manager
Chip
manager
Manufacturing
Process
technology
Cell library
group
Design
team
Layout
specialist
Project
schedule
Technical
overview
Chip
schedule
Test
vectors
Process
file
Cell
library
Chip
specification
Layout
Chip
design
High level
design
Schematic
Netlist
Verification
plan
Verification
vectors
Simulation
prelayout
Simulation
postlayout
Review
Review
Review
Use
Use
Create
Use
Create
Use
Use
Use
Create
Create
Use
Create
Use
Review
Review
contribute
Use
Use
Use
Create
Use
Review
Create

## Slide 55: Project Budgeting

## Slide 56: Budgeting
Budgeting: the process of forecasting what resources the project will require.
Cost estimating process: evaluating each work element for its resource requirement and then determining its costs. Forecasting required resources, quantities, timing, and costs
Formalization of the process: using forms and other simple procedures to improve the process of cost estimating.
Learning Curves and Tracking Signals: quantitative tools for improving cost estimations.
Projects are unique: risk pervades all elements of the project, and particularly performance, schedule, and budget.
Two methods of budgeting
Top-down Budgeting. Senior management decides how much the project should cost (the total project budget). The budget is divided among the activities.
bottom-up Budgeting. Cost are estimates by those responsible for each task. Estimates are rolled up for all activities to get the total project budget.

## Slide 57: S-shaped and J-shaped Project Life Cycles
S-shaped: with a somewhat reduced level of resources, a smaller than proportional cut will be made in the project’s objectives or performance. The top-down budgeting process is more acceptable
J-shaped: a larger than proportional budget cut will be made in the project’s performance. It is dangerous for upper management not to accept the bottom-up budget estimates

## Slide 58: Estimate of Project Cost- Made at Project Start & at Intermediate Points

## Slide 59: Risk Management Planning
Risk Identification
Risk Analysis: Evaluating the seriousness (magnitude) of risk and likelihood (probability)
  Qualitative
  Quantitative
Risk Response Planning
Risk Monitoring and Control
A structured approach to help identify, prioritize, and manage risk
  List ways project might fail
  Evaluate severity (S) of each failure
  Estimate likelihood (L) of each failure occurring
  Estimate ability to detect each failure (D)
  Calculate Risk Priority Number (RPN)
  Sort potential failures by their RPNs

## Slide 60: Quantitative Approaches to Risk Management
Game Theory
  The decision maker takes a pessimistic mind-set and selects a course of action that minimizes the maximum harm (the minimax solution) any outcome can render regardless of the probabilities
Expected Value
  The value of an outcome multiplied by the probability of that outcome occurring
Simulation
  Use standard deviation to quantify the amount of risk associated with a given project
  Use frequency charts to calculate the probability for any number of scenarios

## Slide 61: Learning Curves

## Slide 62: Learning Curves
Tn = the time required to complete the nth unit
T1 = the time required to complete the first unit
Time to produce nth unit with 85% learning (LR=0.85) when T1= 43
So, the 8th unit with 85% learning & T1=43:
r = (ln 8)/(ln 2) =
T8 = T1(LR)(ln 8)/(ln 2) = 43(.85)3 =

## Slide 63: Learning Curves
A firm has a project to produce 21 units of a new part for a customer.
The firm’s typical learning rate is 85%.
The first unit of the part that was produced (the prototype) required 43 hours to make.
Labor cost is $27 per hour.
Pricing policy is 3 times the total labor cost.
How much should customer be charged?

## Slide 64: Project Networks

## Slide 65: Project Scheduling
From Action Plan and WBS to Gantt chart and project network.
Project Network
  Critical Path Method (CPM)- Late 1950s
  Dupont De Nemours Inc. developed the method
  Deterministic activity durations
Program Evaluation and Review Technique (PERT)
  U.S. Navy, Booz-Allen Hamilton, and Lockeheed Aircraft
  Probabilistic activity durations
Risk analysis: likelihood of completing the project on time, on budget, to specifications
  Statistics
  Simulation

## Slide 66: Activity on Arrow

## Slide 67: Activity on Arrow Network
An Activity is an arc with two nodes at its beginning and its end
Task | Predecessor
a b c | -- a b
a
b
c
Task | Predecessor
a b c d | --- -- b a
a
b
d
c
Task | Predecessor
a b c d | --- a a a
a
b
d
c

## Slide 68: Activity on Arrow Network
Task | Predecessor
a b c d | --- -- -- a,b,c
a
b
d
c
Task | Predecessor
a b c d | --- a a b,c
a
b
d
c

## Slide 69: AoA: A Power Plant Construction Project
a
b
c
f
d
g
e
h
i
j

## Slide 70: Draw AOA
12/23/2023
Ardavan Asef-Vaziri
5-70
1
2
3
4
5
6
7
a = 6
b = 2
g = 9
h = 9
k = 6
d = 4
c = 5
e = 3
i = 4
f = 8
j = 7

## Slide 71: Activity on Node

## Slide 72: Draw Activity on Node Network
a:-
b:a
c:a
d:a
e: b
f:c
g:c
h:e,f
i: d,g
j: h,i
a
b
c
d
e
f
g
h
i
j

## Slide 73: Draw Activity on Node Network
A
Excavate
B
Lay Foundation
C
D
Rough Plumbing
Frame
E
F
G
Finish Exterior
HVAC
Rough Electric
H
Sheet Rock
Install Cabinets
I
J
Paint
K
Final Plumbing
L
Final Electric
M
Install
Flooring
Activity | Imm. Pred
A | --
B | A
C | B
D | B
E | D
F | D
G | D
H | C, E, F, G
I | H
J | H
K | I
L | J
M | K, L

## Slide 74: Critical Path Method (CPM)

## Slide 75: Critical Path Method
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
12/23/2023
5-1-75
Activity | Immediate Precedence | Duration
A1 | - | 4
A2 | - | 3
A3 | A1 | 6
A4 | A1 | 4
A5 | A2 | 2
A6 | A4, A5 | 3

## Slide 76: Critical Path Method: Paths
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
10
Critical Path is the longest path
11
8
How many path?
It is the shortest time to complete the project
12/23/2023

## Slide 77: Forward Path; Earliest Starts
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
0
0
0
0
0
0
4
3
3
4
4
3
4
4
10
8
5
5
8
10
8
11
11
11

## Slide 78: Forward Path
10
30
20
Max = 30
5
35
35
35
12/23/2023

## Slide 79: Backward Path; Latest Starts
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
0
0
0
0
0
0
4
3
3
4
4
3
4
4
10
8
5
5
8
10
8
11
11
11
11
11
11
11
5
5
8
8
8
8
8
4
6
4
6
6
3
3
4
0
0
11
12/23/2023

## Slide 80: Backward Path
30
30
30
Min = 35
5
35
45
30
12/23/2023

## Slide 81: Computing Slack Times
Task = duration
slack = xxxx
EST
EFT
LST
LFT
12/23/2023

## Slide 82: Critical Path, Slacks
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
0
0
4
3
3
4
4
10
8
5
8
11
11
11
11
5
8
8
8
4
6
6
3
4
0
11
12/23/2023

## Slide 83: Slack Times Example
Start
Finish
a=4
slack=
b=3
slack=
c=3
slack=
d=2
slack=
e=6
slack=
f=4
slack=
g=1
slack=
h=4
slack=
i=5
slack=
j=6
slack=
k=1
slack=
Task=dur
slack=xxx
EST
EFT
LFT
LST
12/23/2023

## Slide 84: Slack Times Example
Start
Finish
a=4
slack=
b=3
slack=
c=3
slack=
d=2
slack=
e=6
slack=
f=4
slack=
g=1
slack=
h=4
slack=
i=5
slack=
j=6
slack=
k=1
slack=
Task=dur
slack=xxx
EST
EFT
LFT
LST
12/23/2023
5-1-84
0
4
4
4
6
7
7
8
0
3
3
7
3
9
9
9
15
13
7
12
13
14
15

## Slide 85: Slack Times Example
5
8
Start
Finish
a=4
slack=
b=3
slack=
c=3
slack=
d=2
slack=
e=6
slack=
f=4
slack=
g=1
slack=
h=4
slack=
i=5
slack=
j=6
slack=
k=1
slack=
Task=dur
slack=xxx
EST
EFT
LFT
LST
12/23/2023
0
4
4
4
6
7
7
8
0
3
3
7
3
9
9
9
15
13
7
12
13
14
15
15
15
15
14
14
14
9
9
5
10
9
9
3
3
0
9
8
8
6
5
1
0
3
3
9
9
15
15
9
9
3
3
0

## Slide 86: Graphical Format
A
B
C
D
E
F
G
H
I
S
F

## Slide 87: Random Activities

## Slide 89: Program Evaluation and Review Technique (PERT)

## Slide 90: Activity Times in PERT
Optimistic (a)
  Activity duration to be ≤ a has 1% probability.  ≥ a has 99% probability
Pessimistic (b)
  Activity duration to be ≥ b has 1% probability  ≤ b has 99% probability
Most likely (m)
  The mode of the distribution
All possible task durations (or task costs) can be represented by statistical distributions

## Slide 91: Beta Distribution: The Probability Distribution of Activity Times
Mean = : TE = (a + 4m + b)/6
Standard deviation =  = (b-a)/6
Variance = 2 = [(b-a)/6]2

## Slide 92: 95% & 90% Levels
If we replace 99% with 95% level
  Activity duration to be ≤ a has 5% probability
  Activity duration to be ≥ b has 5% probability
  If we replace 99% with 90% level
  Activity duration to be ≤ a has 10% probability
  Activity duration to be ≥ b has 10% probability

## Slide 93: Probability of Completing the Critical Path on Time
We assume the various activities are statistically independent of each other
Individual variances (and mean) of the activities on a path can then be summed to find the variance (mean) of the path
Determine the mean and standard deviation of the critical path
Compute the probability of critical path being ≤ a
DCP = the desired completion date of the critical path
mCP= the sum of the TE for the activities on the critical path
2CP = the sum of the variances of the activities on the critical path
Given Z, the probability of having the standard normal variable being ≤ Z is the probability of completing the project in a time ≤ D

## Slide 94: Selecting Risk and Finding D
Find all paths in the network
Compute mean and standard deviation of each path
Compute the probability of completing each path in ≤ the given time
Calculate the probability that the entire project is completed within the specified time by multiplying these probabilities together

## Slide 95: Critical Path Method: Paths
A1
A3
A4
A6
A5
A2
4,1
3,0.5
6,2
4,1
2,0.5
3,1
E
S
10
The first number is the mean; the second is standard deviation.
11
8
Suppose all activities have beta distribution

## Slide 96: Probability of Completing CP in 12 days
DCP = the desired completion date of the critical path
mCP= 4+4+3 = 11
2CP = 12+12+12 = 3
CP = 1.73
Z= 0.58  P(z≤0.58) = 0.72
What is the probability of competing the critical path in a maximum of 12 days?

## Slide 97: Selecting Risk and Finding CP Time
With a probability of 90%, in how many days will the CP be completed?
From Standard Normal Table  Z 90% = 1.28

## Slide 98: Probability of Completing The Project in 12 days
mCP= 6+4 = 10
2CP = 12+22 = 5
CP = 2.24
Z= (12-10)/2.24 = 0.89  P(z≤0.89) = 0.81
The probability of completing the critical path in not more than 12 days was 0.72. We need to compute this probability for blue path and green path too, and then multiply these probabilities
mCP= 3+2+3 = 8
2CP = 0.52+0.52+12 = 1.22
CP = 1.1
Z= (12-8)/1.1 = 3.63  P(z≤3.63) ≈ 1
The probability of competing the Project in not more than 12 days is 0.72×0.81×1 = 0.58

## Slide 99: Problem- PERT
a
d
g
h
e
f
c
b
Activity | Immediate Predecessor | Optimistic Duration | Most Likely | Pessimistic Duration | Expected Duration te | Vt Variance
a | -- | 15 | 18 | 20 |  | 
b | -- | 20 | 20 | 22 |  | 
c | -- | 12 | 14 | 16 |  | 
d | a | 7 | 7 | 7 |  | 
e | b | 8 | 11 | 12 |  | 
f | c | 17 | 21 | 24 |  | 
g | b,d | 10 | 12 | 15 |  | 
h | e,f | 9 | 10 | 11 |  | 
Find the Critical path:
Compute expected duration of CP m cp=
Compute Standard deviation of critical path σcp =
Prob( TCP≤ 48)?, Prob(TCP ≤ 43)? , Prob(43 ≤TCP≤ 48)?
Find a completion date that you’re 80% sure you can meet.
Prob( TProject≤ 43)?

## Slide 100: Goldratt’s Critical Chain & Srinivansan’s Contributions

## Slide 101: Srinivasan’s Notes on Goldratt’s Critical Chain ritical Path Method
In 1997, Goldratt introduced the Critical Chain methodology to apply Theory of Constraints concepts to manage projects.
The Critical Chain methodology expands on the notion of a critical path and helps determine where buffers should be placed to prevent unplanned disruptions from delaying project completion.
To schedule work is also to schedule resource usage. Resource availability constrains all solutions to the scheduling problem.
Project management is fundamentally concerned with effectively trading off performance, cost, and time. Yet, to what extent is the need to make these trade-offs caused by human decisions and practices?
A project has four sets of activities that must be completed before a synchronization operation, represented by C4 can be completed.
Use historical data to obtain an estimate of the average time for each activity.
Sum these estimates to obtain the average time it takes each series of activities that must be completed before C4 can begin.

## Slide 102: The Critical Chain Concept
Feeding Buffer
Feeding Buffer
Feeding Buffer
Project Buffer
Start Date
A1
A2
B1
B2
C1
C2
C3
C4
D1
D2
Critical Chain
Completion Date
Time
An analysis reveals that the series of activities with the longest average time is C1-C2-C3.
This is the Critical Chain and the activities along the critical chain are termed critical activities.

## Slide 103: Estimating Task Times: 3 Project Scenario
The primary difference is the degree of interdependence across the paths.
  Scenario 1: there is only a single path
  Scenario 2: the path B-C-D-E is preceded by three activities A1, A2, & A3. The completion of path B-C-D-E depends on which of its three preceding tasks takes the longest
  Scenario 3: there are two completely independent paths each consisting of five tasks
All three tasks require 10 days to complete.
What completion time would you calculate for each project?
Project times are not known with certainty
Activities that take less than the expected time tend to cancel out the variability of activities that take more than the expected completion time for the project.

## Slide 104: The Critical Chain Concept

## Slide 105: Path Simulation

## Slide 106: Common Chain of Events
12/23/2023
Ardavan Asef-Vaziri
106
According to Goldratt, activities dealing with resource allocation lead to the following chain of events.
  Assuming that the activity times are known and that the paths are independent leads to underestimating the actual amount of time needed to complete the project.
  Because the time needed to complete the project is underestimated, project team members tend to inflate their time estimates.
  Inflated time estimates lead to work filling available time, workers not reporting that a task has been completed early, and the ever-present student syndrome.
  An important caveat than becomes that safety time is usually visible to project workers and is often misused.
  Misused safety time further complicates the task of prioritizing project activities.
  Hidden safety time further complicates the task of prioritizing project activities.
  The lack of clear priorities likely results in poor multitasking.
  Task durations increase as a result of poor multitasking.
  Uneven demand on resources- some overloaded and others underloaded- may also occur as a result of poor multitasking.
  In an effort to utilize all resources fully, more projects will be undertaken to make sure that no resources are underutilized.
  Adding more projects further increases poor multitasking.

## Slide 107: Critical Chain Project Management
12/23/2023
Ardavan Asef-Vaziri
107
Identify the critical chain: set of tasks that determine the overall duration of the project
Use deterministic CPM model with buffers to deal with uncertainty
Remove padding from activity estimates (otherwise, slack will be wasted). Estimate task durations at median.
Place project buffer after last task to protect customer’s completion schedule
Exploit constraining resource(s)
Avoid wasting slack times by encouraging early task completions
Have project team focus 100% effort on critical tasks
Work to your plan and avoid tampering
Carefully monitor and communicate buffer status

## Slide 108: Critical Chain Project Management
12/23/2023
Ardavan Asef-Vaziri
108

## Slide 109: Project Crashing

## Slide 110: Crashing
Crashing: shortening duration of activities. Because
  Some activities were delayed.
  Client is willing to pay more for earlier completion.
Crashing changes the schedule for remaining activities.
It has impact on schedules for all the subcontractors.
Often introduces unanticipated problems.
The faster an activity is completed, the more it costs.
There is always a lower bound on task duration.

## Slide 111: Linear Time / Cost Tradeoff
Time
Cost
Crash point
Normal point
Normal time
Crash time
Normal cost
Crash cost
Slope (bj) = increase in cost from reducing task duration by one time unit

## Slide 112: Crashing Algorithm
Assume each task can be crashed one day at a time (simplifying assumption, but not necessary)
Crash only critical activities. Crashing other activities can only increase cost without changing project duration
To decrease project duration by one day, the critical path or paths must decrease by one day.
  Find the critical path or paths
  If there is no other critical activity which could still be reduced, and shorten the critical path. Stop.
  Crash the cheapest critical activity (or combination of activities) to shorten the critical path (or paths) by one day.
  Go to 1

## Slide 113: Crashing 21 Days to 20 Days Network
Activities A,C, and F are on Critical Path. A and C are the least-cost choice. We crash A because it affects two paths. Lower A’s normal time by one day.
It now equals the crash time and cannot be shortened further.
The critical path is unchanged.
The critical time will be lowered to 20 days.
The cost of the project will be $400+30(A)= $430.

## Slide 114: Crashing 20 Days to 19 Days Network
Activities A,C, & F are still on the critical path.
A cannot be crashed any more. C is the least-cost choice.
Lower C’s normal time by one day. The critical path is unchanged
The critical time will be lowered to 19 days
The cost of the project will be $400+ 30(A) + 30(C) = $460

## Slide 115: Crashing 19 Days to 18 Days Network
All activities are now critical. 3 paths; ACF,EDG, and BEG. A cannot be crashed any more. The only way to crash ACF is to crash C or F. C is cheaper.
On ADG path, A and D cannot be crashed. The only way to crash ADG is to crash G. Crashing G crashes BEG path too.
The critical time will be lowered to 18 days
The cost of the project will be $400+ 30(A) + 30(C2) + 60(G) = $550

## Slide 116: Crashing 18 Days to 17 Days Network
All activities are critical. There are three paces ACF, ADG, and BEG.
Crash F and G by 1 at cost of 60 +40 = 100
The critical time has been lowered to 17 days
The cost of the project is $400+ 30(A) + 30(C2) + 60(G2)+40(F) = $650

## Slide 117: Crashing 17 Days to 16 Days Network
We can shorten the project to 16 days by crashing F and G by another day.
The cost of the project is $400+ 30(A) + 30(C2) + 60(G3)+40(F2) = $750
Activities A,C,F, and g have been crashed to their limits.
No further crashing will help so B,D, and E remain at their normal times and costs.

## Slide 118: Time-Cost Tradeoff

## Slide 119: Crash the Following Network. Prepare Cost-time Curve

## Slide 120: Crash the Following Network. Prepare Cost-time Curve

## Slide 121: Crash the Following Network. Prepare Cost-time Curve

## Slide 122: Crash the Following Network. Prepare Cost-time Curve

## Slide 123: Crash the Following Network. Prepare Cost-time Curve

## Slide 124: Crash the Following Network. Prepare Cost-time Curve

## Slide 125: Time-Cost Curve
Ardavan Asef-Vaziri
e+a
0 2 4 6 8 10
Total Duration (Days)
All crash
e(2)+a+d(2)+b
e(2)+a+d
e
All normal
$400
300
200
100

## Slide 126: Practice
The same example as we solved. Activity c either 0 or 2 but not 1. Solve it in the easiest way. Prepare Time-Cost Trade-off Curve