## Slide 1
Project Management
306

## Slide 2: Scheduling the Project
From Action Plan and WBS to Gantt chart and project network.
Project Network
  Critical Path Method (CPM)
  Program Evaluation and Review Technique (PERT)
Risk analysis: likelihood of completing the project on time, on budget, to specifications
  Statistics
  Simulation
7/10/2022
5-1-2
CPM; Deterministic activity durations
PERT; Probabilistic activity durations

## Slide 3: Draw Activity on Node Network
a:-
b:a
c:a
d:a
e: b
f:c
g:c
h:e,f
i: d,g
j: h,i
5-1-3
a
b
c
d
e
f
g
h
i
j

## Slide 4: An Activity-On-Node (AON) Network
A
Excavate
B
Lay Foundation
C
D
Rough Plumbing
Frame
E
F
G
Finish Exterior
HVAC
Rough Electric
H
Sheet Rock
Install Cabinets
I
J
Paint
K
Final Plumbing
L
Final Electric
M
Install
Flooring
Activity | Imm. Pred
A | --
B | A
C | B
D | B
E | D
F | D
G | D
H | C, E, F, G
I | H
J | H
K | I
L | J
M | K, L

## Slide 5: Critical Path Method
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
7/10/2022
5-1-5
Activity | Immediate Precedence | Duration
A1 | - | 4
A2 | - | 3
A3 | A1 | 6
A4 | A1 | 4
A5 | A2 | 2
A6 | A4, A5 | 3

## Slide 6: Critical Path Method: Paths
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
10
Critical Path is the longest path
11
8
How many path?
It is the shortest time to complete the project
7/10/2022

## Slide 7: Forward Path; Earliest Starts
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
0
0
0
0
0
0
4
3
3
4
4
3
4
4
10
8
5
5
8
10
8
11
11
11

## Slide 8: Forward Path
10
30
20
Max = 30
5
35
35
35
7/10/2022

## Slide 9: Backward Path; Latest Starts
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
0
0
0
0
0
0
4
3
3
4
4
3
4
4
10
8
5
5
8
10
8
11
11
11
11
11
11
11
5
5
8
8
8
8
8
4
6
4
6
6
3
3
4
0
0
11
7/10/2022

## Slide 10: Backward Path
30
30
30
Min = 35
5
35
45
30
7/10/2022

## Slide 11: Computing Slack Times
Task = duration
slack = xxxx
EST
EFT
LST
LFT
7/10/2022

## Slide 12: Critical Path, Slacks
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
0
0
4
3
3
4
4
10
8
5
8
11
11
11
11
5
8
8
8
4
6
6
3
4
0
11
7/10/2022

## Slide 13: Project vs Process- Flow Time, Theoretical Flow Time
A1
A3
A4
A6
A5
A2
4
3
6
4
2
3
E
S
W1
W2
W4
W3
W6
W7
W5
W9
W8
The time of the critical path differs from the time of the theoretical critical path. Why?
The critical path itself also may differ from the theoretical critical path. Why?

## Slide 14: Slack Times Example
Start
Finish
a=4
slack=
b=3
slack=
c=3
slack=
d=2
slack=
e=6
slack=
f=4
slack=
g=1
slack=
h=4
slack=
i=5
slack=
j=6
slack=
k=1
slack=
Task=dur
slack=xxx
EST
EFT
LFT
LST
7/10/2022

## Slide 15: Slack Times Example
Start
Finish
a=4
slack=
b=3
slack=
c=3
slack=
d=2
slack=
e=6
slack=
f=4
slack=
g=1
slack=
h=4
slack=
i=5
slack=
j=6
slack=
k=1
slack=
Task=dur
slack=xxx
EST
EFT
LFT
LST
7/10/2022
5-1-15
0
4
4
4
6
7
7
8
0
3
3
7
3
9
9
9
15
13
7
12
13
14
15

## Slide 16: Slack Times Example
5
8
Start
Finish
a=4
slack=
b=3
slack=
c=3
slack=
d=2
slack=
e=6
slack=
f=4
slack=
g=1
slack=
h=4
slack=
i=5
slack=
j=6
slack=
k=1
slack=
Task=dur
slack=xxx
EST
EFT
LFT
LST
7/10/2022
0
4
4
4
6
7
7
8
0
3
3
7
3
9
9
9
15
13
7
12
13
14
15
15
15
15
14
14
14
9
9
5
10
9
9
3
3
0
9
8
8
6
5
1
0
3
3
9
9
15
15
9
9
3
3
0

## Slide 17: Graphical Format
A
B
C
D
E
F
G
H
I
S
F

## Slide 18: A Key Problem: The Impact Converging Activities
15
Activity 2
15
Activity 1
15
Activity
15
Activity 2
15
Activity 1
Which process has a longer flow time?.
In a deterministic world they both have a flow time of 30 mins.
The situation differs in real world where nothing is deterministic.
Suppose instead of an exact number of 15, the activity time is uniformly distributed in the range of 10 to 20. The average is still 15.

## Slide 19: A Key Problem: The Impact Converging Activities
Activity time = 10+10rand()
rand() is a random number between 0 and 1.
If it is ranch = 0, the duration of the activity is 10, if rand() = 1, 1, the duration of the activity is 20.
For all possible rand() 10 ≤ Activity Time ≤ 20
For the fist project, the project duration is computed as the duration of Activity 1 + duration of Activity 2. That is
10+10rand()+10+10rand()
We can generate 1000 instance of each activity in excel and compute project duration.

## Slide 20: A Key Problem: The Impact Converging Activities
For project 2, still duration of all the activities are computed as 10 ≤ 10+10rand() ≤ 20
However, the the project duration is computed as the MAX duration of (Activity 1, Activity 2) + duration of Activity 3.
Max duration of (Activity 1, Activity 2) > 10+10rand().
That is the significance of convergence points.
Not even in a single instance the duration of Project 1 was greater that that of Prject 2.

## Slide 21: Key Problem Flow time: 10,000 Instances

## Slide 22: Converging Activities + Common Resources
Activity R2
Activity B2
Activity B1
Activity R1
Activity G
All activities are [10,20] minutes. 10+10RAND(). Average 15.
One Recourse Red, One Resource Blue, One Resource Green.
Project Duration >> 45

## Slide 24
Chart: