The solutions for all assigned problems are given below.

I have also included some qualitative and quantitative questions similar to the questions in Midterm I

SampleMid1Q1. What are the main differences between NPV, IRR, and B/C?

SampleMid1Q2. What advantages are lost if the sum of the weights in a weighted scoring approach does not add to 1.0?  Why is it suggested that factors with less than 2 percent or 3 percent impact not be considered in this approach?

SampleMid1Q3. When it comes to assigning individuals to work on projects, functional managers and project managers are often in conflict. How can the PM resolve this problem?

SampleMid1Q4. Which technique can provides almost all information provided by an interface map?

70%

20%

10%

5M

15M

30M

Technically Infeasible

Extraordinary  com. success

Average com. success

Commercial failure  success

-6M

Invest

-5M

Design a new Product

70%

Technically Feasible

SampleMid1P1. All cash inflow/outflow in this problem occur at the end of the corresponding year. The design of a new product is expected to take one year at a cost of 5M. There is a 0.7 probability that the project will be technically feasible. If feasible, it can be launched with an estimated cost of $6M paid in Year 2. If launched, the useful life of the project is only one year with no salvage value at the end of Year 3. When launched, it will be in one of the following three states: (1) Extraordinary commercial success with probability of 0.2, earning a net after-tax cash inflow of $30M.  (2) Average commercial success with probability of 0.7, earning the net after-tax cash inflow of $15M.  (3) Commercial failure earning the net after-tax cash inflow is $5M.  The discount rate is 10 percent.   Compute the expected commercial value of this project.

Expected return in Year 3  if the project is technically feasible = 0.2*30+0.7*15+0.1*5

Expected return in Year 3  if the project is technically feasible =  17M

The present value of this cash flow at the end of year 2 is 17/1.1 = 15.45M

The investment at the end of Year 2 is -6M. Therefore, the net present value at the end of year 2 is 15.45 – 6 = 9.45.

But there is only 70% probability for this line. Therefore, the expected cash flow is

9.45*.7 = 6.61M. Furthermore, it is a cash flow at the end of Year 2.

The present value of this cash flow at the end of year 1 is 6.61/1.1 = 6.01M

Since the initial investment is –5, the net present  value of the project at the end of year 1 is  6.01-5 = 1.01

Expected commercial value at the end of year 0 is  1.01/1.1 = 0.92

Chapter 1

Problem19.

I have solved this problem in 3 ways

1) Using statistics

2) Using Excel

The analytical solution is preferred.

a) Analytical solution

The Present Value of the “Mean” of each cash flow is:

Mean I0 = -75000

Mean P1 = 20000(1.2)(-1)   = 16666.7

Mean P2 = 25000(1.2)(-2)   = 17361.1

Mean P3 = 30000(1.2)(-3)  =  17361.1

Mean P4 = 50000(1.2)(-4)  =  24112.7

The Present Value of the “Mean” of NPV is:

Mean NPV = -75000+16666.7+17361.1+17361.1+24112.7 = 501.6

The  Present Value of the “Standard Deviation ” of each cash flow is:

Standard Deviation  I0 = 0

Standard Deviation  P1 = (1.2)(-1) (1000)  = 833.3

Standard Deviation  P2 = (1.2)(-2) (1500)  = 1041.7

Standard Deviation  P3 = (1.2)(-3) (2000)  = 1157.4

Standard Deviation  P4 = (1.2)(-4) (3500)  = 1687.9

The Present Value of the “Standard Deviation ” of NPV is:

Variance NPV =  Variance I0 +Variance P1+ Variance P2 + Variance P3+ Variance P4

Variance NPV =  5968064

Standard Deviation of NPV = 2443

Therefore, NPV is a Normal Variable with Mean of 501.6 and Standard Deviation of 2443

Z = (0-501.6)/2443 = -0.21

If you look at the Normal table in your book, you will see that the probability associated with +0.21 is 58.3%. That is the area to the left or +.21. Therefore the area to the right of -0.21 is the same  58.3%.

P(NPV≥0) = 58.3

If you solve the problem using Crystal Ball – see below – you will get P(NPV≥0) = 59.6.

If you solve the problem using Crystal Ball – see below – you will get P(NPV≥0) = 56.9.

The analytical solution is a rigorous reliable solution.

b) Solution to Problem 19 using random

This is the result for only one replication. Ti see the functions please double click on the Table.

The histogram of  NPV  for 1000 replications is shown below

As we can see. P(NPV≤0) = 43.1%   P(NPV≥0) = 56.9%