Project/Project information /start date etc

Enter data and precedence (Table 5-2 page 149)

A	5	-

B	4	-

C	3	a

D	4	a

E	6	a

F	4	b,c

G	5	d

H	6	d,e

I	6	f

J	4	g,h

Add Start and End

View/View Bar

View/zoom/entire project

Network, right click on white background, allow manual position

To see the slacks

View/more/view/Detail Gantt

Or

Table/Schedule

Project/filter/critical

Summary Task: Table 3-5 or 5-3?

PERT Analysis

View/Toolbars/PERT Analysis

Click on Pert Entry sheet icon

To transform all times in a unique unit

Tools/Options

Schedule Tab  select weeks

The schedule tab is where you modify the default settings for entering tasks.

Ignore Duration for now, these will be calculated

Ignore Resource Names, we will learn this in a later lesson

Duration is now in weeks… 1day/5days= .2wks

Enter data from Table 5-6

Click on Pert Calculate icon

Click Yes ( you may want to save the pre-existing project before doing this, as it will overwrite any previous entries in duration).

Calendar

Standard calendar: 8 hrs/wk, 5days/wk

Click on calendar icon

Month/week/ custom (to choose a specific time interval)

  forward backward buttons

To modify calendar structure  Format/TimeScale

Here we can modify: (Monthly, daily, & weekly titles,  Display all days/work days, Date boxes, shading, and more)

To Create 2nd,  3rd, …. Calendars

Tools/change working time

Select create new calendar

Name your calendar: Type the name of your calendar

Make a copy of Standard

Click on detail bottom

You can also Modify the schedule for the work week: (hypothetical, get off @ 1 on Fridays)

Choose the Work Weeks Tab (in the same Change Working Time box)

Enter the Name, Start date, and End date (in this ex., Early Fridays will apply for the length of the project).

Early Friday. Recurrence: weekly

Apply project calendar to the entire project

Project/Project Information/ Calendar dropdown/select calendar/OK

In the calendar view you can now see changes have been applied. May 5 no longer scheduled, Early Friday

Gantt and Network also updated

WBS

Part 2

From 5 days a week to 7 days

Tools/ Change Working Time/ Work Weeks/Details/ Select all seven days/ Set days to specific Working Times/Set the whole week to an 8 hour shift/ OK