## P4_17
17. A light manufacturing firm has set up a project for developing a new machine for one of its production lines.
The most likely estimated cost of the project it­self is $1,000,000, but the most optimistic estimate is $900,000 while the pessimists predict a project cost of $1,200,000.
The real problem is that even if the project costs are within those limits, if the project it­ self plus its implementation costs exceed $1,425,000, the project will not meet the firm's NPV hurdle.
There are four cost categories involved in adding the prospective new machine to the production line:
(1) engineering labor cost, (2) nonengineering labor cost, (3) assorted material cost, and (4) production line down-time cost.
Engineering human resource 600 + 15% Hours @ $80/hr
Nonengineering human resource Opt 1200 Exp 1500 Pess 2200 Hours @ $35/hr
Material $100000, 135000, 155000
Production time lost 105, 110, 120 @500 profit per hour
Probability the project meet NPV requirements

## Generate
Investment |  | Engineering |  | Nonengineering |  | Material |  | ProductionLost
a= | 900000 | a= | 40800 | a= | 42000 | a= | 100000 | a= | 52500
b= | 1200000 | b= | 55200 | b= | 77000 | b= | 155000 | b= | 60000
m= | 1000000 | m= | 48000 | m= | 52500 | m= | 135000 | m= | 55000
LeftArea= | 0.33333 | LeftArea= | 0.5 | LeftArea= | 0.3 | LeftArea= | 0.63636 | LeftArea= | 0.33333
(m-a)(b-a)= | 30000000000 | (m-a)(b-a)= | 103680000 | (m-a)(b-a)= | 367500000 | (m-a)(b-a)= | 1925000000 | (m-a)(b-a)= | 18750000
(b-m)(b-a)= | 60000000000 | (b-m)(b-a)= | 103680000 | (b-m)(b-a)= | 857500000 | (b-m)(b-a)= | 1100000000 | (b-m)(b-a)= | 37500000
Uniform PS | Triangle | Uniform PS | Triangle | Uniform PS | Triangle | Uniform PS | Triangle | Uniform PS | Triangle | Total
0.50303 | 1027319.8764 | 0.45048 | 47634.1602 | 0.64604 | 59578.2596 | 0.64604 | 135268.0132 | 0.64604 | 56356.7405 | 1326157.0499
0.44442 | 1017422.1888 | 0.44746 | 47611.2138 | 0.72419 | 61621.2254 | 0.72419 | 137581.8907 | 0.72419 | 56783.9684 | 1321020.4871
0.093161 | 952866.2378 | 0.030469 | 42577.3683 | 0.12823 | 48864.8245 | 0.12823 | 115711.4452 | 0.12823 | 54050.6058 | 1214070.4816
0.30601 | 995814.5752 | 0.235 | 45736.0338 | 0.25081 | 51600.7264 | 0.25081 | 121973.0725 | 0.25081 | 54668.583 | 1269792.991
0.34744 | 1002127.6065 | 0.83638 | 51081.2137 | 0.22006 | 50992.8805 | 0.22006 | 120581.9026 | 0.22006 | 54531.2847 | 1279314.888
0.98419 | 1169200.5084 | 0.2046 | 45405.7091 | 0.50327 | 56361.4797 | 0.50327 | 131125.376 | 0.50327 | 55684.0428 | 1457777.116
0.19472 | 976429.4647 | 0.58289 | 48623.808 | 0.086405 | 47635.0419 | 0.086405 | 112896.8559 | 0.086405 | 53772.8262 | 1239357.9967
0.28359 | 992237.2851 | 0.058756 | 43268.1703 | 0.62421 | 59048.9028 | 0.62421 | 134664.1001 | 0.62421 | 56246.0406 | 1285464.4989
0.91152 | 1127138.1602 | 0.40424 | 47273.8795 | 0.68868 | 60661.0861 | 0.68868 | 136494.4302 | 0.68868 | 56583.1827 | 1428150.7387
0.061584 | 942982.9288 | 0.057189 | 43235.0297 | 0.63114 | 59215.367 | 0.63114 | 134856.1918 | 0.63114 | 56280.8519 | 1236570.3692
0.3423 | 1001349.9916 | 0.00017748 | 40935.6515 | 0.35685 | 53515.9118 | 0.35685 | 126209.4142 | 0.35685 | 55088.9736 | 1277099.9427
0.87011 | 1111719.0849 | 0.64779 | 49157.0603 | 0.32803 | 52995.5267 | 0.32803 | 125128.8024 | 0.32803 | 54980.0307 | 1393980.5052
0.20753 | 978904.3413 | 0.78828 | 50514.7581 | 0.2037 | 50652.227 | 0.2037 | 119802.2528 | 0.2037 | 54454.3389 | 1254327.918
0.43129 | 1015276.9758 | 0.1836 | 45162.9659 | 0.68816 | 60647.4448 | 0.68816 | 136478.98 | 0.68816 | 56580.33 | 1314146.6966
0.86009 | 1108377.1756 | 0.4768 | 47830.9797 | 0.087129 | 47658.6239 | 0.087129 | 112950.8277 | 0.087129 | 53778.1529 | 1370595.7598
0.22668 | 982464.2807 | 0.4732 | 47804.3707 | 0.62253 | 59008.9069 | 0.62253 | 134617.5202 | 0.62253 | 56237.6766 | 1280132.7552
0.22541 | 982232.7076 | 0.9283 | 52473.4973 | 0.21885 | 50968.0383 | 0.21885 | 120525.0466 | 0.21885 | 54525.6734 | 1260724.9633
0.51004 | 1028541.9943 | 0.80067 | 50653.9119 | 0.71878 | 61471.0938 | 0.71878 | 137411.8507 | 0.71878 | 56752.5727 | 1334831.4235
0.039648 | 934488.3895 | 0.67474 | 49392.8093 | 0.69726 | 60888.0147 | 0.69726 | 136751.4511 | 0.69726 | 56630.6384 | 1238151.3029
0.45615 | 1019359.1723 | 0.97882 | 53718.1979 | 0.76596 | 62833.4653 | 0.76596 | 138954.8823 | 0.76596 | 57037.4738 | 1331903.1917
0.91888 | 1130234.8434 | 0.48206 | 47869.655 | 0.30352 | 52561.7317 | 0.30352 | 124171.9245 | 0.30352 | 54885.5938 | 1409723.7484
0.66722 | 1058696.5215 | 0.030789 | 42586.6825 | 0.57181 | 57838.1915 | 0.57181 | 133177.2483 | 0.57181 | 55992.8549 | 1348291.4987
0.78414 | 1086195.3211 | 0.33779 | 46717.9137 | 0.94806 | 70326.4432 | 0.94806 | 147441.4823 | 0.94806 | 58604.4162 | 1409285.5765
0.66982 | 1059249.2219 | 0.64303 | 49116.337 | 0.33558 | 53130.743 | 0.33558 | 125416.3064 | 0.33558 | 55008.4265 | 1341921.0348
0.28815 | 992975.4322 | 0.52569 | 48187.3752 | 0.67063 | 60194.156 | 0.67063 | 135965.5818 | 0.67063 | 56485.5376 | 1293808.0828
0.47235 | 1022069.5189 | 0.97163 | 53484.9437 | 0.41111 | 54528.3861 | 0.41111 | 128131.5868 | 0.41111 | 55300.7036 | 1313515.1391
0.6954 | 1064810.5436 | 0.72693 | 49879.1347 | 0.23692 | 51330.9719 | 0.23692 | 121355.6884 | 0.23692 | 54607.6517 | 1341983.9903
0.14776 | 966578.5113 | 0.19068 | 45246.348 | 0.11225 | 48422.7588 | 0.11225 | 114699.6944 | 0.11225 | 53950.7533 | 1228898.0659
0.14818 | 966673.0155 | 0.16338 | 44915.6918 | 0.96686 | 71669.0607 | 0.96686 | 148962.1403 | 0.96686 | 58885.1863 | 1291105.0945
0.5001 | 1026811.9877 | 0.85535 | 51327.3115 | 0.56193 | 57618.4117 | 0.56193 | 132889.4077 | 0.56193 | 55946.8943 | 1324594.0128
0.82832 | 1098505.8605 | 0.86056 | 51397.6977 | 0.93212 | 69370.3624 | 0.93212 | 146358.6183 | 0.93212 | 58404.4792 | 1424037.018
0.73078 | 1072904.5024 | 0.83603 | 51076.8461 | 0.034298 | 45550.2736 | 0.034298 | 108125.4705 | 0.034298 | 53301.9251 | 1330959.0176
0.90146 | 1123109.7504 | 0.94716 | 52859.4769 | 0.0077254 | 43684.9613 | 0.0077254 | 103856.3516 | 0.0077254 | 52880.594 | 1376391.1342
0.56701 | 1038818.4911 | 0.16728 | 44964.6155 | 0.16133 | 49700.0347 | 0.16133 | 117622.9811 | 0.16133 | 54239.2605 | 1305345.3829
0.54199 | 1034227.6083 | 0.74517 | 50059.9008 | 0.99927 | 76207.7832 | 0.99927 | 154102.7297 | 0.99927 | 59834.3305 | 1374432.3525
0.41562 | 1012749.7613 | 0.68772 | 49509.9415 | 0.35017 | 53394.3363 | 0.35017 | 125963.0783 | 0.35017 | 55063.5495 | 1296680.6669
0.0025897 | 908814.3167 | 0.44255 | 47573.7752 | 0.22227 | 51038.0109 | 0.22227 | 120685.1921 | 0.22227 | 54541.4786 | 1182652.7735
0.21221 | 979789.4083 | 0.61879 | 48913.1613 | 0.25611 | 51701.6336 | 0.25611 | 122204.0176 | 0.25611 | 54691.3757 | 1257299.5965
0.18847 | 975193.6319 | 0.86905 | 51515.2648 | 0.33549 | 53129.1779 | 0.33549 | 125413.0064 | 0.33549 | 55008.0992 | 1260259.1803
0.024843 | 927300.1663 | 0.96057 | 53177.9931 | 0.92088 | 68763.1833 | 0.92088 | 145670.923 | 0.92088 | 58277.505 | 1253189.7707
0.57122 | 1039603.3972 | 0.11774 | 44293.9659 | 0.42663 | 54826.5703 | 0.42663 | 128657.8307 | 0.42663 | 55363.0604 | 1322744.8244
0.55335 | 1036296.4701 | 0.26639 | 46055.4019 | 0.73831 | 62020.1304 | 0.73831 | 138033.6934 | 0.73831 | 56867.388 | 1339273.0839
0.92124 | 1131256.1516 | 0.68018 | 49441.645 | 0.76225 | 62721.567 | 0.76225 | 138828.1454 | 0.76225 | 57014.0735 | 1439261.5825
0.69522 | 1064770.6769 | 0.13311 | 44514.9297 | 0.66383 | 60021.7036 | 0.66383 | 135770.2611 | 0.66383 | 56449.4741 | 1361527.0455
0.05068 | 938992.3667 | 0.73882 | 49996.2153 | 0.90947 | 68189.0214 | 0.90947 | 145020.6232 | 0.90947 | 58157.4354 | 1260355.662
0.7966 | 1089527.228 | 0.084825 | 43765.583 | 0.80242 | 63983.6783 | 0.80242 | 140257.6217 | 0.80242 | 57278.008 | 1394812.119
0.059334 | 942190.2441 | 0.74128 | 50020.8422 | 0.61661 | 58868.3522 | 0.61661 | 134452.5015 | 0.61661 | 56208.2836 | 1241740.2236
0.93535 | 1137718.8175 | 0.15721 | 44837.2162 | 0.26597 | 51886.4841 | 0.26597 | 122627.0829 | 0.26597 | 54733.1291 | 1411802.73
0.64602 | 1054263.747 | 0.39515 | 47200.6809 | 0.47464 | 55775.1402 | 0.47464 | 130227.23 | 0.47464 | 55561.4267 | 1343028.2248
0.57489 | 1040292.7282 | 0.35859 | 46897.4003 | 0.51075 | 56517.5249 | 0.51075 | 131355.9237 | 0.51075 | 55716.6752 | 1330780.2523
0.9995 | 1194502.4965 | 0.275 | 46139.6862 | 0.72792 | 61725.6765 | 0.72792 | 137700.1928 | 0.72792 | 56805.8114 | 1496873.8634
0.012437 | 919316.1453 | 0.44122 | 47563.576 | 0.19596 | 50486.1478 | 0.19596 | 119422.1492 | 0.19596 | 54416.8254 | 1191204.8438
0.23364 | 983720.495 | 0.066357 | 43422.9638 | 0.73138 | 61822.8583 | 0.73138 | 137810.2617 | 0.73138 | 56826.1342 | 1283602.7131
0.12923 | 962264.389 | 0.96233 | 53223.727 | 0.67818 | 60388.0173 | 0.67818 | 136185.1506 | 0.67818 | 56526.0782 | 1268587.3621
0.12953 | 962337.3918 | 0.64986 | 49174.8389 | 0.59691 | 58408.4282 | 0.59691 | 133897.7696 | 0.59691 | 56112.1037 | 1259930.5322
0.53275 | 1032563.8564 | 0.53518 | 48257.9367 | 0.57262 | 57856.2798 | 0.57262 | 133200.6815 | 0.57262 | 55996.6376 | 1327875.3919
0.75442 | 1078611.9885 | 0.43956 | 47550.7893 | 0.85146 | 65714.0082 | 0.85146 | 142217.4056 | 0.85146 | 57639.8571 | 1391734.0486
0.7914 | 1088126.0094 | 0.34529 | 46783.2983 | 0.59515 | 58367.7675 | 0.59515 | 133847.6148 | 0.59515 | 56103.6006 | 1383228.2908
0.29349 | 993832.6775 | 0.90257 | 52021.7214 | 0.80682 | 64129.5531 | 0.80682 | 140422.8405 | 0.80682 | 57308.5136 | 1307715.3062
0.71421 | 1069050.9239 | 0.08604 | 43786.745 | 0.27402 | 52035.0796 | 0.27402 | 122967.1716 | 0.27402 | 54766.6934 | 1342606.6134
0.68875 | 1063343.2061 | 0.34783 | 46805.2232 | 0.84671 | 65535.062 | 0.84671 | 142014.7298 | 0.84671 | 57602.4356 | 1375300.6566
0.80389 | 1091526.498 | 0.074933 | 43587.306 | 0.50184 | 56331.8436 | 0.50184 | 131081.1986 | 0.50184 | 55677.8453 | 1378204.6915
0.23558 | 984068.4437 | 0.28439 | 46230.0473 | 0.15123 | 49454.9482 | 0.15123 | 117062.0545 | 0.15123 | 54183.9012 | 1250999.3949
0.037154 | 933386.016 | 0.44133 | 47564.4253 | 0.35421 | 53467.7328 | 0.35421 | 126112.224 | 0.35421 | 55078.8983 | 1215609.2964
0.42555 | 1014346.4775 | 0.3959 | 47206.7794 | 0.73342 | 61880.7217 | 0.73342 | 137875.7982 | 0.73342 | 56838.2347 | 1318148.0115
0.25977 | 988277.806 | 0.17836 | 45100.2466 | 0.032025 | 45430.6335 | 0.032025 | 107851.6515 | 0.032025 | 53274.9011 | 1239935.2386
0.060406 | 942569.5797 | 0.7256 | 49866.1683 | 0.52329 | 56781.6233 | 0.52329 | 131738.3746 | 0.52329 | 55771.9039 | 1236727.6498
0.2592 | 988181.2862 | 0.48126 | 47863.7592 | 0.87782 | 66764.2878 | 0.87782 | 143406.9597 | 0.87782 | 57859.4931 | 1304075.786
0.25842 | 988049.4086 | 0.53923 | 48288.2126 | 0.64957 | 59665.2532 | 0.64957 | 135366.5428 | 0.64957 | 56374.9327 | 1287744.3499
0.75044 | 1077633.3303 | 0.247 | 45860.554 | 0.94383 | 70059.6047 | 0.94383 | 147139.2591 | 0.94383 | 58548.6145 | 1399241.3626
0.40784 | 1011507.4557 | 0.18914 | 45228.3421 | 0.75925 | 62631.8088 | 0.75925 | 138726.4847 | 0.75925 | 56995.3031 | 1315089.3944
0.070016 | 945831.0448 | 0.011574 | 41895.46 | 0.94715 | 70268.3649 | 0.94715 | 147375.7023 | 0.94715 | 58592.2707 | 1263962.8427
0.51845 | 1030019.8103 | 0.41707 | 47375.837 | 0.55256 | 57412.2057 | 0.55256 | 132614.0119 | 0.55256 | 55903.7722 | 1323325.637
0.94294 | 1141488.0074 | 0.40278 | 47262.223 | 0.07582 | 47278.6281 | 0.07582 | 112081.1357 | 0.07582 | 53692.3206 | 1401802.3148
0.97368 | 1160264.0941 | 0.59574 | 48725.9475 | 0.89561 | 67538.8482 | 0.89561 | 144284.2323 | 0.89561 | 58021.4703 | 1478834.5923
0.73696 | 1074372.474 | 0.71179 | 49733.5571 | 0.32094 | 52869.3135 | 0.32094 | 124855.951 | 0.32094 | 54953.1023 | 1356784.398
0.48243 | 1023778.558 | 0.080875 | 43695.713 | 0.7678 | 62889.169 | 0.7678 | 139017.9727 | 0.7678 | 57049.1226 | 1326430.5353
0.63822 | 1052666.8482 | 0.13968 | 44605.5152 | 0.80623 | 64109.9393 | 0.80623 | 140400.6257 | 0.80623 | 57304.4119 | 1359087.3403
0.26441 | 989063.3776 | 0.55499 | 48407.4683 | 0.1367 | 49087.7388 | 0.1367 | 116221.6265 | 0.1367 | 54100.957 | 1256881.1682
0.17089 | 971600.6903 | 0.67888 | 49429.9486 | 0.47225 | 55726.8777 | 0.47225 | 130150.9703 | 0.47225 | 55551.3339 | 1262459.8209
0.70571 | 1067119.4921 | 0.82886 | 50987.6569 | 0.63155 | 59225.0358 | 0.63155 | 134867.2618 | 0.63155 | 56282.8738 | 1368482.3205
0.35031 | 1002562.7065 | 0.36501 | 46951.7369 | 0.49797 | 56251.6731 | 0.49797 | 130961.056 | 0.49797 | 55661.0799 | 1292388.2523
0.40283 | 1010710.6477 | 0.20799 | 45443.7003 | 0.10501 | 48212.1416 | 0.10501 | 114217.6573 | 0.10501 | 53903.1798 | 1272487.3267
0.3684 | 1005331.6462 | 0.88791 | 51791.0002 | 0.30388 | 52568.0101 | 0.30388 | 124186.1681 | 0.30388 | 54886.9995 | 1288763.8241
0.77735 | 1084418.4391 | 0.37209 | 47011.1345 | 0.47588 | 55800.2561 | 0.47588 | 130266.7712 | 0.47588 | 55566.6789 | 1373063.2798
0.33284 | 999926.1446 | 0.83187 | 51024.9126 | 0.81016 | 64241.1429 | 0.81016 | 140549.228 | 0.81016 | 57331.8494 | 1313073.2775
0.87886 | 1114744.7381 | 0.18162 | 45139.428 | 0.23616 | 51315.9884 | 0.23616 | 121321.3958 | 0.23616 | 54604.2673 | 1387125.8175
0.36237 | 1004404.2319 | 0.20068 | 45361.4057 | 0.84469 | 65459.5563 | 0.84469 | 141929.2116 | 0.84469 | 57586.6457 | 1314741.0512
0.65379 | 1055873.1625 | 0.88113 | 51689.3253 | 0.48688 | 56023.8527 | 0.48688 | 130614.5013 | 0.48688 | 55613.4378 | 1349814.2796
0.2132 | 979975.5356 | 0.70945 | 49711.4842 | 0.72779 | 61721.8127 | 0.72779 | 137695.8167 | 0.72779 | 56805.0034 | 1285909.6526
0.35154 | 1002750.4106 | 0.57492 | 48561.2656 | 0.51233 | 56550.7026 | 0.51233 | 131404.4992 | 0.51233 | 55723.6134 | 1294990.4914
0.33345 | 1000017.8056 | 0.0096153 | 41798.4538 | 0.642 | 59478.8954 | 0.642 | 135155.4726 | 0.642 | 56335.9613 | 1292786.5886
0.94014 | 1140070.8552 | 0.22161 | 45593.3551 | 0.26835 | 51930.5999 | 0.26835 | 122728.0502 | 0.26835 | 54743.0939 | 1415065.9543
0.13345 | 963272.3913 | 0.34253 | 46759.3047 | 0.84761 | 65568.5335 | 0.84761 | 142052.6399 | 0.84761 | 57609.4352 | 1275262.3046
0.86651 | 1110504.258 | 0.70655 | 49684.0885 | 0.53909 | 57119.597 | 0.53909 | 132214.0967 | 0.53909 | 55842.5814 | 1405364.6216
0.037625 | 933597.062 | 0.54552 | 48335.5301 | 0.27919 | 52129.2354 | 0.27919 | 123182.665 | 0.27919 | 54787.9611 | 1212032.4535
0.4594 | 1019900.5211 | 0.72504 | 49860.7615 | 0.60992 | 58710.9086 | 0.60992 | 134265.1738 | 0.60992 | 56175.3588 | 1318912.7238
0.75882 | 1079706.226 | 0.0045128 | 41484.0203 | 0.35967 | 53567.3899 | 0.35967 | 126312.6438 | 0.35967 | 55099.7387 | 1356170.0188
0.49638 | 1026169.0845 | 0.6696 | 49347.1892 | 0.39009 | 54130.9201 | 0.39009 | 127403.1022 | 0.39009 | 55217.585 | 1312267.881
0.68823 | 1063229.4726 | 0.97312 | 53530.4952 | 0.5546 | 57456.9775 | 0.5546 | 132674.2518 | 0.5546 | 55913.1349 | 1362804.3321
0.45879 | 1019797.622 | 0.33119 | 46659.8405 | 0.64126 | 59461.0216 | 0.64126 | 135135.2286 | 0.64126 | 56332.2235 | 1317385.9362
0.63137 | 1051280.2392 | 0.36237 | 46929.4801 | 0.32311 | 52907.8068 | 0.32311 | 124939.6353 | 0.32311 | 54961.3613 | 1331018.5226
0.024023 | 926845.4161 | 0.51158 | 48083.8697 | 0.92265 | 68856.029 | 0.92265 | 145776.0806 | 0.92265 | 58296.921 | 1247858.3164
0.79217 | 1088331.1904 | 0.26732 | 46064.5499 | 0.19364 | 50435.7302 | 0.19364 | 119306.7591 | 0.19364 | 54405.4372 | 1358543.6669
0.60936 | 1046904.598 | 0.9232 | 52378.1834 | 0.52216 | 56757.7811 | 0.52216 | 131704.24 | 0.52216 | 55766.9179 | 1343511.7205
0.27969 | 991600.2309 | 0.38326 | 47103.7074 | 0.81373 | 64361.7453 | 0.81373 | 140685.8231 | 0.81373 | 57357.0699 | 1301108.5766
0.75805 | 1079513.7272 | 0.49535 | 47966.4765 | 0.56912 | 57778.2076 | 0.56912 | 133099.2622 | 0.56912 | 55980.311 | 1374337.9846
0.4116 | 1012105.7164 | 0.02157 | 42295.4509 | 0.78477 | 63414.6675 | 0.78477 | 139613.156 | 0.78477 | 57159.0156 | 1314588.0064
0.75999 | 1079998.3118 | 0.15724 | 44837.676 | 0.71625 | 61401.4508 | 0.71625 | 137332.9725 | 0.71625 | 56738.0089 | 1380308.4201
0.77174 | 1082971.5985 | 0.27835 | 46172.0503 | 0.34 | 53210.2232 | 0.34 | 125583.0449 | 0.34 | 55025.0475 | 1362961.9643
0.91723 | 1129530.4853 | 0.054706 | 43181.5721 | 0.015187 | 44362.4335 | 0.015187 | 105406.8744 | 0.015187 | 53033.6193 | 1375514.9846
0.8732 | 1112776.4071 | 0.82402 | 50928.5396 | 0.065485 | 46905.6922 | 0.065485 | 111227.6016 | 0.065485 | 53608.0829 | 1375446.3236
0.075156 | 947483.314 | 0.54042 | 48297.1302 | 0.049521 | 46266.0039 | 0.049521 | 109763.5542 | 0.049521 | 53463.5921 | 1205273.5943
0.56307 | 1038086.7294 | 0.46373 | 47733.9046 | 0.28 | 52143.9239 | 0.28 | 123216.2824 | 0.28 | 54791.2789 | 1315972.1193
0.60026 | 1045130.5482 | 0.52331 | 48169.8381 | 0.47655 | 55813.6968 | 0.47655 | 130287.8911 | 0.47655 | 55569.4897 | 1334971.4639
0.54262 | 1034340.6063 | 0.1408 | 44620.7806 | 0.28354 | 52207.8108 | 0.28354 | 123362.4997 | 0.28354 | 54805.7094 | 1309337.4069
0.38797 | 1008371.3479 | 0.93875 | 52680.0818 | 0.47393 | 55760.6974 | 0.47393 | 130204.4472 | 0.47393 | 55558.4064 | 1302574.9807
0.30575 | 995773.6659 | 0.60071 | 48765.8735 | 0.32873 | 53008.0588 | 0.32873 | 125155.6555 | 0.32873 | 54982.6809 | 1277685.9347
0.064769 | 944080.2862 | 0.75586 | 50168.8844 | 0.1834 | 50209.6807 | 0.1834 | 118789.4022 | 0.1834 | 54354.3779 | 1217602.6314
0.40339 | 1010799.4611 | 0.45602 | 47676.0784 | 0.75117 | 62392.8396 | 0.75117 | 138455.8265 | 0.75117 | 56945.3295 | 1316269.5352
0.38245 | 1007508.4782 | 0.026157 | 42446.8063 | 0.83753 | 65196.8223 | 0.83753 | 141631.6372 | 0.83753 | 57531.7024 | 1314315.4465
0.19211 | 975917.3803 | 0.72433 | 49853.8354 | 0.62528 | 59074.642 | 0.62528 | 134693.9886 | 0.62528 | 56251.4232 | 1275791.2694
0.23103 | 983251.4991 | 0.30918 | 46461.7835 | 0.48957 | 56078.7725 | 0.48957 | 130698.749 | 0.48957 | 55624.9227 | 1272115.7267
0.35725 | 1003619.9188 | 0.64983 | 49174.6097 | 0.11163 | 48404.9452 | 0.11163 | 114658.9248 | 0.11163 | 53946.7297 | 1269805.1282
0.17501 | 972457.944 | 0.12005 | 44327.9297 | 0.35752 | 53528.2553 | 0.35752 | 126234.2244 | 0.35752 | 55091.5549 | 1251639.9083
0.28997 | 993269.5418 | 0.59657 | 48732.581 | 0.89108 | 67335.6552 | 0.89108 | 144054.0945 | 0.89108 | 57978.9783 | 1311370.8508
0.33801 | 1000703.3317 | 0.84016 | 51129.087 | 0.92212 | 68827.7431 | 0.92212 | 145744.0438 | 0.92212 | 58291.0058 | 1324695.2115
0.55094 | 1035855.7666 | 0.7706 | 50323.1322 | 0.57979 | 58017.6873 | 0.57979 | 133408.0823 | 0.57979 | 56030.3913 | 1333635.0597
0.43723 | 1016244.0371 | 0.18712 | 45204.6289 | 0.94073 | 69870.7858 | 0.94073 | 146925.4014 | 0.94073 | 58509.1284 | 1336753.9816
0.98417 | 1169181.7132 | 0.3395 | 46732.8769 | 0.76433 | 62784.156 | 0.76433 | 138899.0342 | 0.76433 | 57027.1622 | 1474624.9425
0.37233 | 1005936.8997 | 0.20668 | 45429.1246 | 0.76635 | 62845.1905 | 0.76635 | 138968.1623 | 0.76635 | 57039.9258 | 1310219.3029
0.3951 | 1009489.5469 | 0.9177 | 52278.8343 | 0.15344 | 49509.1675 | 0.15344 | 117186.1457 | 0.15344 | 54196.1481 | 1282659.8426
0.73913 | 1074891.9143 | 0.71207 | 49736.2498 | 0.16803 | 49858.1844 | 0.16803 | 117984.9366 | 0.16803 | 54274.9829 | 1346746.2681
0.9679 | 1156115.4757 | 0.25141 | 45905.5112 | 0.89145 | 67352.0534 | 0.89145 | 144072.6673 | 0.89145 | 57982.4075 | 1471428.1151
0.85891 | 1107991.4119 | 0.97776 | 53681.4401 | 0.99274 | 74504.4386 | 0.99274 | 152173.5094 | 0.99274 | 59478.1246 | 1447828.9246
0.12572 | 961412.9326 | 0.56498 | 48484.1547 | 0.034533 | 45562.4402 | 0.034533 | 108153.316 | 0.034533 | 53304.6732 | 1216917.5166
0.59593 | 1044294.5543 | 0.87669 | 51624.4547 | 0.84463 | 65457.4472 | 0.84463 | 141926.8228 | 0.84463 | 57586.2047 | 1360889.4838
0.97951 | 1164934.1049 | 0.07251 | 43541.8754 | 0.1135 | 48458.5146 | 0.1135 | 114781.5284 | 0.1135 | 53958.8298 | 1425674.8531
0.4805 | 1023449.5541 | 0.46578 | 47749.2524 | 0.91972 | 68702.8573 | 0.91972 | 145602.5973 | 0.91972 | 58264.8895 | 1343769.1506
0.86271 | 1109238.655 | 0.72206 | 49831.9006 | 0.18889 | 50331.6303 | 0.18889 | 119068.5068 | 0.18889 | 54381.9235 | 1382852.6161
0.32621 | 998925.4826 | 0.17147 | 45016.3841 | 0.55994 | 57574.5247 | 0.55994 | 132831.232 | 0.55994 | 55937.7165 | 1290285.3399
0.49189 | 1025395.6465 | 0.94299 | 52768.8 | 0.065842 | 46919.0487 | 0.065842 | 111258.1704 | 0.065842 | 53611.0998 | 1289952.7654
0.19785 | 977043.1318 | 0.95161 | 52960.229 | 0.71797 | 61448.7162 | 0.71797 | 137386.5056 | 0.71797 | 56747.8931 | 1285586.4757
0.64981 | 1055047.5727 | 0.2805 | 46192.81 | 0.14184 | 49219.7355 | 0.14184 | 116523.7259 | 0.14184 | 54130.772 | 1321114.6162
0.1546 | 968103.5081 | 0.12162 | 44350.994 | 0.59232 | 58302.6779 | 0.59232 | 133766.9431 | 0.59232 | 56089.989 | 1260614.1121
0.66216 | 1057625.1862 | 0.90831 | 52116.7629 | 0.54793 | 57311.1484 | 0.54793 | 132477.1202 | 0.54793 | 55882.6389 | 1355412.8567
0.023173 | 926366.3598 | 0.51918 | 48139.4515 | 0.5373 | 57080.9297 | 0.5373 | 132160.4302 | 0.5373 | 55834.4953 | 1219581.6665
0.3172 | 997550.7503 | 0.015807 | 42080.1962 | 0.5298 | 56920.3037 | 0.5298 | 131935.406 | 0.5298 | 55800.9049 | 1284287.5611
0.92919 | 1134820.9882 | 0.54892 | 48361.2967 | 0.66423 | 60031.7403 | 0.66423 | 135781.6287 | 0.66423 | 56451.573 | 1435447.2269
0.062354 | 943250.8084 | 0.57818 | 48586.7771 | 0.33126 | 53053.2681 | 0.33126 | 125252.1744 | 0.33126 | 54992.2066 | 1225135.2346
0.77505 | 1083823.5391 | 0.44685 | 47606.5378 | 0.75938 | 62635.8901 | 0.75938 | 138731.1072 | 0.75938 | 56996.1566 | 1389793.2309
0.5053 | 1027715.5091 | 0.32884 | 46638.9815 | 0.81585 | 64433.7338 | 0.81585 | 140767.3578 | 0.81585 | 57372.1243 | 1336927.7065
0.83729 | 1101193.1347 | 0.72248 | 49835.8831 | 0.33574 | 53133.6293 | 0.33574 | 125422.3902 | 0.33574 | 55009.0301 | 1384594.0674
0.21511 | 980332.2386 | 0.076837 | 43622.488 | 0.15209 | 49476.1708 | 0.15209 | 117110.6264 | 0.15209 | 54188.6948 | 1244730.2186
0.94032 | 1140159.0143 | 0.41443 | 47355.0146 | 0.28669 | 52264.4256 | 0.28669 | 123492.0732 | 0.28669 | 54818.4974 | 1418089.0251
0.1933 | 976151.0659 | 0.083917 | 43749.6638 | 0.66228 | 59982.6158 | 0.66228 | 135725.9899 | 0.66228 | 56441.3 | 1272050.6355
0.47029 | 1021723.9267 | 0.73671 | 49975.2534 | 0.61009 | 58714.7687 | 0.61009 | 134269.7983 | 0.61009 | 56176.166 | 1320859.9132
0.50659 | 1027940.0237 | 0.75345 | 50144.0907 | 0.03754 | 45714.2732 | 0.03754 | 108500.8145 | 0.03754 | 53338.9688 | 1285638.171
0.86127 | 1108766.3135 | 0.88202 | 51702.4903 | 0.78685 | 63480.4574 | 0.78685 | 139687.6702 | 0.78685 | 57172.7737 | 1420809.7051
0.63397 | 1051805.3833 | 0.4433 | 47579.4605 | 0.076195 | 47291.6646 | 0.076195 | 112110.9721 | 0.076195 | 53695.2652 | 1312482.7456
0.27015 | 990025.8006 | 0.37665 | 47049.1063 | 0.13632 | 49077.8715 | 0.13632 | 116199.0433 | 0.13632 | 54098.7282 | 1256450.5499
0.30999 | 996434.3246 | 0.45784 | 47689.7417 | 0.67207 | 60230.9725 | 0.67207 | 136007.2805 | 0.67207 | 56493.2368 | 1296855.556
0.32889 | 999330.9312 | 0.83359 | 51046.3254 | 0.24513 | 51491.275 | 0.24513 | 121722.5723 | 0.24513 | 54643.8605 | 1278234.9644
0.94491 | 1142509.8176 | 0.12157 | 44350.3353 | 0.43676 | 55023.2313 | 0.43676 | 128995.9111 | 0.43676 | 55404.1864 | 1426283.4817
0.97862 | 1164184.1052 | 0.55952 | 48442.144 | 0.63408 | 59286.3229 | 0.63408 | 134937.2092 | 0.63408 | 56295.6903 | 1463145.4715
0.44025 | 1016737.7271 | 0.94887 | 52897.4888 | 0.62485 | 59064.3061 | 0.62485 | 134681.9947 | 0.62485 | 56249.2618 | 1319630.7784
0.58664 | 1042514.8642 | 0.31098 | 46478.2387 | 0.30882 | 52654.8568 | 0.30882 | 124381.9689 | 0.30882 | 54906.3237 | 1320936.2523
0.42785 | 1014719.379 | 0.2694 | 46084.9991 | 0.21862 | 50963.4024 | 0.21862 | 120514.4364 | 0.21862 | 54524.6262 | 1286806.8431
0.16325 | 969981.7066 | 0.16817 | 44975.6713 | 0.20803 | 50743.5355 | 0.20803 | 120011.2294 | 0.20803 | 54474.9633 | 1240187.1062
0.9942 | 1181351.4334 | 0.90709 | 52096.2866 | 0.97883 | 72739.3518 | 0.97883 | 150174.3596 | 0.97883 | 59109.0071 | 1515470.4385
0.54531 | 1034829.2076 | 0.11367 | 44233.0345 | 0.57584 | 57928.5496 | 0.57584 | 133293.9217 | 0.57584 | 56011.7507 | 1326296.4641
0.35124 | 1002704.6083 | 0.86831 | 51504.9073 | 0.0047737 | 43324.5087 | 0.0047737 | 103031.3879 | 0.0047737 | 52799.176 | 1253364.5883
0.39157 | 1008935.0612 | 0.75491 | 50159.056 | 0.073306 | 47190.3592 | 0.073306 | 111879.1156 | 0.073306 | 53672.3826 | 1271835.9747
0.87507 | 1113422.1477 | 0.48223 | 47870.9288 | 0.063323 | 46824.0211 | 0.063323 | 111040.6818 | 0.063323 | 53589.6353 | 1372747.4148
0.65731 | 1056607.508 | 0.21052 | 45471.9462 | 0.98005 | 72863.9986 | 0.98005 | 150315.5355 | 0.98005 | 59135.0734 | 1384394.0617
0.27499 | 990827.2282 | 0.39144 | 47170.6181 | 0.14473 | 49293.0845 | 0.14473 | 116691.599 | 0.14473 | 54147.3399 | 1258129.8697
0.26022 | 988354.513 | 0.3618 | 46924.6556 | 0.056565 | 46559.3603 | 0.056565 | 110434.9557 | 0.056565 | 53529.8545 | 1245803.3392
0.79538 | 1089196.1315 | 0.58993 | 48679.5961 | 0.34023 | 53214.3683 | 0.34023 | 125591.6957 | 0.34023 | 55025.9143 | 1371707.7058
0.27641 | 991062.6659 | 0.11857 | 44306.2453 | 0.86584 | 66274.2543 | 0.86584 | 142851.9443 | 0.86584 | 57757.0166 | 1302252.1264
0.71441 | 1069098.3993 | 0.89851 | 51956.2217 | 0.46615 | 55604.3656 | 0.46615 | 129955.733 | 0.46615 | 55525.714 | 1362140.4337
0.45138 | 1018569.6692 | 0.782 | 50445.8425 | 0.32764 | 52988.5787 | 0.32764 | 125113.8962 | 0.32764 | 54978.5596 | 1302096.5462
0.55013 | 1035706.8061 | 0.82357 | 50923.1125 | 0.48177 | 55919.6936 | 0.48177 | 130453.4691 | 0.48177 | 55591.6559 | 1328594.7372
0.13983 | 964766.9743 | 0.72051 | 49816.9559 | 0.14127 | 49205.3138 | 0.14127 | 116490.7191 | 0.14127 | 54127.5145 | 1234407.4775
0.38948 | 1008606.8485 | 0.15517 | 44810.9704 | 0.82868 | 64879.5982 | 0.82868 | 141272.3469 | 0.82868 | 57465.3641 | 1317035.1281
0.32331 | 998484.3452 | 0.46484 | 47742.2058 | 0.14444 | 49285.726 | 0.14444 | 116674.7575 | 0.14444 | 54145.6777 | 1266332.7123
0.64715 | 1054498.2527 | 0.33044 | 46653.1644 | 0.53384 | 57006.6933 | 0.53384 | 132056.8517 | 0.53384 | 55818.9708 | 1346033.9329
0.2515 | 986861.7985 | 0.82719 | 50967.2136 | 0.5928 | 58313.8989 | 0.5928 | 133780.8843 | 0.5928 | 56092.3356 | 1286016.1308
0.25718 | 987836.6065 | 0.66964 | 49347.5105 | 0.16829 | 49864.2719 | 0.16829 | 117998.8689 | 0.16829 | 54276.3579 | 1259323.6157
0.16941 | 971290.0039 | 0.47472 | 47815.6586 | 0.4652 | 55585.2165 | 0.4652 | 129924.9998 | 0.4652 | 55521.7095 | 1260137.5883
0.88763 | 1117888.7569 | 0.67374 | 49383.9666 | 0.22388 | 51070.6536 | 0.22388 | 120759.9009 | 0.22388 | 54548.8518 | 1393652.1299
0.75212 | 1078046.3603 | 0.63907 | 49082.7099 | 0.82944 | 64906.4725 | 0.82944 | 141302.785 | 0.82944 | 57470.9841 | 1390809.3118
0.42892 | 1014892.1129 | 0.71231 | 49738.5298 | 0.81513 | 64409.2607 | 0.81513 | 140739.6393 | 0.81513 | 57367.0064 | 1327146.5491
0.38186 | 1007416.0488 | 0.56632 | 48494.4988 | 0.68635 | 60600.12 | 0.68635 | 136425.3796 | 0.68635 | 56570.4334 | 1309506.4806
0.72497 | 1071541.1267 | 0.56782 | 48506.0668 | 0.51474 | 56601.2891 | 0.51474 | 131478.2676 | 0.51474 | 55734.1921 | 1363860.9423
0.27312 | 990517.7156 | 0.28774 | 46261.97 | 0.087453 | 47669.133 | 0.087453 | 112974.8798 | 0.087453 | 53780.5266 | 1251204.225
0.352 | 1002819.4589 | 0.43873 | 47544.4603 | 0.80956 | 64220.9876 | 0.80956 | 140526.3998 | 0.80956 | 57327.6345 | 1312438.9411
0.32586 | 998872.052 | 0.66202 | 49280.3853 | 0.062871 | 46806.7832 | 0.062871 | 111001.2295 | 0.062871 | 53585.7416 | 1259546.1917
0.39984 | 1010238.1808 | 0.34486 | 46779.5367 | 0.41761 | 54652.8465 | 0.41761 | 128353.2816 | 0.41761 | 55326.731 | 1295350.5767
0.6995 | 1065723.55 | 0.044657 | 42951.7589 | 0.6702 | 60183.1839 | 0.6702 | 135953.1548 | 0.6702 | 56483.2431 | 1361294.8907
0.51414 | 1029262.1191 | 0.86654 | 51480.1067 | 0.85337 | 65786.7382 | 0.85337 | 142299.7802 | 0.85337 | 57655.0665 | 1346483.8107
0.43011 | 1015085.0959 | 0.26693 | 46060.7066 | 0.37729 | 53892.0905 | 0.37729 | 126949.5738 | 0.37729 | 55167.6406 | 1297155.1074
0.32791 | 999183.1004 | 0.31152 | 46483.2012 | 0.92054 | 68745.5146 | 0.92054 | 145650.9113 | 0.92054 | 58273.8101 | 1318336.5376
0.71495 | 1069221.7318 | 0.68123 | 49451.1086 | 0.46426 | 55566.3668 | 0.46426 | 129894.6895 | 0.46426 | 55517.7677 | 1359651.6644
0.8472 | 1104250.609 | 0.82199 | 50903.915 | 0.152 | 49473.8949 | 0.152 | 117105.4177 | 0.152 | 54188.1808 | 1375922.0175
0.089363 | 951777.3721 | 0.076448 | 43615.3375 | 0.40974 | 54502.2777 | 0.40974 | 128084.702 | 0.40974 | 55295.2438 | 1233274.9331
0.99951 | 1194568.1576 | 0.49599 | 47971.0955 | 0.84507 | 65473.8068 | 0.84507 | 141945.3518 | 0.84507 | 57589.6258 | 1507548.0374
0.4479 | 1017994.7614 | 0.88923 | 51811.136 | 0.70306 | 61043.069 | 0.70306 | 136927.0667 | 0.70306 | 56663.0635 | 1324439.0966
0.46746 | 1021247.5717 | 0.54882 | 48360.5223 | 0.0063844 | 43531.7498 | 0.0063844 | 103505.6983 | 0.0063844 | 52845.987 | 1269491.5292
0.97255 | 1159419.0471 | 0.79924 | 50637.6821 | 0.71568 | 61385.7933 | 0.71568 | 137315.2387 | 0.71568 | 56734.7345 | 1465492.4957
0.54891 | 1035483.7423 | 0.13462 | 44536.0134 | 0.10708 | 48273.084 | 0.10708 | 114357.1355 | 0.10708 | 53916.9452 | 1296566.9205
0.83463 | 1100391.1202 | 0.41938 | 47394.0356 | 0.6144 | 58816.1579 | 0.6144 | 134390.6927 | 0.6144 | 56197.3687 | 1397189.3751
0.76872 | 1082201.0985 | 0.047763 | 43025.3165 | 0.27321 | 52020.2292 | 0.27321 | 122933.1838 | 0.27321 | 54763.3391 | 1354943.167
0.38611 | 1008079.4944 | 0.1381 | 44583.9673 | 0.38686 | 54070.4011 | 0.38686 | 127289.3357 | 0.38686 | 55204.9292 | 1289228.1276
0.5348 | 1032931.3104 | 0.81549 | 50826.2244 | 0.95273 | 70633.1989 | 0.95273 | 147788.9159 | 0.95273 | 58668.5654 | 1360848.215
0.62394 | 1049787.3589 | 0.90831 | 52116.8037 | 0.29703 | 52447.926 | 0.29703 | 123912.0485 | 0.29703 | 54859.9459 | 1333124.0831
0.6149 | 1047993.9405 | 0.72839 | 49893.3225 | 0.54701 | 57291.052 | 0.54701 | 132449.7446 | 0.54701 | 55878.4363 | 1343506.4958
0.52398 | 1030999.1575 | 0.7389 | 49997.0686 | 0.40581 | 54427.5894 | 0.40581 | 127949.8424 | 0.40581 | 55279.6249 | 1318653.2828
0.95188 | 1146266.6775 | 0.823 | 50916.1317 | 0.62197 | 58995.4578 | 0.62197 | 134601.8198 | 0.62197 | 56234.8641 | 1447014.9509
0.13256 | 963061.3754 | 0.52067 | 48150.3992 | 0.15601 | 49571.8934 | 0.15601 | 117329.7056 | 0.15601 | 54210.3164 | 1232323.69
0.55085 | 1035838.8662 | 0.28014 | 46189.3714 | 0.26319 | 51834.8133 | 0.26319 | 122508.8245 | 0.26319 | 54721.4579 | 1311093.3333
0.97021 | 1157721.1832 | 0.11477 | 44249.4942 | 0.23632 | 51319.1238 | 0.23632 | 121328.5719 | 0.23632 | 54604.9755 | 1429223.3485
0.89306 | 1119899.1884 | 0.18837 | 45219.3551 | 0.99048 | 74142.913 | 0.99048 | 151764.043 | 0.99048 | 59402.5218 | 1450428.0214
0.72677 | 1071962.1726 | 0.315 | 46514.839 | 0.84412 | 65438.6506 | 0.84412 | 141905.5337 | 0.84412 | 57582.2739 | 1383403.4698
0.49249 | 1025499.1041 | 0.86195 | 51416.7819 | 0.89428 | 67478.6225 | 0.89428 | 144216.0203 | 0.89428 | 58008.8758 | 1346619.4047
0.3052 | 995687.4712 | 0.081687 | 43710.2156 | 0.91324 | 68374.8843 | 0.91324 | 145231.1327 | 0.91324 | 58196.3033 | 1311200.0071
0.62259 | 1049519.472 | 0.91351 | 52205.5348 | 0.023697 | 44951.0626 | 0.023697 | 106754.0632 | 0.023697 | 53166.5771 | 1306596.7097
0.83752 | 1101262.9469 | 0.77243 | 50342.6224 | 0.80877 | 64194.39 | 0.80877 | 140496.2752 | 0.80877 | 57322.0723 | 1413618.3069
0.56185 | 1037861.5921 | 0.79423 | 50581.1149 | 0.47777 | 55838.4497 | 0.47777 | 130326.7131 | 0.47777 | 55574.666 | 1330182.5359
0.24069 | 984975.5815 | 0.34993 | 46823.3426 | 0.20681 | 50718.0124 | 0.20681 | 119952.815 | 0.20681 | 54469.1983 | 1256938.9497
0.92273 | 1131909.0482 | 0.23311 | 45716.1651 | 0.4865 | 56016.0367 | 0.4865 | 130602.4747 | 0.4865 | 55611.8033 | 1419855.528
0.10981 | 957395.5664 | 0.68652 | 49498.9811 | 0.62266 | 59012.0332 | 0.62266 | 134621.1672 | 0.62266 | 56238.3304 | 1256766.0784
0.2599 | 988300.3875 | 0.14639 | 44695.8595 | 0.016506 | 44462.9196 | 0.016506 | 105636.8559 | 0.016506 | 53056.3168 | 1236152.3394
0.43134 | 1015284.9982 | 0.094705 | 43933.5232 | 0.91005 | 68217.6865 | 0.91005 | 145053.0894 | 0.91005 | 58163.4299 | 1330652.7273
0.83283 | 1099849.2543 | 0.58735 | 48659.0704 | 0.92634 | 69052.4973 | 0.92634 | 145998.6021 | 0.92634 | 58338.0068 | 1421897.4309
0.76182 | 1080454.9006 | 0.033094 | 42652.3535 | 0.056253 | 46546.738 | 0.056253 | 110406.0671 | 0.056253 | 53527.0034 | 1333587.0625
0.20554 | 978526.0792 | 0.018818 | 42196.8131 | 0.55352 | 57433.2998 | 0.55352 | 132642.4247 | 0.55352 | 55908.1834 | 1266706.8002
0.064658 | 944042.5622 | 0.015089 | 42050.7623 | 0.64309 | 59505.6296 | 0.64309 | 135185.752 | 0.64309 | 56341.552 | 1237126.2581
0.60062 | 1045201.0176 | 0.041721 | 42879.8267 | 0.55451 | 57455.0838 | 0.55451 | 132671.7089 | 0.55451 | 55912.7389 | 1334120.3758
0.21332 | 979997.5962 | 0.094479 | 43929.7906 | 0.17212 | 49953.1519 | 0.17212 | 118202.2876 | 0.17212 | 54296.4339 | 1246379.2601
0.2413 | 985082.8184 | 0.028275 | 42512.184 | 0.64742 | 59612.1577 | 0.64742 | 135306.4064 | 0.64742 | 56363.8293 | 1278877.3959
0.89189 | 1119461.6969 | 0.075957 | 43606.2749 | 0.27651 | 52080.5578 | 0.27651 | 123071.2571 | 0.27651 | 54776.9659 | 1392996.7527
0.83677 | 1101035.2282 | 0.54383 | 48322.8449 | 0.55635 | 57495.3016 | 0.55635 | 132725.6192 | 0.55635 | 55921.1493 | 1395500.1432
0.19495 | 976475.5421 | 0.49357 | 47953.5485 | 0.74469 | 62203.6433 | 0.74469 | 138241.5414 | 0.74469 | 56905.7645 | 1281780.0399
0.093113 | 952852.5639 | 0.73811 | 49989.1565 | 0.65044 | 59686.6617 | 0.65044 | 135390.7902 | 0.65044 | 56379.4097 | 1254298.582
0.95695 | 1149176.4779 | 0.16843 | 44978.8797 | 0.26015 | 51777.8809 | 0.26015 | 122378.5239 | 0.26015 | 54708.5982 | 1423020.3605
0.82436 | 1097343.0249 | 0.051455 | 43109.7205 | 0.033867 | 45527.8982 | 0.033867 | 108074.2601 | 0.033867 | 53296.871 | 1347351.7746
0.67643 | 1060664.5366 | 0.73602 | 49968.4063 | 0.64917 | 59655.3088 | 0.64917 | 135355.2796 | 0.64917 | 56372.8531 | 1362016.3844
0.28693 | 992779.5375 | 0.53596 | 48263.7312 | 0.85499 | 65848.9289 | 0.85499 | 142370.2178 | 0.85499 | 57668.0719 | 1306930.4873
0.88642 | 1117448.6687 | 0.27566 | 46146.0751 | 0.90153 | 67811.0753 | 0.90153 | 144592.5586 | 0.90153 | 58078.3988 | 1434076.7765
0.85854 | 1107870.2247 | 0.26978 | 46088.7544 | 0.27443 | 52042.5618 | 0.27443 | 122984.2962 | 0.27443 | 54768.3835 | 1383754.2206
0.26728 | 989545.1702 | 0.85734 | 51354.0472 | 0.61405 | 58807.9793 | 0.61405 | 134380.9814 | 0.61405 | 56195.6584 | 1290283.8366
0.69641 | 1065034.755 | 0.37068 | 46999.346 | 0.68881 | 60664.567 | 0.68881 | 136498.3726 | 0.68881 | 56583.9107 | 1365780.9513
0.6507 | 1055231.3393 | 0.33578 | 46700.3196 | 0.55511 | 57468.218 | 0.55511 | 132689.3367 | 0.55511 | 55915.4855 | 1348004.6991
0.82955 | 1098871.1578 | 0.53033 | 48221.7839 | 0.30081 | 52514.2219 | 0.30081 | 124063.7477 | 0.30081 | 54874.9175 | 1378545.8288
0.98002 | 1165375.5262 | 0.68873 | 49519.0737 | 0.80494 | 64066.8699 | 0.80494 | 140351.845 | 0.80494 | 57295.4051 | 1476608.72
0.13174 | 962866.5297 | 0.08535 | 43774.7367 | 0.60761 | 58656.7865 | 0.60761 | 134200.1662 | 0.60761 | 56164.0407 | 1255662.2597
0.46502 | 1020838.2502 | 0.7581 | 50191.9372 | 0.97767 | 72624.2587 | 0.97767 | 150044.0044 | 0.97767 | 59084.9387 | 1352783.3891
0.043323 | 936051.2689 | 0.69378 | 49565.3624 | 0.21096 | 50805.0494 | 0.21096 | 120152.0158 | 0.21096 | 54488.8579 | 1211062.5545
0.25908 | 988161.0115 | 0.018656 | 42190.7675 | 0.15891 | 49642.0713 | 0.15891 | 117490.321 | 0.15891 | 54226.168 | 1251710.3393
0.64525 | 1054106.6715 | 0.51253 | 48090.7808 | 0.58438 | 58121.5017 | 0.58438 | 133539.8798 | 0.58438 | 56052.1012 | 1349910.935
0.25744 | 987881.389 | 0.03758 | 42773.9117 | 0.64541 | 59562.6025 | 0.64541 | 135250.2799 | 0.64541 | 56353.4663 | 1281821.6493
0.75959 | 1079897.9547 | 0.035406 | 42715.9505 | 0.71375 | 61332.8159 | 0.71375 | 137255.2361 | 0.71375 | 56723.6558 | 1377925.6129
0.12738 | 961817.6919 | 0.85528 | 51326.3821 | 0.88555 | 67093.5592 | 0.88555 | 143779.8948 | 0.88555 | 57928.3508 | 1281945.8788
0.093532 | 952971.1951 | 0.30464 | 46420.1058 | 0.18325 | 50206.3989 | 0.18325 | 118781.8912 | 0.18325 | 54353.6366 | 1222733.2276
0.94122 | 1140612.5946 | 0.33221 | 46668.8307 | 0.62251 | 59008.3715 | 0.62251 | 134616.8956 | 0.62251 | 56237.5647 | 1437144.2571
0.65095 | 1055282.3094 | 0.5739 | 48553.3565 | 0.91584 | 68505.0185 | 0.91584 | 145378.5236 | 0.91584 | 58223.5172 | 1375942.7251
0.22612 | 982362.1704 | 0.84542 | 51196.6442 | 0.60488 | 58593.152 | 0.60488 | 134123.328 | 0.60488 | 56150.7334 | 1282426.028
0.93401 | 1137075.5101 | 0.45321 | 47654.8197 | 0.58665 | 58173.2568 | 0.58665 | 133605.1234 | 0.58665 | 56062.9243 | 1432571.6343
0.23024 | 983109.0399 | 0.7148 | 49762.2204 | 0.26299 | 51831.0142 | 0.26299 | 122500.1295 | 0.26299 | 54720.5997 | 1261923.0037
0.94608 | 1143121.284 | 0.20291 | 45386.7024 | 0.099111 | 48035.1806 | 0.099111 | 113812.6486 | 0.099111 | 53863.2083 | 1404219.0238
0.97182 | 1158877.394 | 0.42851 | 47465.4631 | 0.21965 | 50984.6 | 0.21965 | 120562.951 | 0.21965 | 54529.4143 | 1432419.8223
0.63883 | 1052792.5188 | 0.046993 | 43007.3158 | 0.8206 | 64596.8833 | 0.8206 | 140952.1421 | 0.8206 | 57406.2423 | 1358755.1023
0.64952 | 1054986.1168 | 0.25972 | 45989.165 | 0.39813 | 54282.1326 | 0.39813 | 127684.0171 | 0.39813 | 55249.2068 | 1338190.6382
0.48756 | 1024653.1339 | 0.62469 | 48962.0783 | 0.34117 | 53231.3657 | 0.34117 | 125627.1232 | 0.34117 | 55029.4689 | 1307503.17
0.063686 | 943710.1498 | 0.8959 | 51914.6468 | 0.53175 | 56962.0252 | 0.53175 | 131994.1807 | 0.53175 | 55809.6298 | 1240390.6323
0.76089 | 1080222.203 | 0.75306 | 50140.1056 | 0.96071 | 71195.8656 | 0.96071 | 148426.1962 | 0.96071 | 58786.231 | 1408770.6015
0.041002 | 935072.2647 | 0.30244 | 46399.7116 | 0.79009 | 63583.7038 | 0.79009 | 139804.6077 | 0.79009 | 57194.3648 | 1242054.6526
0.35946 | 1003958.4464 | 0.42602 | 47446.063 | 0.23504 | 51293.9983 | 0.23504 | 121271.0673 | 0.23504 | 54599.3002 | 1278568.8753
0.59753 | 1044602.4869 | 0.095681 | 43949.6332 | 0.20735 | 50729.241 | 0.20735 | 119978.5139 | 0.20735 | 54471.7346 | 1313731.6096
0.84458 | 1103434.2609 | 0.54028 | 48296.1016 | 0.0044529 | 43279.228 | 0.0044529 | 102927.7545 | 0.0044529 | 52788.9482 | 1350726.2931
0.17696 | 972860.7635 | 0.81592 | 50831.2784 | 0.95379 | 70704.8631 | 0.95379 | 147870.0832 | 0.95379 | 58683.5519 | 1300950.54
0.35286 | 1002950.4614 | 0.12231 | 44361.0459 | 0.51586 | 56624.7898 | 0.51586 | 131512.4171 | 0.51586 | 55739.1066 | 1291187.8208
0.90956 | 1126334.2233 | 0.56662 | 48496.8369 | 0.16983 | 49900.2671 | 0.16983 | 118081.2508 | 0.16983 | 54284.4884 | 1397097.0666
0.29024 | 993312.3652 | 0.064893 | 43393.854 | 0.082128 | 47493.8347 | 0.082128 | 112573.6766 | 0.082128 | 53740.9308 | 1250514.6612
0.91454 | 1128391.5685 | 0.13353 | 44520.8483 | 0.63896 | 59404.6801 | 0.63896 | 135071.4159 | 0.63896 | 56320.4413 | 1423708.9541
0.8483 | 1104595.6822 | 0.74756 | 50084.096 | 0.03317 | 45491.4317 | 0.03317 | 107990.7997 | 0.03317 | 53288.634 | 1361450.6436
0.96843 | 1156477.9979 | 0.43235 | 47495.2357 | 0.92187 | 68815.0294 | 0.92187 | 145729.6442 | 0.92187 | 58288.3471 | 1476806.2543
0.60853 | 1046740.5327 | 0.46408 | 47736.5712 | 0.22551 | 51103.5544 | 0.22551 | 120835.2006 | 0.22551 | 54556.2833 | 1320972.1422
0.12146 | 960363.4528 | 0.049102 | 43056.2936 | 0.042361 | 45945.5736 | 0.042361 | 109030.1891 | 0.042361 | 53391.2142 | 1211786.7233
0.60733 | 1046506.9423 | 0.72613 | 49871.297 | 0.92708 | 69092.3968 | 0.92708 | 146043.7925 | 0.92708 | 58346.3506 | 1369860.779
0.86407 | 1109690.9223 | 0.72711 | 49880.8626 | 0.8919 | 67372.0384 | 0.8919 | 144095.3024 | 0.8919 | 57986.5868 | 1429025.7124
0.17417 | 972283.8426 | 0.733 | 49938.57 | 0.18403 | 50223.7061 | 0.18403 | 118821.5019 | 0.18403 | 54357.5459 | 1245625.1664
0.15886 | 969035.5782 | 0.32341 | 46590.6305 | 0.19457 | 50456.0416 | 0.19457 | 119353.2455 | 0.19457 | 54410.0251 | 1239845.521
0.94583 | 1142987.3146 | 0.9827 | 53860.5798 | 0.59 | 58249.7454 | 0.59 | 133700.9885 | 0.59 | 56078.9197 | 1444877.548
0.11537 | 958830.323 | 0.79176 | 50553.4654 | 0.79836 | 63850.7391 | 0.79836 | 140107.0538 | 0.79836 | 57250.2076 | 1270591.789
0.32814 | 999217.6338 | 0.95046 | 52933.634 | 0.631 | 59211.7705 | 0.631 | 134852.0716 | 0.631 | 56280.0998 | 1302495.2097
0.23675 | 984275.7935 | 0.90066 | 51990.6599 | 0.15632 | 49579.4343 | 0.15632 | 117346.9645 | 0.15632 | 54212.0197 | 1257404.872
0.6353 | 1052073.6229 | 0.68744 | 49507.3188 | 0.18788 | 50309.3988 | 0.18788 | 119017.6259 | 0.18788 | 54376.9019 | 1325284.8683
0.38244 | 1007507.2048 | 0.72194 | 49830.7117 | 0.12566 | 48795.4955 | 0.12566 | 115552.7727 | 0.12566 | 54034.946 | 1275721.1307
0.64727 | 1054522.1774 | 0.33589 | 46701.2943 | 0.87045 | 66460.25 | 0.87045 | 143062.6044 | 0.87045 | 57795.9123 | 1368542.2384
0.077514 | 948222.7156 | 0.8789 | 51656.6003 | 0.76671 | 62856.3253 | 0.76671 | 138980.7736 | 0.76671 | 57042.2543 | 1258758.6691
0.29565 | 994178.6092 | 0.27789 | 46167.6631 | 0.98828 | 73830.0868 | 0.98828 | 151409.7338 | 0.98828 | 59337.1032 | 1324923.196
0.82721 | 1098178.8563 | 0.60322 | 48786.0713 | 0.76037 | 62665.3003 | 0.76037 | 138764.4174 | 0.76037 | 57002.3069 | 1405396.9522
0.66798 | 1058856.6501 | 0.78397 | 50467.2985 | 0.68066 | 60452.03 | 0.68066 | 136257.6517 | 0.68066 | 56539.4646 | 1362573.0949
0.25254 | 987040.7666 | 0.14164 | 44632.0837 | 0.066496 | 46943.414 | 0.066496 | 111313.935 | 0.066496 | 53616.6034 | 1243546.8027
0.2226 | 981719.2395 | 0.37087 | 47000.9289 | 0.60827 | 58672.2742 | 0.60827 | 134218.8012 | 0.60827 | 56167.2795 | 1277778.5233
0.12956 | 962345.3672 | 0.78688 | 50499.2924 | 0.71676 | 61415.3217 | 0.71676 | 137348.6828 | 0.71676 | 56740.9096 | 1268349.5736
0.11477 | 958678.2029 | 0.28422 | 46228.4567 | 0.25666 | 51711.8905 | 0.25666 | 122227.4925 | 0.25666 | 54693.6925 | 1233539.7351
0.52192 | 1030633.4649 | 0.7867 | 50497.2946 | 0.14224 | 49230.0148 | 0.14224 | 116547.2519 | 0.14224 | 54133.0939 | 1301041.1201
0.56755 | 1038918.7353 | 0.50776 | 48056.1191 | 0.85587 | 65882.8405 | 0.85587 | 142408.6263 | 0.85587 | 57675.1636 | 1352941.4847
0.9211 | 1131194.7326 | 0.60203 | 48776.4821 | 0.020321 | 44732.7396 | 0.020321 | 106254.3897 | 0.020321 | 53117.2629 | 1384075.607
0.26375 | 988952.6537 | 0.85624 | 51339.2345 | 0.8158 | 64431.9588 | 0.8158 | 140765.3474 | 0.8158 | 57371.7531 | 1302860.9474
0.84147 | 1102471.4308 | 0.31244 | 46491.5729 | 0.54088 | 57158.158 | 0.54088 | 132267.4233 | 0.54088 | 55850.6453 | 1394239.2303
0.39012 | 1008707.0645 | 0.88302 | 51717.3356 | 0.3793 | 53929.4835 | 0.3793 | 127021.3972 | 0.3793 | 55175.4603 | 1296550.741
0.5957 | 1044249.398 | 0.37838 | 47063.39 | 0.95576 | 70840.8148 | 0.95576 | 148024.0631 | 0.95576 | 58711.9823 | 1368889.6482
0.97014 | 1157673.283 | 0.64075 | 49096.9546 | 0.58288 | 58087.6585 | 0.58288 | 133497.0506 | 0.58288 | 56045.0238 | 1454399.9705
0.87183 | 1112304.5375 | 0.36849 | 46981.0215 | 0.47616 | 55805.8244 | 0.47616 | 130275.5243 | 0.47616 | 55567.8434 | 1400934.7511
0.49813 | 1026471.0588 | 0.69704 | 49595.4188 | 0.3535 | 53454.8557 | 0.3535 | 126086.1524 | 0.3535 | 55076.2054 | 1310683.6911
0.58435 | 1042079.6665 | 0.33392 | 46683.9667 | 0.30021 | 52503.7562 | 0.30021 | 124039.8243 | 0.30021 | 54872.5565 | 1320179.7703
0.44845 | 1018085.4794 | 0.38926 | 47152.8482 | 0.94033 | 69846.8514 | 0.94033 | 146898.2931 | 0.94033 | 58504.1232 | 1340487.5953
0.94325 | 1141645.9506 | 0.68636 | 49497.4946 | 0.78129 | 63305.2723 | 0.78129 | 139489.2542 | 0.78129 | 57136.1388 | 1451074.1104
0.75911 | 1079777.3042 | 0.75974 | 50209.0204 | 0.55378 | 57438.9904 | 0.55378 | 132650.0803 | 0.55378 | 55909.3734 | 1375984.7688
0.64336 | 1053718.3042 | 0.68653 | 49499.0881 | 0.44705 | 55224.8119 | 0.44705 | 129335.3343 | 0.44705 | 55446.3412 | 1343223.8797
0.13654 | 964002.2484 | 0.066141 | 43418.679 | 0.46375 | 55556.2302 | 0.46375 | 129878.366 | 0.46375 | 55515.6479 | 1248371.1716
0.48942 | 1024972.7134 | 0.14846 | 44723.3683 | 0.021016 | 44779.0817 | 0.021016 | 106360.4525 | 0.021016 | 53127.7306 | 1273963.3466
0.16803 | 970998.2457 | 0.26964 | 46087.4105 | 0.52976 | 56919.3424 | 0.52976 | 131934.049 | 0.52976 | 55800.7039 | 1261739.7516
0.70734 | 1067488.4092 | 0.55898 | 48437.9773 | 0.68664 | 60607.8007 | 0.68664 | 136434.0788 | 0.68664 | 56572.0396 | 1369540.3056
0.22754 | 982621.7212 | 0.34386 | 46770.9023 | 0.13695 | 49094.3997 | 0.13695 | 116236.8712 | 0.13695 | 54102.4615 | 1248826.356
0.58532 | 1042263.4997 | 0.0905 | 43863.1706 | 0.35181 | 53424.016 | 0.35181 | 126023.5481 | 0.35181 | 55069.7562 | 1320643.9906
0.064022 | 943825.1944 | 0.73052 | 49914.2376 | 0.84172 | 65349.8143 | 0.84172 | 141804.917 | 0.84172 | 57563.6963 | 1258457.8597
0.07369 | 947018.0496 | 0.7264 | 49873.9792 | 0.19006 | 50357.5558 | 0.19006 | 119127.8423 | 0.19006 | 54387.7794 | 1220765.2063
0.13364 | 963318.5846 | 0.42651 | 47449.8797 | 0.41259 | 54556.5732 | 0.41259 | 128182.0559 | 0.41259 | 55306.5982 | 1248813.6915
0.90496 | 1124485.2888 | 0.51087 | 48078.6596 | 0.56722 | 57735.7702 | 0.56722 | 133043.8297 | 0.56722 | 55971.4364 | 1419314.9846
0.15094 | 967292.0629 | 0.3282 | 46633.3477 | 0.7067 | 61141.0137 | 0.7067 | 137037.9996 | 0.7067 | 56683.5459 | 1268787.9699
0.30915 | 996304.1031 | 0.005542 | 41558.0189 | 0.41638 | 54629.2203 | 0.41638 | 128311.4255 | 0.41638 | 55321.7902 | 1276124.5581
0.64032 | 1053095.6851 | 0.15123 | 44759.6784 | 0.34818 | 53358.158 | 0.34818 | 125889.0742 | 0.34818 | 55055.9839 | 1332158.5796
0.65371 | 1055856.7586 | 0.49882 | 47991.5309 | 0.19138 | 50386.4557 | 0.19138 | 119193.9852 | 0.19138 | 54394.3073 | 1327823.0377
0.030872 | 930432.6385 | 0.98202 | 53834.7467 | 0.28359 | 52208.7052 | 0.28359 | 123364.5465 | 0.28359 | 54805.9114 | 1214646.5484
0.39853 | 1010031.3045 | 0.21125 | 45479.9693 | 0.018989 | 44641.6681 | 0.018989 | 106045.9555 | 0.018989 | 53096.692 | 1259295.5894
0.14325 | 965556.0113 | 0.086665 | 43797.5696 | 0.3661 | 53685.4788 | 0.3661 | 126547.0862 | 0.3661 | 55124.4337 | 1244710.5796
0.85517 | 1106780.6892 | 0.30709 | 46442.6481 | 0.59812 | 58436.3372 | 0.59812 | 133932.089 | 0.59812 | 56117.94 | 1401709.7035
0.87712 | 1114135.4652 | 0.079412 | 43669.3919 | 0.84487 | 65466.5472 | 0.84487 | 141937.1295 | 0.84487 | 57588.1077 | 1422796.6416
0.93322 | 1136700.7335 | 0.16657 | 44955.7242 | 0.69277 | 60768.8802 | 0.69277 | 136616.5186 | 0.69277 | 56605.7248 | 1435647.5813
0.11115 | 957746.3651 | 0.87929 | 51662.3343 | 0.43857 | 55058.507 | 0.43857 | 129055.8215 | 0.43857 | 55411.5633 | 1248934.5913
0.48082 | 1023503.9855 | 0.54141 | 48304.5989 | 0.54378 | 57220.9438 | 0.54378 | 132353.8419 | 0.54378 | 55863.7752 | 1317247.1452
0.38559 | 1007998.9472 | 0.73111 | 49920.0094 | 0.42798 | 54852.6463 | 0.42798 | 128703.0609 | 0.42798 | 55368.5134 | 1296843.1772
0.75948 | 1079869.4603 | 0.097225 | 43974.9398 | 0.47611 | 55804.7829 | 0.47611 | 130273.8875 | 0.47611 | 55567.6256 | 1365490.6961
0.56916 | 1039219.7555 | 0.44624 | 47601.9381 | 0.81614 | 64443.6384 | 0.81614 | 140778.5758 | 0.81614 | 57374.1955 | 1349418.1033
0.46492 | 1020821.5579 | 0.83525 | 51067.1115 | 0.67707 | 60359.414 | 0.67707 | 136152.7542 | 0.67707 | 56520.0966 | 1324920.9343
0.65461 | 1056044.0402 | 0.88205 | 51703.0499 | 0.87533 | 66660.3352 | 0.87533 | 143289.2223 | 0.87533 | 57837.7544 | 1375534.402
0.25183 | 986918.7532 | 0.20786 | 45442.2495 | 0.32279 | 52902.0706 | 0.32279 | 124927.191 | 0.32279 | 54960.1331 | 1265150.3974
0.70164 | 1066203.4238 | 0.98646 | 54014.9735 | 0.20871 | 50757.96 | 0.20871 | 120044.2428 | 0.20871 | 54478.2215 | 1345498.8218
0.97979 | 1165181.0124 | 0.05588 | 43206.9934 | 0.66134 | 59958.7968 | 0.66134 | 135699.0123 | 0.66134 | 56436.319 | 1460482.1339
0.26557 | 989259.4478 | 0.79909 | 50635.9196 | 0.080392 | 47435.4579 | 0.080392 | 112440.0703 | 0.080392 | 53727.7448 | 1253498.6403
0.47603 | 1022691.5092 | 0.607 | 48816.762 | 0.21122 | 50810.3518 | 0.21122 | 120164.1511 | 0.21122 | 54490.0556 | 1296972.8296
0.56161 | 1037816.1073 | 0.41159 | 47332.5115 | 0.74301 | 62155.0417 | 0.74301 | 138186.4948 | 0.74301 | 56895.6009 | 1342385.7561
0.78759 | 1087108.3097 | 0.98849 | 54107.6566 | 0.73446 | 61910.3271 | 0.73446 | 137909.3293 | 0.73446 | 56844.4258 | 1397880.0484
0.59046 | 1043243.6751 | 0.072101 | 43534.1303 | 0.16237 | 49724.6951 | 0.16237 | 117679.4213 | 0.16237 | 54244.8308 | 1308426.7526
0.63329 | 1051668.021 | 0.63713 | 49066.3283 | 0.64483 | 59548.3594 | 0.64483 | 135234.148 | 0.64483 | 56350.4877 | 1351867.3443
0.18196 | 973883.9992 | 0.63235 | 49026.0249 | 0.76114 | 62688.5275 | 0.76114 | 138790.7246 | 0.76114 | 57007.1642 | 1281396.4403
0.68398 | 1062300.7165 | 0.74174 | 50025.385 | 0.56571 | 57702.1943 | 0.56571 | 132999.8196 | 0.56571 | 55964.415 | 1358992.5305
0.45263 | 1018776.5187 | 0.39613 | 47208.6409 | 0.45685 | 55418.678 | 0.45685 | 129655.202 | 0.45685 | 55486.8828 | 1306545.9224
0.21664 | 980617.9919 | 0.15707 | 44835.4986 | 0.34158 | 53238.7267 | 0.34158 | 125642.4426 | 0.34158 | 55031.0082 | 1259365.668
0.88392 | 1116544.9038 | 0.3773 | 47054.4601 | 0.21077 | 50801.1221 | 0.21077 | 120143.0273 | 0.21077 | 54487.9708 | 1389031.4842
0.23984 | 984824.4626 | 0.40969 | 47317.3904 | 0.0014127 | 42720.5311 | 0.0014127 | 101649.0713 | 0.0014127 | 52662.7514 | 1229174.2068
0.90777 | 1125610.5244 | 0.9058 | 52074.8632 | 0.14032 | 49181.1273 | 0.14032 | 116435.3638 | 0.14032 | 54122.0513 | 1397423.9301
0.50621 | 1027874.5316 | 0.80545 | 50708.7431 | 0.12994 | 48910.3417 | 0.12994 | 115815.6199 | 0.12994 | 54060.8871 | 1297370.1234
0.52296 | 1030818.2095 | 0.12674 | 44425.0009 | 0.6512 | 59705.6565 | 0.6512 | 135412.3038 | 0.6512 | 56383.3819 | 1326744.5526
0.94884 | 1144598.3764 | 0.09002 | 43855.0376 | 0.24425 | 51474.3562 | 0.24425 | 121683.8504 | 0.24425 | 54640.0389 | 1416251.6596
0.59308 | 1043746.084 | 0.76718 | 50286.8266 | 0.62292 | 59018.0995 | 0.62292 | 134628.2407 | 0.62292 | 56239.599 | 1343918.8498
0.22315 | 981820.6587 | 0.59627 | 48730.181 | 0.70282 | 61036.4529 | 0.70282 | 136919.5733 | 0.70282 | 56661.68 | 1285168.5459
0.2703 | 990049.6253 | 0.087584 | 43813.4274 | 0.97799 | 72655.69 | 0.97799 | 150079.6037 | 0.97799 | 59091.5116 | 1315689.8581
0.62523 | 1050045.544 | 0.12492 | 44398.9115 | 0.50986 | 56498.8569 | 0.50986 | 131328.524 | 0.50986 | 55712.7713 | 1337984.6078
0.79274 | 1088486.02 | 0.7323 | 49931.6413 | 0.62125 | 58978.4593 | 0.62125 | 134581.9487 | 0.62125 | 56231.3094 | 1388209.3787
0.4182 | 1013162.3815 | 0.64209 | 49108.3466 | 0.57051 | 57809.1285 | 0.57051 | 133139.5163 | 0.57051 | 55986.7772 | 1309206.1501
0.79715 | 1089676.4589 | 0.75147 | 50123.8259 | 0.6107 | 58729.0495 | 0.6107 | 134286.893 | 0.6107 | 56179.1524 | 1388995.3797
0.3479 | 1002196.5393 | 0.56943 | 48518.542 | 0.50045 | 56303.112 | 0.50045 | 131038.2486 | 0.50045 | 55671.8369 | 1293728.2789
0.006541 | 914008.2332 | 0.64767 | 49156.0569 | 0.59468 | 58357.0805 | 0.59468 | 133834.4019 | 0.59468 | 56101.3658 | 1211457.1383
0.0084239 | 915897.1209 | 0.14864 | 44725.6591 | 0.42355 | 54767.0276 | 0.42355 | 128554.0816 | 0.42355 | 55350.6087 | 1199294.4979
0.19866 | 977198.9987 | 0.26204 | 46012.3645 | 0.31335 | 52734.7574 | 0.31335 | 124560.122 | 0.31335 | 54923.9061 | 1255430.1486
0.48708 | 1024572.1445 | 0.15889 | 44858.7905 | 0.7078 | 61170.843 | 0.7078 | 137071.7845 | 0.7078 | 56689.7838 | 1324363.3464
0.48986 | 1025047.3907 | 0.33706 | 46711.5473 | 0.18547 | 50255.8122 | 0.18547 | 118894.9828 | 0.18547 | 54364.7979 | 1295274.5309
0.34012 | 1001021.1516 | 0.81494 | 50819.7218 | 0.5203 | 56718.3178 | 0.5203 | 131647.5716 | 0.5203 | 55758.6653 | 1295965.4281
0.094632 | 953281.8389 | 0.59015 | 48681.288 | 0.13107 | 48940.2537 | 0.13107 | 115884.0792 | 0.13107 | 54067.6435 | 1220855.1033
0.35911 | 1003904.5179 | 0.13476 | 44537.9191 | 0.34544 | 53308.6186 | 0.34544 | 125787.2098 | 0.34544 | 55045.6241 | 1282583.8896
0.39574 | 1009590.9598 | 0.048619 | 43045.1755 | 0.13482 | 49038.9416 | 0.13482 | 116109.945 | 0.13482 | 54089.9348 | 1271874.9567
0.71269 | 1068704.1416 | 0.55321 | 48393.8509 | 0.70816 | 61180.5008 | 0.70816 | 137082.723 | 0.70816 | 56691.8035 | 1372053.0198
0.63866 | 1052758.2346 | 0.72887 | 49898.0122 | 0.56058 | 57588.6785 | 0.56058 | 132850.0196 | 0.56058 | 55940.6764 | 1349035.6213
0.83359 | 1100076.3134 | 0.82027 | 50883.2421 | 0.057615 | 46601.4843 | 0.057615 | 110531.3644 | 0.057615 | 53539.3694 | 1361631.7735
0.75551 | 1078883.2731 | 0.6862 | 49496.0443 | 0.85853 | 65985.9613 | 0.85853 | 142525.4216 | 0.85853 | 57696.7283 | 1394587.4285
0.7131 | 1068798.8696 | 0.047936 | 43029.3606 | 0.045999 | 46111.5162 | 0.045999 | 109409.98 | 0.045999 | 53428.6968 | 1320778.4233
0.52425 | 1031047.7199 | 0.35572 | 46872.9703 | 0.88599 | 67112.5796 | 0.88599 | 143801.4374 | 0.88599 | 57932.3284 | 1346767.0355
0.91507 | 1128614.5857 | 0.64955 | 49172.2007 | 0.40592 | 54429.6345 | 0.40592 | 127953.5497 | 0.40592 | 55280.0526 | 1415450.0231
0.0024613 | 908593.0279 | 0.38179 | 47091.5519 | 0.28552 | 52243.5325 | 0.28552 | 123444.2554 | 0.28552 | 54813.7781 | 1186186.1458
0.90938 | 1126261.7269 | 0.34988 | 46822.92 | 0.26063 | 51786.8457 | 0.26063 | 122399.0416 | 0.26063 | 54710.6231 | 1401981.1573
0.75064 | 1077681.3358 | 0.45717 | 47684.7352 | 0.53031 | 56931.0383 | 0.53031 | 131950.5503 | 0.53031 | 55803.1497 | 1370050.8093
0.38995 | 1008681.5008 | 0.36338 | 46937.9822 | 0.84415 | 65439.5263 | 0.84415 | 141906.5254 | 0.84415 | 57582.457 | 1320547.9918
0.29209 | 993609.549 | 0.008934 | 41762.4317 | 0.54294 | 57202.7417 | 0.54294 | 132328.8403 | 0.54294 | 55859.9688 | 1280763.5315
0.19193 | 975881.3332 | 0.021362 | 42288.2109 | 0.010613 | 43974.8991 | 0.010613 | 104519.9289 | 0.010613 | 52946.0842 | 1219610.4564
0.54055 | 1033965.9827 | 0.35093 | 46831.9454 | 0.19725 | 50514.1333 | 0.19725 | 119486.1993 | 0.19725 | 54423.1467 | 1305221.4074
0.59445 | 1044009.7205 | 0.78633 | 50493.2948 | 0.6181 | 58903.4993 | 0.6181 | 134493.9607 | 0.6181 | 56215.6336 | 1344116.1089
0.92206 | 1131613.676 | 0.21197 | 45487.9169 | 0.32044 | 52860.4122 | 0.32044 | 124836.5404 | 0.32044 | 54951.1866 | 1409749.7321
0.90273 | 1123604.8125 | 0.45142 | 47641.2671 | 0.80392 | 64033.0507 | 0.80392 | 140313.5413 | 0.80392 | 57288.3328 | 1432881.0045
0.39198 | 1008999.6277 | 0.3751 | 47036.2397 | 0.93978 | 69814.2649 | 0.93978 | 146861.3855 | 0.93978 | 58497.3087 | 1331208.8265
0.62881 | 1050763.6184 | 0.43484 | 47514.5073 | 0.11771 | 48577.0003 | 0.11771 | 115052.7051 | 0.11771 | 53985.5929 | 1315893.424
0.86183 | 1108950.2741 | 0.51333 | 48096.6471 | 0.86928 | 66412.6325 | 0.86928 | 143008.6725 | 0.86928 | 57785.9544 | 1424254.1807
0.84662 | 1104068.897 | 0.97414 | 53562.5189 | 0.097694 | 47991.8767 | 0.097694 | 113713.5395 | 0.097694 | 53853.427 | 1373190.2591
0.39536 | 1009530.9867 | 0.23655 | 45752.3564 | 0.56171 | 57613.6345 | 0.56171 | 132883.0865 | 0.56171 | 55945.8952 | 1301725.9593
0.84115 | 1102374.6935 | 0.02869 | 42524.6946 | 0.74601 | 62242.0012 | 0.74601 | 138284.9859 | 0.74601 | 56913.786 | 1402340.1612
0.69187 | 1064030.0018 | 0.21879 | 45562.8416 | 0.66972 | 60171.0822 | 0.66972 | 135939.4483 | 0.66972 | 56480.7124 | 1362184.0864
0.56239 | 1037960.2587 | 0.055784 | 43204.9283 | 0.39416 | 54207.2224 | 0.39416 | 127545.4436 | 0.39416 | 55233.5414 | 1318151.3945
0.1041 | 955884.7276 | 0.72717 | 49881.409 | 0.96142 | 71248.2785 | 0.96142 | 148485.5594 | 0.96142 | 58797.1917 | 1284297.1662
0.7652 | 1081306.5648 | 0.42492 | 47437.4356 | 0.35988 | 53571.3909 | 0.35988 | 126320.6408 | 0.35988 | 55100.5754 | 1363736.6075
0.020413 | 924746.2971 | 0.13516 | 44543.4156 | 0.85781 | 65958.0521 | 0.85781 | 142493.8114 | 0.85781 | 57690.8919 | 1235432.4681
0.37607 | 1006516.251 | 0.35687 | 46882.7863 | 0.14924 | 49405.6707 | 0.14924 | 116949.2737 | 0.14924 | 54172.7705 | 1273926.7522
0.8905 | 1118943.8968 | 0.096047 | 43955.6513 | 0.64302 | 59503.9814 | 0.64302 | 135183.8852 | 0.64302 | 56341.2073 | 1413928.622
0.34115 | 1001176.6534 | 0.83121 | 51016.664 | 0.30151 | 52526.4987 | 0.30151 | 124091.7678 | 0.30151 | 54877.6829 | 1283689.2668
0.14016 | 964845.402 | 0.33839 | 46723.1615 | 0.5347 | 57025.2226 | 0.5347 | 132082.7723 | 0.5347 | 55822.8457 | 1256499.4042
0.10457 | 956010.1472 | 0.6345 | 49044.144 | 0.35065 | 53403.0096 | 0.35065 | 125980.7719 | 0.35065 | 55065.3633 | 1239503.436
0.66766 | 1058790.2832 | 0.32216 | 46579.3626 | 0.15478 | 49542.0169 | 0.15478 | 117261.3277 | 0.15478 | 54203.568 | 1326376.5583
0.11774 | 959432.4661 | 0.41353 | 47347.8613 | 0.48295 | 55943.5472 | 0.48295 | 130490.4928 | 0.48295 | 55596.6442 | 1248811.0117
0.090958 | 952237.2343 | 0.68302 | 49467.2015 | 0.32666 | 52971.1491 | 0.32666 | 125076.4446 | 0.32666 | 54974.8634 | 1234726.8928
0.45215 | 1018696.7856 | 0.77799 | 50402.2715 | 0.14158 | 49213.3449 | 0.14158 | 116509.0998 | 0.14158 | 54129.3285 | 1288950.8304
0.6494 | 1054961.2084 | 0.24649 | 45855.2898 | 0.46686 | 55618.4423 | 0.46686 | 129978.2876 | 0.46686 | 55528.6578 | 1341941.8859
0.44749 | 1017927.1742 | 0.047309 | 43014.7306 | 0.97349 | 72231.7907 | 0.97349 | 149599.4923 | 0.97349 | 59002.8652 | 1341776.0531
0.032455 | 931203.5484 | 0.32549 | 46609.2317 | 0.55648 | 57498.3333 | 0.55648 | 132729.6749 | 0.55648 | 55921.7833 | 1223962.5716
0.5833 | 1041879.7278 | 0.98569 | 53981.7348 | 0.24679 | 51523.4879 | 0.24679 | 121796.2977 | 0.24679 | 54651.1367 | 1323832.3849
0.64159 | 1053355.6956 | 0.96791 | 53375.9873 | 0.13143 | 48949.8603 | 0.13143 | 115906.0656 | 0.13143 | 54069.8134 | 1325657.4222
0.9016 | 1123163.9316 | 0.45135 | 47640.7685 | 0.19972 | 50567.2589 | 0.19972 | 119607.7873 | 0.19972 | 54435.1465 | 1395414.8929
0.27364 | 990604.9562 | 0.089297 | 43842.7452 | 0.88406 | 67029.1921 | 0.88406 | 143706.9922 | 0.88406 | 57914.8902 | 1303098.7759
0.92438 | 1132640.6129 | 0.71903 | 49802.6579 | 0.48631 | 56012.1796 | 0.48631 | 130596.5363 | 0.48631 | 55610.9967 | 1424662.9834
0.23227 | 983474.3935 | 0.64955 | 49172.19 | 0.37613 | 53870.5975 | 0.37613 | 126908.1511 | 0.37613 | 55163.1459 | 1268588.478
0.90383 | 1124040.0192 | 0.84216 | 51154.62 | 0.89317 | 67428.8389 | 0.89317 | 144159.635 | 0.89317 | 57998.465 | 1444781.5781
0.82877 | 1098639.909 | 0.53192 | 48233.6285 | 0.72552 | 61658.3849 | 0.72552 | 137623.9779 | 0.72552 | 56791.7393 | 1402947.6396
0.21667 | 980622.8622 | 0.49331 | 47951.6927 | 0.063716 | 46838.9748 | 0.063716 | 111074.9063 | 0.063716 | 53593.013 | 1240081.449
0.88239 | 1115996.8399 | 0.83392 | 51050.3779 | 0.18154 | 50168.0474 | 0.18154 | 118694.1166 | 0.18154 | 54344.9739 | 1390254.3556
0.25581 | 987602.2469 | 0.26443 | 46036.0507 | 0.041025 | 45882.8723 | 0.041025 | 108886.6852 | 0.041025 | 53377.0514 | 1241784.9066
0.62165 | 1049332.3896 | 0.63599 | 49056.6731 | 0.31839 | 52823.8949 | 0.31839 | 124756.6745 | 0.31839 | 54943.3044 | 1330912.9365
0.98249 | 1167583.046 | 0.34229 | 46757.2135 | 0.62976 | 59181.9182 | 0.62976 | 134817.822 | 0.62976 | 56273.857 | 1464613.8567
0.65537 | 1056202.767 | 0.26071 | 45999.1225 | 0.58036 | 58030.4037 | 0.58036 | 133424.2933 | 0.58036 | 56033.0506 | 1349689.637
0.56719 | 1038852.0919 | 0.24817 | 45872.5388 | 0.16607 | 49812.1146 | 0.16607 | 117879.4971 | 0.16607 | 54264.5768 | 1306680.8193
0.24466 | 985672.2523 | 0.79569 | 50597.4869 | 0.40273 | 54369.0223 | 0.40273 | 127843.3201 | 0.40273 | 55267.3773 | 1273749.4587
0.66987 | 1059259.5613 | 0.2099 | 45465.0315 | 0.11687 | 48553.6713 | 0.11687 | 114999.3124 | 0.11687 | 53980.3234 | 1322257.8999
0.074535 | 947286.9074 | 0.77163 | 50334.0487 | 0.14246 | 49235.5555 | 0.14246 | 116559.933 | 0.14246 | 54134.3454 | 1217550.7901
0.46127 | 1020212.3883 | 0.17915 | 45109.8453 | 0.10331 | 48161.6338 | 0.10331 | 114102.0606 | 0.10331 | 53891.7712 | 1281477.6992
0.10032 | 954860.3405 | 0.25935 | 45985.5222 | 0.10033 | 48072.3147 | 0.10033 | 113897.637 | 0.10033 | 53871.5961 | 1216687.4104
0.093833 | 953056.6002 | 0.10377 | 44080.0733 | 0.02507 | 45035.3426 | 0.02507 | 106946.9539 | 0.02507 | 53185.614 | 1202304.584
0.74461 | 1076213.0113 | 0.68126 | 49451.3737 | 0.58188 | 58064.8039 | 0.58188 | 133468.0531 | 0.58188 | 56040.2444 | 1373237.4865
0.91652 | 1129228.6777 | 0.34652 | 46793.9534 | 0.36744 | 53710.1503 | 0.36744 | 126595.6567 | 0.36744 | 55129.593 | 1411458.031
0.71751 | 1069809.8409 | 0.17714 | 45085.5592 | 0.12677 | 48825.6284 | 0.12677 | 115621.7375 | 0.12677 | 54041.7523 | 1333384.5183
0.40549 | 1011133.0114 | 0.96862 | 53396.2665 | 0.47725 | 55827.807 | 0.47725 | 130310.0329 | 0.47725 | 55572.4404 | 1306239.5583
0.47621 | 1022722.8282 | 0.4691 | 47773.9834 | 0.68386 | 60535.3067 | 0.68386 | 136351.9715 | 0.68386 | 56556.8796 | 1323940.9693
0.56554 | 1038544.7998 | 0.63241 | 49026.5143 | 0.085099 | 47592.3066 | 0.085099 | 112799.0481 | 0.085099 | 53763.1733 | 1301725.842
0.7352 | 1073952.959 | 0.63101 | 49014.811 | 0.99213 | 74401.5622 | 0.99213 | 152056.9909 | 0.99213 | 59456.6109 | 1408882.9341
0.14181 | 965224.6784 | 0.67814 | 49423.3036 | 0.087242 | 47662.2673 | 0.087242 | 112959.1662 | 0.087242 | 53778.9758 | 1229048.3913
0.045639 | 937002.1072 | 0.0023536 | 41293.9844 | 0.53133 | 56952.8648 | 0.53133 | 131981.2958 | 0.53133 | 55807.7141 | 1223037.9664
0.8978 | 1121693.2645 | 0.54215 | 48310.1503 | 0.66383 | 60021.5795 | 0.66383 | 135770.1204 | 0.66383 | 56449.4482 | 1422244.5629
0.36202 | 1004349.6153 | 0.99644 | 54592.1695 | 0.92898 | 69195.9585 | 0.92898 | 146161.0872 | 0.92898 | 58368.0076 | 1332666.8381
0.48445 | 1024121.5429 | 0.12785 | 44440.8266 | 0.52619 | 56843.217 | 0.52619 | 131826.2024 | 0.52619 | 55784.7844 | 1313016.5733
0.47985 | 1023339.4048 | 0.28515 | 46237.334 | 0.59271 | 58311.8176 | 0.59271 | 133778.2995 | 0.59271 | 56091.9003 | 1317758.7562
0.089406 | 951789.7083 | 0.29983 | 46375.5197 | 0.42131 | 54723.9037 | 0.42131 | 128478.5307 | 0.42131 | 55341.5906 | 1236709.2531
0.56005 | 1037528.9969 | 0.038105 | 42787.6407 | 0.22177 | 51027.8433 | 0.22177 | 120661.9214 | 0.22177 | 54539.1819 | 1306545.5842
0.37522 | 1006384.1785 | 0.52567 | 48187.2686 | 0.76643 | 62847.6311 | 0.76643 | 138970.9265 | 0.76643 | 57040.4362 | 1313430.4409
0.66772 | 1058802.5847 | 0.91396 | 52213.2909 | 0.89972 | 67726.8715 | 0.89972 | 144497.1889 | 0.89972 | 58060.79 | 1381300.726
0.47711 | 1022874.8575 | 0.96018 | 53168.1865 | 0.9595 | 71106.5488 | 0.9595 | 148325.0354 | 0.9595 | 58767.553 | 1354242.1812
0.92712 | 1133870.9725 | 0.7425 | 50033.0024 | 0.32176 | 52883.8888 | 0.32176 | 124887.6865 | 0.32176 | 54956.2343 | 1416631.7846
0.69654 | 1065063.4561 | 0.68808 | 49513.199 | 0.97509 | 72377.9594 | 0.97509 | 149765.0441 | 0.97509 | 59033.4322 | 1395753.0908
0.29435 | 993970.8747 | 0.6477 | 49156.3173 | 0.79933 | 63882.3867 | 0.79933 | 140142.8981 | 0.79933 | 57256.8258 | 1304409.3026
0.29418 | 993942.8167 | 0.26288 | 46020.6417 | 0.89343 | 67440.6235 | 0.89343 | 144172.9823 | 0.89343 | 58000.9294 | 1309577.9935
0.55403 | 1036421.0889 | 0.72554 | 49865.5663 | 0.82838 | 64868.9512 | 0.82838 | 141260.2881 | 0.82838 | 57463.1376 | 1349879.0321
0.77034 | 1082612.9787 | 0.85201 | 51282.8572 | 0.62387 | 59040.8314 | 0.62387 | 134654.7134 | 0.62387 | 56244.3527 | 1383835.7333
0.99401 | 1181036.3158 | 0.30119 | 46388.1222 | 0.93198 | 69362.8275 | 0.93198 | 146350.0842 | 0.93198 | 58402.9035 | 1501540.2532
0.58447 | 1042102.7454 | 0.85722 | 51352.4326 | 0.53539 | 57040.0174 | 0.53539 | 132103.4363 | 0.53539 | 55825.9396 | 1338424.5713
0.85475 | 1106644.8079 | 0.80621 | 50717.5179 | 0.16145 | 49702.7452 | 0.16145 | 117629.1847 | 0.16145 | 54239.8728 | 1378934.1286
0.63321 | 1051650.5244 | 0.071719 | 43526.8689 | 0.8047 | 64059.1137 | 0.8047 | 140343.0603 | 0.8047 | 57293.7832 | 1356873.3505
0.98402 | 1169038.4483 | 0.95167 | 52961.5097 | 0.25699 | 51718.2606 | 0.25699 | 122242.0716 | 0.25699 | 54695.1313 | 1450655.4215
0.32029 | 998023.6931 | 0.78431 | 50471.0962 | 0.56102 | 57598.3253 | 0.56102 | 132862.8107 | 0.56102 | 55942.6938 | 1294898.6191
0.47271 | 1022130.7709 | 0.3951 | 47200.3402 | 0.36381 | 53643.2841 | 0.36381 | 126463.6911 | 0.36381 | 55115.6098 | 1304553.6961
0.073516 | 946962.388 | 0.2945 | 46325.7417 | 0.76463 | 62793.367 | 0.76463 | 138909.4666 | 0.76463 | 57029.0884 | 1252020.0517
0.33406 | 1000109.5059 | 0.92994 | 52504.8146 | 0.32531 | 52946.9787 | 0.32531 | 125024.3712 | 0.32531 | 54969.7241 | 1285555.3945
0.52962 | 1032004.1137 | 0.31422 | 46507.7272 | 0.96003 | 71145.8567 | 0.96003 | 148369.5558 | 0.96003 | 58775.7731 | 1356803.0266
0.28623 | 992665.9854 | 0.88366 | 51726.9071 | 0.13547 | 49055.9309 | 0.13547 | 116148.8282 | 0.13547 | 54093.7723 | 1263691.4239
0.95645 | 1148879.8725 | 0.4203 | 47401.2567 | 0.55201 | 57400.2321 | 0.55201 | 132597.8592 | 0.55201 | 55901.2682 | 1442180.4886
0.26031 | 988369.7715 | 0.055492 | 43198.6368 | 0.90258 | 67860.1079 | 0.90258 | 144648.0933 | 0.90258 | 58088.6526 | 1302165.262
0.86729 | 1110766.8169 | 0.6888 | 49519.7742 | 0.20109 | 50596.5303 | 0.20109 | 119674.7804 | 0.20109 | 54441.7583 | 1384999.6602
0.60092 | 1045259.0043 | 0.21676 | 45540.6139 | 0.19878 | 50547.0863 | 0.19878 | 119561.6186 | 0.19878 | 54430.59 | 1315338.9131
0.038967 | 934190.8707 | 0.67284 | 49375.9572 | 0.87498 | 66646.2329 | 0.87498 | 143273.2499 | 0.87498 | 57834.8053 | 1251321.116
0.79097 | 1088010.8686 | 0.10636 | 44120.7281 | 0.90989 | 68209.6136 | 0.90989 | 145043.946 | 0.90989 | 58161.7417 | 1403546.8981
0.23306 | 983616.2054 | 0.13979 | 44607.0573 | 0.9244 | 68948.2587 | 0.9244 | 145880.5407 | 0.9244 | 58316.2082 | 1301368.2703
0.077577 | 948242.1424 | 0.017685 | 42154.0845 | 0.019994 | 44710.6815 | 0.019994 | 106203.9056 | 0.019994 | 53112.2805 | 1194423.0945
0.68784 | 1063144.8406 | 0.42755 | 47457.9637 | 0.853 | 65772.6432 | 0.853 | 142283.816 | 0.853 | 57652.1189 | 1376311.3824
0.29541 | 994140.3642 | 0.36367 | 46940.4545 | 0.45601 | 55401.9665 | 0.45601 | 129627.8773 | 0.45601 | 55483.388 | 1281594.0506
0.89465 | 1120494.8006 | 0.54167 | 48306.5441 | 0.28591 | 52250.4895 | 0.28591 | 123460.1779 | 0.28591 | 54815.3496 | 1399327.3618
0.27519 | 990860.1407 | 0.67523 | 49397.2662 | 0.66233 | 59983.752 | 0.66233 | 135727.2768 | 0.66233 | 56441.5376 | 1292409.9733
0.93056 | 1135452.6857 | 0.47118 | 47789.4498 | 0.99601 | 75150.0473 | 0.99601 | 152904.7304 | 0.99601 | 59613.1352 | 1470910.0484
0.86426 | 1109752.6338 | 0.41789 | 47382.2878 | 0.26206 | 51813.6425 | 0.26206 | 122460.371 | 0.26206 | 54716.6759 | 1386125.611
0.51482 | 1029381.1646 | 0.18402 | 45167.9601 | 0.17147 | 49938.2637 | 0.17147 | 118168.2132 | 0.17147 | 54293.071 | 1296948.6727
0.74149 | 1075459.0258 | 0.22468 | 45626.4853 | 0.46472 | 55575.7389 | 0.46472 | 129909.767 | 0.46472 | 55519.7276 | 1362090.7445
0.74802 | 1077041.8509 | 0.58949 | 48676.0512 | 0.6867 | 60609.1994 | 0.6867 | 136435.663 | 0.6867 | 56572.3321 | 1379335.0966
0.023199 | 926381.2151 | 0.28912 | 46275.0126 | 0.849 | 65621.1166 | 0.849 | 142112.1959 | 0.849 | 57620.4315 | 1238009.9716
0.61031 | 1047090.5572 | 0.43668 | 47528.6927 | 0.90136 | 67803.1934 | 0.90136 | 144583.6316 | 0.90136 | 58076.7505 | 1365082.8254
0.007334 | 914833.0334 | 0.88339 | 51722.8461 | 0.67844 | 60394.6076 | 0.67844 | 136192.6147 | 0.67844 | 56527.4564 | 1219670.5582
0.22709 | 982539.131 | 0.64781 | 49157.2145 | 0.47624 | 55807.4334 | 0.47624 | 130278.0526 | 0.47624 | 55568.1799 | 1273350.0114
0.25434 | 987351.6583 | 0.60123 | 48770.0438 | 0.37817 | 53908.4553 | 0.37817 | 126981.0447 | 0.37817 | 55171.0628 | 1272182.2649
0.10193 | 955298.1613 | 0.44947 | 47626.4954 | 0.066764 | 46953.3637 | 0.066764 | 111336.7068 | 0.066764 | 53618.8508 | 1214833.578
0.42674 | 1014539.1794 | 0.17042 | 45003.5197 | 0.13928 | 49154.5239 | 0.13928 | 116374.4768 | 0.13928 | 54116.0422 | 1279187.7419
0.78247 | 1085756.6338 | 0.70905 | 49707.6955 | 0.096362 | 47950.8885 | 0.096362 | 113619.7304 | 0.096362 | 53844.1687 | 1350879.1169
0.56509 | 1038461.0283 | 0.37399 | 47026.939 | 0.62207 | 58997.9279 | 0.62207 | 134604.7047 | 0.62207 | 56235.3807 | 1335325.9806
0.71827 | 1069985.9677 | 0.92638 | 52437.2967 | 0.85816 | 65971.4102 | 0.85816 | 142508.941 | 0.85816 | 57693.6854 | 1388597.301
0.54031 | 1033923.692 | 0.9591 | 53140.7843 | 0.049936 | 46283.8549 | 0.049936 | 109804.4097 | 0.049936 | 53467.6242 | 1296620.3651
0.66064 | 1057306.6109 | 0.071307 | 43519.0305 | 0.42437 | 54782.7808 | 0.42437 | 128581.5942 | 0.42437 | 55353.903 | 1339543.9196
0.22862 | 982817.336 | 0.60596 | 48808.3033 | 0.75964 | 62643.4228 | 0.75964 | 138739.6388 | 0.75964 | 56997.7318 | 1290006.4327
0.25501 | 987466.4546 | 0.11508 | 44254.149 | 0.71904 | 61478.2074 | 0.71904 | 137419.9076 | 0.71904 | 56754.0603 | 1287372.7789
0.98106 | 1166287.478 | 0.10565 | 44109.6082 | 0.94205 | 69950.924 | 0.94205 | 147016.1665 | 0.94205 | 58525.8871 | 1485890.0638
0.16733 | 970852.116 | 0.92888 | 52484.4813 | 0.89506 | 67513.682 | 0.89506 | 144255.7289 | 0.89506 | 58016.2075 | 1293122.2155
0.35714 | 1003603.5159 | 0.73068 | 49915.7367 | 0.15202 | 49474.4884 | 0.15202 | 117106.776 | 0.15202 | 54188.3148 | 1274288.8318
0.69073 | 1063778.7784 | 0.35318 | 46851.2213 | 0.13979 | 49167.5618 | 0.13979 | 116404.3166 | 0.13979 | 54118.9872 | 1330320.8653
0.050659 | 938984.1453 | 0.44387 | 47583.8065 | 0.8093 | 64212.4519 | 0.8093 | 140516.7323 | 0.8093 | 57325.8495 | 1248622.9855
0.87606 | 1113766.3429 | 0.43505 | 47516.1352 | 0.33755 | 53166.1739 | 0.33755 | 125490.839 | 0.33755 | 55015.8359 | 1394955.3269
0.12232 | 960578.3566 | 0.91895 | 52301.1823 | 0.15399 | 49522.7515 | 0.15399 | 117217.2351 | 0.15399 | 54199.2163 | 1233818.7417
0.49032 | 1025126.3151 | 0.52508 | 48182.9234 | 0.71646 | 61407.2346 | 0.71646 | 137339.5232 | 0.71646 | 56739.2184 | 1328795.2147
0.4779 | 1023009.1676 | 0.31103 | 46478.6592 | 0.41321 | 54568.5016 | 0.41321 | 128203.3675 | 0.41321 | 55309.0927 | 1307568.7885
0.10925 | 957250.7462 | 0.76484 | 50262.2744 | 0.47444 | 55771.1424 | 0.47444 | 130220.9268 | 0.47444 | 55560.5906 | 1249065.6805
0.19502 | 976488.7821 | 0.94173 | 52742.0589 | 0.20232 | 50622.7247 | 0.20232 | 119734.7313 | 0.20232 | 54447.675 | 1254035.9721
0.28561 | 992564.6627 | 0.69318 | 49559.8831 | 0.82498 | 64749.1681 | 0.82498 | 141124.6208 | 0.82498 | 57438.0883 | 1305436.4231
0.14965 | 967003.471 | 0.099719 | 44015.4133 | 0.31016 | 52678.4139 | 0.31016 | 124434.69 | 0.31016 | 54911.5269 | 1243043.5151
0.97109 | 1158351.8685 | 0.57855 | 48589.6988 | 0.98483 | 73393.6224 | 0.98483 | 150915.3911 | 0.98483 | 59245.8291 | 1490496.41
0.044909 | 936705.3366 | 0.5688 | 48513.7173 | 0.4785 | 55853.1546 | 0.4785 | 130349.731 | 0.4785 | 55577.7412 | 1226999.6807
0.097141 | 953983.6525 | 0.37116 | 47003.343 | 0.5546 | 57456.9363 | 0.5546 | 132674.1965 | 0.5546 | 55913.1263 | 1247031.2547
0.34698 | 1002057.3196 | 0.18296 | 45155.3849 | 0.56533 | 57693.8336 | 0.56533 | 132988.8396 | 0.56533 | 55962.6666 | 1293858.0443
0.049394 | 938494.2556 | 0.89967 | 51974.6929 | 0.37745 | 53895.1168 | 0.37745 | 126955.3981 | 0.37745 | 55168.2735 | 1226487.7369
0.047532 | 937761.851 | 0.71872 | 49799.7124 | 0.48093 | 55902.6111 | 0.48093 | 130426.9014 | 0.48093 | 55588.0836 | 1229479.1595
0.3538 | 1003094.1504 | 0.99072 | 54219.3332 | 0.1907 | 50371.5407 | 0.1907 | 119159.8494 | 0.1907 | 54390.9383 | 1281235.812
0.48803 | 1024734.1937 | 0.10569 | 44110.3047 | 0.79474 | 63733.0199 | 0.79474 | 139973.7242 | 0.79474 | 57225.59 | 1329776.8325
0.73611 | 1074168.1607 | 0.44431 | 47587.1624 | 0.82815 | 64860.8194 | 0.82815 | 141251.0779 | 0.82815 | 57461.437 | 1385328.6575
0.79128 | 1088093.7284 | 0.32655 | 46618.6854 | 0.011795 | 44082.0193 | 0.011795 | 104765.0937 | 0.011795 | 52970.2802 | 1336529.807
0.6279 | 1050580.7461 | 0.89849 | 51955.8037 | 0.15437 | 49532.0592 | 0.15437 | 117238.5375 | 0.15437 | 54201.3187 | 1323508.4651
0.1916 | 975815.7226 | 0.83301 | 51038.9882 | 0.84825 | 65592.6657 | 0.84825 | 142079.9722 | 0.84825 | 57614.4818 | 1292141.8305
0.038098 | 933807.4767 | 0.094913 | 43936.965 | 0.53931 | 57124.3101 | 0.53931 | 132220.6248 | 0.53931 | 55843.567 | 1222932.9435
0.99624 | 1184982.5651 | 0.072964 | 43550.4444 | 0.51646 | 56637.5014 | 0.51646 | 131530.8568 | 0.51646 | 55741.7649 | 1472443.1326
0.25691 | 987790.7787 | 0.68286 | 49465.7555 | 0.56943 | 57785.1538 | 0.56943 | 133108.315 | 0.56943 | 55981.7636 | 1284131.7665
0.079065 | 948702.5761 | 0.95363 | 53007.3805 | 0.52843 | 56890.9713 | 0.52843 | 131893.9461 | 0.52843 | 55794.7709 | 1246289.6449
0.37677 | 1006624.5859 | 0.85277 | 51292.9146 | 0.15192 | 49471.944 | 0.15192 | 117100.9526 | 0.15192 | 54187.7401 | 1278678.1373
0.60118 | 1045309.7957 | 0.80214 | 50670.8026 | 0.62533 | 59075.7718 | 0.62533 | 134695.2989 | 0.62533 | 56251.6595 | 1346003.3285
0.26939 | 989898.2813 | 0.2873 | 46257.7569 | 0.81771 | 64497.3314 | 0.81771 | 140839.3888 | 0.81771 | 57385.4239 | 1298878.1822
0.24429 | 985608.1103 | 0.49591 | 47970.4615 | 0.50011 | 56296.0563 | 0.50011 | 131027.683 | 0.50011 | 55670.3614 | 1276572.6725
0.87359 | 1112911.3358 | 0.40218 | 47257.3825 | 0.046557 | 46136.4087 | 0.046557 | 109466.9512 | 0.046557 | 53434.3195 | 1369206.3977
0.20331 | 978098.4926 | 0.44349 | 47580.9684 | 0.90623 | 68032.7743 | 0.90623 | 144843.6565 | 0.90623 | 58124.7608 | 1296680.6526
0.6282 | 1050642.0981 | 0.38941 | 47154.0664 | 0.91285 | 68355.2895 | 0.91285 | 145208.9396 | 0.91285 | 58192.2057 | 1369552.5993
0.7071 | 1067432.3629 | 0.38892 | 47150.064 | 0.32443 | 52931.2585 | 0.32443 | 124990.4165 | 0.32443 | 54966.373 | 1347470.4749
0.74733 | 1076872.3123 | 0.057928 | 43250.7094 | 0.82633 | 64796.7384 | 0.82633 | 141178.4993 | 0.82633 | 57448.0363 | 1383546.2956
0.46787 | 1021317.0277 | 0.50157 | 48011.348 | 0.24117 | 51414.4165 | 0.24117 | 121546.6673 | 0.24117 | 54626.4999 | 1296915.9594
0.65803 | 1056758.7179 | 0.45339 | 47656.1992 | 0.25889 | 51754.121 | 0.25889 | 122324.1449 | 0.25889 | 54703.2313 | 1333196.4143
0.067147 | 944882.1824 | 0.059756 | 43289.0693 | 0.1108 | 48381.2452 | 0.1108 | 114604.6827 | 0.1108 | 53941.3764 | 1205098.556
0.6582 | 1056792.9795 | 0.18555 | 45186.0884 | 0.0811 | 47459.3172 | 0.0811 | 112494.6767 | 0.0811 | 53733.1341 | 1315666.1958
0.26498 | 989158.569 | 0.93387 | 52581.5212 | 0.774 | 63079.068 | 0.774 | 139233.0537 | 0.774 | 57088.8346 | 1301141.0465
0.87612 | 1113787.182 | 0.48903 | 47920.5606 | 0.80723 | 64143.0715 | 0.80723 | 140438.1515 | 0.80723 | 57311.3405 | 1423600.3061
0.8317 | 1099511.6208 | 0.12142 | 44348.0849 | 0.25498 | 51680.1855 | 0.25498 | 122154.9297 | 0.25498 | 54686.531 | 1372381.3519
0.26972 | 989953.519 | 0.7746 | 50365.749 | 0.37761 | 53898.0651 | 0.37761 | 126961.0703 | 0.37761 | 55168.89 | 1276347.2934
0.5485 | 1035410.0053 | 0.14955 | 44737.7452 | 0.53142 | 56954.9339 | 0.53142 | 131984.2072 | 0.53142 | 55808.1468 | 1324895.0384
0.46746 | 1021248.0551 | 0.95681 | 53084.0053 | 0.21036 | 50792.4501 | 0.21036 | 120123.1797 | 0.21036 | 54486.012 | 1299733.7022
0.59081 | 1043310.7056 | 0.59763 | 48741.0936 | 0.56881 | 57771.1704 | 0.56881 | 133090.085 | 0.56881 | 55978.8394 | 1338891.8939
0.60155 | 1045381.4714 | 0.66058 | 49267.7577 | 0.64762 | 59617.0078 | 0.64762 | 135311.8997 | 0.64762 | 56364.8436 | 1345942.9801
0.39004 | 1008695.5411 | 0.050933 | 43097.9837 | 0.17165 | 49942.4206 | 0.17165 | 118177.7271 | 0.17165 | 54294.01 | 1274207.6825
0.92546 | 1133125.3346 | 0.50766 | 48055.3998 | 0.68093 | 60458.9549 | 0.68093 | 136265.4949 | 0.68093 | 56540.9128 | 1434446.097
0.6017 | 1045410.5646 | 0.12484 | 44397.6593 | 0.93802 | 69709.5301 | 0.93802 | 146742.762 | 0.93802 | 58475.4064 | 1364735.9224
0.82154 | 1096522.9023 | 0.47578 | 47823.4793 | 0.64753 | 59614.8527 | 0.64753 | 135309.4588 | 0.64753 | 56364.3929 | 1395635.0861
0.6769 | 1060766.0628 | 0.0010239 | 41125.8161 | 0.35691 | 53517.0504 | 0.35691 | 126211.7043 | 0.35691 | 55089.2117 | 1336709.8452
0.91347 | 1127944.6734 | 0.64541 | 49136.7134 | 0.075888 | 47280.993 | 0.075888 | 112086.5481 | 0.075888 | 53692.8547 | 1390141.7827
0.57032 | 1039436.7079 | 0.65404 | 49210.8839 | 0.11714 | 48561.1796 | 0.11714 | 115016.4966 | 0.11714 | 53982.0194 | 1306207.2875
0.63369 | 1051747.6393 | 0.1925 | 45267.5171 | 0.087351 | 47665.8037 | 0.087351 | 112967.2601 | 0.087351 | 53779.7746 | 1311427.9949
0.97829 | 1163905.4105 | 0.22791 | 45661.0396 | 0.010823 | 43994.39 | 0.010823 | 104564.5375 | 0.010823 | 52950.4868 | 1411075.8644
0.84782 | 1104443.657 | 0.022618 | 42331.3354 | 0.67476 | 60299.7955 | 0.67476 | 136085.2299 | 0.67476 | 56507.6291 | 1399667.647
0.88303 | 1116225.208 | 0.44791 | 47614.6588 | 0.70861 | 61192.9209 | 0.70861 | 137096.79 | 0.70861 | 56694.4008 | 1418823.9785
0.83739 | 1101223.23 | 0.83556 | 51070.9121 | 0.98478 | 73386.8579 | 0.98478 | 150907.7297 | 0.98478 | 59244.4145 | 1435833.1441
0.15543 | 968286.1447 | 0.92962 | 52498.703 | 0.33593 | 53136.977 | 0.33593 | 125429.4441 | 0.33593 | 55009.7302 | 1254360.999
0.73652 | 1074265.9231 | 0.47349 | 47806.5439 | 0.87727 | 66741.2144 | 0.87727 | 143380.8267 | 0.87727 | 57854.6679 | 1390049.176
0.97534 | 1161530.5834 | 0.14326 | 44653.9283 | 0.13065 | 48929.2644 | 0.13065 | 115858.928 | 0.13065 | 54065.1613 | 1425037.8654
0.31248 | 996820.9296 | 0.87691 | 51627.6134 | 0.79237 | 63656.7175 | 0.79237 | 139887.3035 | 0.79237 | 57209.6335 | 1309202.1974
0.79847 | 1090037.6066 | 0.15492 | 44807.7365 | 0.42452 | 54785.7026 | 0.42452 | 128586.692 | 0.42452 | 55354.514 | 1373572.2517
0.85925 | 1108104.7935 | 0.45904 | 47698.8179 | 0.90574 | 68009.6931 | 0.90574 | 144817.5146 | 0.90574 | 58119.934 | 1426750.7531
0.45156 | 1018597.9894 | 0.78171 | 50442.6872 | 0.79854 | 63856.5934 | 0.79854 | 140113.6844 | 0.79854 | 57251.4318 | 1330262.3863
0.43345 | 1015628.1676 | 0.90699 | 52094.5558 | 0.23195 | 51232.6123 | 0.23195 | 121130.574 | 0.23195 | 54585.4346 | 1294671.3443
0.27796 | 991317.4188 | 0.85534 | 51327.1877 | 0.85453 | 65831.2176 | 0.85453 | 142350.1579 | 0.85453 | 57664.3681 | 1308490.3501
0.29237 | 993654.4438 | 0.75682 | 50178.7866 | 0.3171 | 52801.0337 | 0.3171 | 124706.4823 | 0.3171 | 54938.3508 | 1276279.0972
0.14078 | 964987.0047 | 0.36558 | 46956.5842 | 0.12025 | 48647.7468 | 0.12025 | 115214.6218 | 0.12025 | 54001.5729 | 1229807.5304
0.22743 | 982601.479 | 0.024229 | 42384.9584 | 0.64677 | 59596.2445 | 0.64677 | 135288.383 | 0.64677 | 56360.5015 | 1276231.5664
0.40858 | 1011624.2133 | 0.654 | 49210.5492 | 0.35427 | 53468.93 | 0.35427 | 126114.6459 | 0.35427 | 55079.1487 | 1295497.487
0.38975 | 1008649.7941 | 0.077227 | 43629.6503 | 0.53553 | 57042.9229 | 0.53553 | 132107.491 | 0.53553 | 55826.5472 | 1297256.4055
0.32158 | 998221.6268 | 0.9406 | 52718.2843 | 0.93745 | 69676.396 | 0.93745 | 146705.2342 | 0.93745 | 58468.4774 | 1325790.0186
0.015223 | 921370.3896 | 0.4177 | 47380.8474 | 0.044626 | 46049.6832 | 0.044626 | 109268.4635 | 0.044626 | 53414.7302 | 1177484.1139
0.35443 | 1003190.6269 | 0.75652 | 50175.6373 | 0.028895 | 45258.6496 | 0.028895 | 107458.034 | 0.028895 | 53236.0539 | 1259319.0017
0.54312 | 1034432.2684 | 0.75142 | 50123.3124 | 0.62031 | 58955.9492 | 0.62031 | 134555.5883 | 0.62031 | 56226.602 | 1334293.7205
0.10574 | 956322.1456 | 0.67177 | 49366.3572 | 0.30988 | 52673.5276 | 0.30988 | 124423.768 | 0.30988 | 54910.4489 | 1237696.2474
0.90187 | 1123267.4817 | 0.061259 | 43320.1936 | 0.085564 | 47607.5766 | 0.085564 | 112833.9964 | 0.085564 | 53766.6224 | 1380795.8707
0.40643 | 1011282.3522 | 0.45285 | 47652.1512 | 0.010603 | 43973.9773 | 0.010603 | 104517.8192 | 0.010603 | 52945.876 | 1260372.1759
0.50578 | 1027799.7403 | 0.90158 | 52005.5294 | 0.79953 | 63888.9171 | 0.79953 | 140150.2944 | 0.79953 | 57258.1914 | 1341102.6726
0.45794 | 1019657.7568 | 0.48592 | 47897.9203 | 0.63259 | 59250.3286 | 0.63259 | 134896.1749 | 0.63259 | 56288.1631 | 1317990.3436
0.83289 | 1099865.894 | 0.36999 | 46993.5824 | 0.71892 | 61475.0184 | 0.71892 | 137416.2957 | 0.71892 | 56753.3934 | 1402504.184
0.41183 | 1012143.2103 | 0.64108 | 49099.7448 | 0.70755 | 61164.0248 | 0.70755 | 137064.0621 | 0.70755 | 56688.358 | 1316159.4
0.27989 | 991634.2345 | 0.14633 | 44695.0377 | 0.032393 | 45450.2751 | 0.032393 | 107896.6051 | 0.032393 | 53279.3377 | 1242955.49
0.29138 | 993495.5235 | 0.015267 | 42058.1269 | 0.37168 | 53788.1924 | 0.37168 | 126748.381 | 0.37168 | 55145.9133 | 1271236.137
0.0090859 | 916509.9436 | 0.056727 | 43225.1791 | 0.33598 | 53138.0432 | 0.33598 | 125431.6899 | 0.33598 | 55009.9531 | 1193314.8089
0.9562 | 1148735.3229 | 0.61794 | 48906.185 | 0.7212 | 61538.1409 | 0.7212 | 137487.7886 | 0.7212 | 56766.5937 | 1453434.0311
0.32847 | 999267.9578 | 0.76179 | 50230.2802 | 0.17238 | 49959.2565 | 0.17238 | 118216.2591 | 0.17238 | 54297.8128 | 1271971.5664
0.031239 | 930613.2588 | 0.68519 | 49486.8887 | 0.65822 | 59880.5489 | 0.65822 | 135610.3882 | 0.65822 | 56419.9557 | 1232011.0402
0.69632 | 1065015.1321 | 0.92776 | 52463.1487 | 0.84529 | 65481.8744 | 0.84529 | 141954.4892 | 0.84529 | 57591.3129 | 1382505.9574
0.019394 | 924121.0935 | 0.99687 | 54630.4648 | 0.0052646 | 43390.9539 | 0.0052646 | 103183.4603 | 0.0052646 | 52814.1845 | 1178140.1571
0.31304 | 996908.7146 | 0.63959 | 49087.1588 | 0.98317 | 73200.5932 | 0.98317 | 150696.7649 | 0.98317 | 59205.4626 | 1329098.694
0.26268 | 988772.368 | 0.85614 | 51337.9411 | 0.92968 | 69234.6703 | 0.92968 | 146204.9325 | 0.92968 | 58376.103 | 1313926.0149
0.85131 | 1105547.0973 | 0.80331 | 50684.216 | 0.4186 | 54671.7209 | 0.4186 | 128386.6435 | 0.4186 | 55330.678 | 1394620.3558
0.21731 | 980742.55 | 0.97166 | 53485.9631 | 0.57893 | 57998.2607 | 0.57893 | 133383.2811 | 0.57893 | 56026.3288 | 1281636.3836
0.32948 | 999420.961 | 0.15995 | 44872.3303 | 0.4183 | 54665.9512 | 0.4183 | 128376.4523 | 0.4183 | 55329.4715 | 1282665.1663
0.65194 | 1055488.6305 | 0.75702 | 50180.8355 | 0.8848 | 67060.8867 | 0.8848 | 143742.8898 | 0.8848 | 57921.5183 | 1374394.7608
0.89787 | 1121721.0711 | 0.10896 | 44161.1206 | 0.53753 | 57086.038 | 0.53753 | 132167.5311 | 0.53753 | 55835.5635 | 1410971.3243
0.60567 | 1046182.7397 | 0.34193 | 46754.1312 | 0.56684 | 57727.3489 | 0.56684 | 133032.8041 | 0.56684 | 55969.6754 | 1339666.6992
0.74214 | 1075616.0253 | 0.08417 | 43754.0978 | 0.70692 | 61146.9761 | 0.70692 | 137044.7526 | 0.70692 | 56684.7927 | 1374246.6446
0.24314 | 985405.2451 | 0.54261 | 48313.652 | 0.91556 | 68490.677 | 0.91556 | 145362.2804 | 0.91556 | 58220.5181 | 1305792.3725
0.26145 | 988563.1949 | 0.13259 | 44507.6741 | 0.35075 | 53404.8098 | 0.35075 | 125984.442 | 0.35075 | 55065.7398 | 1267525.8606
0.79095 | 1088005.2559 | 0.46113 | 47714.4583 | 0.13997 | 49171.9868 | 0.13997 | 116414.444 | 0.13997 | 54119.9867 | 1355426.1317
0.45461 | 1019104.0011 | 0.67604 | 49404.466 | 0.65404 | 59776.0951 | 0.65404 | 135492.0831 | 0.65404 | 56398.1121 | 1320174.7574
0.67903 | 1061227.1145 | 0.12835 | 44447.8954 | 0.0072381 | 43630.9532 | 0.0072381 | 103732.744 | 0.0072381 | 52868.3948 | 1305907.1019
0.65849 | 1056854.983 | 0.54034 | 48296.5196 | 0.49636 | 56218.4793 | 0.49636 | 130911.0389 | 0.49636 | 55654.1384 | 1347935.1591
0.57113 | 1039588.1176 | 0.66204 | 49280.5509 | 0.75451 | 62491.1205 | 0.75451 | 138567.1402 | 0.75451 | 56965.8822 | 1346892.8114
0.51872 | 1030068.3308 | 0.0863 | 43791.2596 | 0.62775 | 59133.7798 | 0.62775 | 134762.4003 | 0.62775 | 56263.7902 | 1324019.5608
0.52644 | 1031437.5217 | 0.72668 | 49876.6314 | 0.81591 | 64435.9618 | 0.81591 | 140769.8812 | 0.81591 | 57372.5902 | 1343892.5863
0.59056 | 1043263.6027 | 0.49229 | 47944.2667 | 0.63175 | 59229.9636 | 0.63175 | 134872.9 | 0.63175 | 56283.9043 | 1341594.6373
0.68303 | 1062093.1206 | 0.33014 | 46650.5447 | 0.10387 | 48178.339 | 0.10387 | 114140.2937 | 0.10387 | 53895.5445 | 1324957.8426
0.30737 | 996026.2025 | 0.5551 | 48408.2777 | 0.87955 | 66837.2232 | 0.87955 | 143489.5669 | 0.87955 | 57874.7454 | 1312636.0157
0.41661 | 1012907.4685 | 0.15871 | 44856.5438 | 0.24091 | 51409.3276 | 0.24091 | 121535.0202 | 0.24091 | 54625.3505 | 1285333.7105
0.3251 | 998757.6264 | 0.20211 | 45377.6585 | 0.5936 | 58332.2135 | 0.5936 | 133803.6081 | 0.5936 | 56096.1655 | 1292367.2721
0.39413 | 1009336.7359 | 0.44124 | 47563.7432 | 0.39637 | 54248.8376 | 0.39637 | 127622.5681 | 0.39637 | 55242.2441 | 1294014.129
0.12879 | 962158.2535 | 0.50169 | 48012.2049 | 0.64232 | 59486.7711 | 0.64232 | 135164.3927 | 0.64232 | 56337.6083 | 1261159.2305
0.75126 | 1077834.8787 | 0.16172 | 44894.7666 | 0.33155 | 53058.4862 | 0.33155 | 125263.2794 | 0.33155 | 54993.3026 | 1356044.7136
0.53095 | 1032240.5269 | 0.62228 | 48942.0737 | 0.12927 | 48892.5858 | 0.12927 | 115774.9821 | 0.12927 | 54056.8764 | 1299907.045
0.8821 | 1115894.2952 | 0.20939 | 45459.3236 | 0.27034 | 51967.3827 | 0.27034 | 122812.2345 | 0.27034 | 54751.4023 | 1390884.6381
0.12068 | 960169.9644 | 0.23438 | 45729.5103 | 0.73949 | 62053.7924 | 0.73949 | 138071.8192 | 0.73949 | 56874.4275 | 1262899.5138
0.66794 | 1058848.6905 | 0.453 | 47653.2468 | 0.02634 | 45111.2826 | 0.02634 | 107120.7569 | 0.02634 | 53202.7671 | 1311936.744
0.50836 | 1028248.3933 | 0.040264 | 42843.1856 | 0.60397 | 58571.859 | 0.60397 | 134097.5186 | 0.60397 | 56146.2805 | 1319907.237
0.7803 | 1085187.1637 | 0.78558 | 50485.0496 | 0.26888 | 51940.4229 | 0.26888 | 122750.5319 | 0.26888 | 54745.3127 | 1365108.4808
0.27071 | 990117.6463 | 0.36474 | 46949.5145 | 0.28504 | 52234.916 | 0.28504 | 123424.535 | 0.28504 | 54811.8319 | 1267538.4437
0.63259 | 1051525.7464 | 0.49415 | 47957.7264 | 0.28346 | 52206.3993 | 0.28346 | 123359.269 | 0.28346 | 54805.3906 | 1329854.5316
0.78122 | 1085427.6311 | 0.856 | 51336.0392 | 0.58554 | 58147.9394 | 0.58554 | 133573.2459 | 0.58554 | 56057.6299 | 1384542.4853
0.19604 | 976689.3621 | 0.70917 | 49708.8067 | 0.79949 | 63887.4349 | 0.79949 | 140148.6157 | 0.79949 | 57257.8814 | 1287692.1009
0.73666 | 1074299.7419 | 0.18285 | 45154.0935 | 0.62743 | 59126.1175 | 0.62743 | 134753.5567 | 0.62743 | 56262.1879 | 1369595.6975
0.17568 | 972597.4535 | 0.1238 | 44382.7145 | 0.24277 | 51445.4383 | 0.24277 | 121617.6665 | 0.24277 | 54633.507 | 1244676.7798
0.76428 | 1081075.291 | 0.45817 | 47692.2746 | 0.5238 | 56792.5064 | 0.5238 | 131753.9303 | 0.5238 | 55774.1798 | 1373088.182
0.18695 | 974889.45 | 0.25689 | 45960.8102 | 0.37426 | 53836.0505 | 0.37426 | 126841.3551 | 0.37426 | 55155.9214 | 1256683.5872
0.79655 | 1089515.0432 | 0.60998 | 48840.9992 | 0.78177 | 63320.229 | 0.78177 | 139506.1943 | 0.78177 | 57139.2665 | 1398321.7323
0.83148 | 1099444.0556 | 0.80489 | 50702.3149 | 0.37879 | 53920.0212 | 0.37879 | 127003.2514 | 0.37879 | 55173.4815 | 1386243.1245
0.48581 | 1024353.693 | 0.2398 | 45786.2774 | 0.28478 | 52230.1922 | 0.28478 | 123413.7237 | 0.28478 | 54810.7649 | 1300594.6512
0.80024 | 1090520.5485 | 0.023368 | 42356.5342 | 0.84531 | 65482.7904 | 0.84531 | 141955.5267 | 0.84531 | 57591.5045 | 1397906.9044
0.73992 | 1075081.4564 | 0.75328 | 50142.3775 | 0.83683 | 65171.2592 | 0.83683 | 141602.6842 | 0.83683 | 57526.3566 | 1389524.1339
0.061362 | 942905.3436 | 0.28442 | 46230.3649 | 0.39074 | 54143.0792 | 0.39074 | 127425.8663 | 0.39074 | 55220.1277 | 1225924.7817
0.40933 | 1011743.6771 | 0.36002 | 46909.59 | 0.43595 | 55007.3904 | 0.43595 | 128968.936 | 0.43595 | 55400.8737 | 1298030.4673
0.85239 | 1105889.1307 | 0.13228 | 44503.3516 | 0.74914 | 62333.2103 | 0.74914 | 138388.2899 | 0.74914 | 56932.8598 | 1408046.8422
0.87258 | 1112561.7686 | 0.56222 | 48462.8858 | 0.46825 | 55646.3816 | 0.46825 | 130022.96 | 0.46825 | 55534.5005 | 1402228.4965
0.026443 | 928165.541 | 0.018254 | 42175.7089 | 0.15223 | 49479.5441 | 0.15223 | 117118.3468 | 0.15223 | 54189.4568 | 1191128.5975
0.11575 | 958926.9844 | 0.72925 | 49901.7305 | 0.79363 | 63697.4045 | 0.79363 | 139933.386 | 0.79363 | 57218.142 | 1269677.6474
0.31975 | 997940.6892 | 0.1942 | 45287.1153 | 0.4247 | 54789.159 | 0.4247 | 128592.7205 | 0.4247 | 55355.2368 | 1281964.9208
0.89269 | 1119758.6478 | 0.16329 | 44914.5778 | 0.32452 | 52933.0094 | 0.32452 | 124994.2018 | 0.32452 | 54966.7466 | 1397567.1835
0.37919 | 1007000.6477 | 0.24919 | 45882.94 | 0.89529 | 67524.1623 | 0.89529 | 144267.599 | 0.89529 | 58018.3991 | 1322693.7482
0.17951 | 973385.07 | 0.69129 | 49542.5309 | 0.22999 | 51193.5254 | 0.22999 | 121041.1163 | 0.22999 | 54576.6057 | 1249738.8483
0.73334 | 1073511.1211 | 0.13361 | 44521.9114 | 0.96813 | 71772.7181 | 0.96813 | 149079.5434 | 0.96813 | 58906.8633 | 1397792.1574
0.18771 | 975042.9604 | 0.66306 | 49289.4637 | 0.24358 | 51461.276 | 0.24358 | 121653.914 | 0.24358 | 54637.0844 | 1252084.6986
0.22389 | 981956.3281 | 0.36692 | 46967.8127 | 0.77658 | 63158.7792 | 0.77658 | 139323.3351 | 0.77658 | 57105.5039 | 1288511.7591
0.46197 | 1020328.3208 | 0.66204 | 49280.5786 | 0.77631 | 63150.2221 | 0.77631 | 139313.6433 | 0.77631 | 57103.7144 | 1329176.4793
0.97547 | 1161633.757 | 0.16942 | 44991.061 | 0.86135 | 66096.3514 | 0.86135 | 142650.4502 | 0.86135 | 57719.8133 | 1473091.4329
0.12016 | 960039.0624 | 0.80117 | 50659.7002 | 0.46722 | 55625.8368 | 0.46722 | 129990.123 | 0.46722 | 55530.2041 | 1251844.9266
0.22942 | 982962.2165 | 0.63114 | 49015.9111 | 0.53072 | 56939.915 | 0.53072 | 131963.0618 | 0.53072 | 55805.006 | 1276686.1104
0.94596 | 1143056.9053 | 0.90179 | 52009.0524 | 0.53065 | 56938.5069 | 0.53065 | 131961.0779 | 0.53065 | 55804.7116 | 1439770.2541
0.56212 | 1037911.0591 | 0.043958 | 42934.8438 | 0.55521 | 57470.3082 | 0.55521 | 132692.1401 | 0.55521 | 55915.9226 | 1326924.2738
0.16466 | 970283.3988 | 0.7338 | 49946.4603 | 0.61735 | 58885.8612 | 0.61735 | 134473.1713 | 0.61735 | 56211.9451 | 1269800.8367
0.87873 | 1114698.7458 | 0.98042 | 53775.219 | 0.3673 | 53707.5609 | 0.3673 | 126590.5656 | 0.3673 | 55129.0515 | 1403901.1428
0.89422 | 1120333.6471 | 0.89487 | 51898.5224 | 0.46899 | 55661.2871 | 0.46899 | 130046.7414 | 0.46899 | 55537.6176 | 1413477.8156
0.75256 | 1078153.0419 | 0.81646 | 50837.6867 | 0.026936 | 45146.2744 | 0.026936 | 107200.8422 | 0.026936 | 53210.6709 | 1334548.5162
0.53741 | 1033400.8388 | 0.2151 | 45522.481 | 0.82877 | 64882.5398 | 0.82877 | 141275.6785 | 0.82877 | 57465.9792 | 1342547.5173
0.60229 | 1045524.4354 | 0.83125 | 51017.1362 | 0.66008 | 59927.2419 | 0.66008 | 135663.273 | 0.66008 | 56429.7202 | 1348561.8067
0.89127 | 1119231.6242 | 0.69994 | 49622.3641 | 0.72883 | 61751.0361 | 0.72883 | 137728.9152 | 0.72883 | 56811.1146 | 1425145.0542
0.48162 | 1023639.3113 | 0.397 | 47215.663 | 0.34593 | 53317.3671 | 0.34593 | 125805.2435 | 0.34593 | 55047.4536 | 1305025.0385
0.24567 | 985849.8543 | 0.53819 | 48280.4467 | 0.69624 | 60860.8212 | 0.69624 | 136720.6515 | 0.69624 | 56624.9516 | 1288336.7253
0.516 | 1029588.6323 | 0.481 | 47861.8696 | 0.067635 | 46985.5758 | 0.067635 | 111410.4301 | 0.067635 | 53626.1268 | 1289472.6346
0.85095 | 1105431.146 | 0.88296 | 51716.44 | 0.98747 | 73722.7668 | 0.98747 | 151288.1824 | 0.98747 | 59314.6603 | 1441473.1956
0.46672 | 1021123.1099 | 0.71989 | 49810.9116 | 0.23856 | 51363.1742 | 0.23856 | 121429.3896 | 0.23856 | 54614.9255 | 1298341.5108
0.91029 | 1126633.7655 | 0.67434 | 49389.248 | 0.27618 | 52074.5636 | 0.27618 | 123057.5382 | 0.27618 | 54775.6119 | 1405930.7272
0.11031 | 957527.699 | 0.32744 | 46626.5341 | 0.10883 | 48324.1274 | 0.10883 | 114473.9579 | 0.10883 | 53928.4748 | 1220880.7932
0.69159 | 1063967.6728 | 0.46679 | 47756.7597 | 0.18756 | 50302.3755 | 0.18756 | 119001.5516 | 0.18756 | 54375.3155 | 1335403.6751
0.3235 | 998514.2671 | 0.36003 | 46909.6988 | 0.46095 | 55500.2812 | 0.46095 | 129787.9684 | 0.46095 | 55503.9477 | 1286216.1632
0.83165 | 1099497.5223 | 0.20501 | 45410.3536 | 0.21639 | 50917.5406 | 0.21639 | 120409.473 | 0.21639 | 54514.2671 | 1370749.1566
0.12358 | 960887.9079 | 0.1106 | 44186.3366 | 0.02888 | 45257.832 | 0.02888 | 107456.1629 | 0.02888 | 53235.8692 | 1211024.1086
0.6098 | 1046989.7124 | 0.29441 | 46324.8769 | 0.52805 | 56882.9569 | 0.52805 | 131882.5982 | 0.52805 | 55793.0949 | 1337873.2392
0.70228 | 1066347.664 | 0.3997 | 47237.4228 | 0.43307 | 54951.3725 | 0.43307 | 128873.1861 | 0.43307 | 55389.1592 | 1352798.8045
0.92466 | 1132766.3973 | 0.63828 | 49076.0076 | 0.043798 | 46011.9414 | 0.043798 | 109182.0842 | 0.043798 | 53406.2052 | 1390442.6357
0.052478 | 939677.865 | 0.63881 | 49080.5193 | 0.0039389 | 43203.1469 | 0.0039389 | 102753.6285 | 0.0039389 | 52771.7632 | 1187486.9229
0.94201 | 1141011.5263 | 0.84849 | 51236.6021 | 0.4692 | 55665.4338 | 0.4692 | 130053.351 | 0.4692 | 55538.4847 | 1433505.398
0.55424 | 1036459.2607 | 0.39209 | 47175.8806 | 0.58307 | 58091.8867 | 0.58307 | 133502.4086 | 0.58307 | 56045.908 | 1331275.3448
0.7444 | 1076160.3767 | 0.50151 | 48010.9056 | 0.32049 | 52861.2103 | 0.32049 | 124838.2816 | 0.32049 | 54951.3584 | 1356822.1327
0.55166 | 1035986.8556 | 0.065621 | 43408.3726 | 0.032882 | 45476.2391 | 0.032882 | 107956.0286 | 0.032882 | 53285.2024 | 1286112.6983
0.072604 | 946670.2252 | 0.67682 | 49411.4569 | 0.016936 | 44494.7978 | 0.016936 | 105709.8152 | 0.016936 | 53063.5174 | 1199349.8125
0.88811 | 1118063.7549 | 0.15802 | 44847.6737 | 0.63854 | 59394.5221 | 0.63854 | 135059.9108 | 0.63854 | 56318.317 | 1413684.1785
0.06361 | 943684.2559 | 0.563 | 48468.8554 | 0.71513 | 61370.8027 | 0.71513 | 137298.2603 | 0.71513 | 56731.5997 | 1247553.774
0.58357 | 1041931.5651 | 0.77509 | 50371.0731 | 0.69456 | 60816.1698 | 0.69456 | 136670.0791 | 0.69456 | 56615.6141 | 1346404.5012
0.71025 | 1068146.9708 | 0.78975 | 50531.1399 | 0.66308 | 60002.7476 | 0.66308 | 135748.7914 | 0.66308 | 56445.51 | 1370875.1598
0.36983 | 1005551.2091 | 0.43419 | 47509.4763 | 0.094199 | 47883.7332 | 0.094199 | 113466.0327 | 0.094199 | 53828.9999 | 1268239.4511
0.28205 | 991985.5971 | 0.7542 | 50151.8048 | 0.35268 | 53439.871 | 0.35268 | 126055.7626 | 0.35268 | 55073.0718 | 1276706.1073
0.13657 | 964009.3573 | 0.62762 | 48986.4071 | 0.73102 | 61812.7359 | 0.73102 | 137798.797 | 0.73102 | 56824.0174 | 1269431.3147
0.67181 | 1059674.2629 | 0.32644 | 46617.693 | 0.95893 | 71065.3293 | 0.95893 | 148278.3498 | 0.95893 | 58758.9331 | 1384394.568
0.86538 | 1110128.412 | 0.7721 | 50339.0569 | 0.20104 | 50595.4099 | 0.20104 | 119672.2161 | 0.20104 | 54441.5052 | 1385176.6
0.10102 | 955052.0076 | 0.31757 | 46538.1011 | 0.0062862 | 43519.9304 | 0.0062862 | 103478.6472 | 0.0062862 | 52843.3173 | 1201432.0037
0.48436 | 1024106.8483 | 0.76141 | 50226.3213 | 0.73055 | 61799.5574 | 0.73055 | 137783.8709 | 0.73055 | 56821.2615 | 1330737.8594
0.38248 | 1007512.4327 | 0.93678 | 52639.739 | 0.046967 | 46154.5667 | 0.046967 | 109508.5092 | 0.046967 | 53438.421 | 1269253.6686
0.15121 | 967351.1416 | 0.00084354 | 41095.7325 | 0.13979 | 49167.5276 | 0.13979 | 116404.2382 | 0.13979 | 54118.9795 | 1228137.6194
0.67512 | 1060382.9465 | 0.39809 | 47224.4969 | 0.74739 | 62282.2392 | 0.74739 | 138330.5597 | 0.74739 | 56922.2006 | 1365142.4428
0.35805 | 1003743.0817 | 0.092403 | 43895.2082 | 0.64893 | 59649.4106 | 0.64893 | 135348.5993 | 0.64893 | 56371.6197 | 1299007.9194
0.32972 | 999456.6513 | 0.92883 | 52483.6163 | 0.35516 | 53485.1673 | 0.35516 | 126147.4589 | 0.35516 | 55082.5442 | 1286655.438
0.56951 | 1039285.6417 | 0.72644 | 49874.3003 | 0.045034 | 46068.1874 | 0.045034 | 109310.8138 | 0.045034 | 53418.9099 | 1297957.8531
0.37804 | 1006823.0515 | 0.62376 | 48954.2894 | 0.72972 | 61776.2266 | 0.72972 | 137757.4462 | 0.72972 | 56816.3825 | 1312127.3961
0.025442 | 927627.3825 | 0.014049 | 42006.9068 | 0.019466 | 44674.6166 | 0.019466 | 106121.3643 | 0.019466 | 53104.1343 | 1173534.4044
0.64013 | 1053057.1299 | 0.31031 | 46472.148 | 0.86048 | 66061.9729 | 0.86048 | 142611.5129 | 0.86048 | 57712.624 | 1365915.3876
0.38376 | 1007712.7558 | 0.58995 | 48679.7367 | 0.082797 | 47516.147 | 0.082797 | 112624.7424 | 0.082797 | 53745.9706 | 1270279.3525
0.87332 | 1112816.1056 | 0.93093 | 52524.0111 | 0.70068 | 60979.0935 | 0.70068 | 136854.6076 | 0.70068 | 56649.6849 | 1419823.5026
0.73104 | 1072965.6049 | 0.44123 | 47563.5985 | 0.83634 | 65153.5086 | 0.83634 | 141582.5797 | 0.83634 | 57522.6446 | 1384787.9363
0.29008 | 993286.9106 | 0.22055 | 45581.8735 | 0.79273 | 63668.2017 | 0.79273 | 139900.3107 | 0.79273 | 57212.0351 | 1299649.3317
0.072245 | 946554.7852 | 0.36062 | 46914.6365 | 0.56973 | 57791.8681 | 0.56973 | 133117.0601 | 0.56973 | 55983.1677 | 1240361.5177
0.10279 | 955532.4028 | 0.75401 | 50149.8764 | 0.49437 | 56177.4718 | 0.49437 | 130849.025 | 0.49437 | 55645.5628 | 1248354.3388
0.1629 | 969907.0253 | 0.15507 | 44809.7447 | 0.35038 | 53398.0261 | 0.35038 | 125970.6079 | 0.35038 | 55064.3211 | 1249149.7252
0.77329 | 1083369.5328 | 0.59913 | 48753.1074 | 0.40138 | 54343.4386 | 0.40138 | 127796.5733 | 0.40138 | 55262.0272 | 1369524.6793
0.61008 | 1047044.2897 | 0.26658 | 46057.327 | 0.43991 | 55084.69 | 0.43991 | 129100.1474 | 0.43991 | 55417.0387 | 1332703.4928
0.10212 | 955348.9164 | 0.86979 | 51525.7722 | 0.97201 | 72100.6607 | 0.97201 | 149450.9736 | 0.97201 | 58975.4431 | 1287401.766
0.072564 | 946657.3253 | 0.22628 | 45643.6777 | 0.58044 | 58032.2345 | 0.58044 | 133426.6257 | 0.58044 | 56033.4335 | 1239793.2965
0.5761 | 1040519.9413 | 0.62116 | 48932.7512 | 0.76391 | 62771.4703 | 0.76391 | 138884.6663 | 0.76391 | 57024.5093 | 1348133.3385
0.3266 | 998984.1296 | 0.36448 | 46947.2863 | 0.66957 | 60167.1278 | 0.66957 | 135934.9695 | 0.66957 | 56479.8854 | 1298513.3985
0.99615 | 1184800.589 | 0.30644 | 46436.6563 | 0.76532 | 62814.1329 | 0.76532 | 138932.9863 | 0.76532 | 57033.431 | 1490017.7954
0.44688 | 1017825.8281 | 0.99154 | 54263.6308 | 0.55125 | 57383.6135 | 0.55125 | 132575.4107 | 0.55125 | 55897.7929 | 1317946.276
0.37776 | 1006778.1216 | 0.080536 | 43689.6382 | 0.25141 | 51612.142 | 0.25141 | 121999.1991 | 0.25141 | 54671.1616 | 1278750.2624
0.57539 | 1040385.9643 | 0.44259 | 47574.0269 | 0.45034 | 55289.8753 | 0.45034 | 129443.392 | 0.45034 | 55459.9474 | 1328153.2059
0.70534 | 1067035.9356 | 0.86451 | 51452.0057 | 0.56508 | 57688.1896 | 0.56508 | 132981.4227 | 0.56508 | 55961.4863 | 1365119.0399
0.96271 | 1152700.6853 | 0.33453 | 46689.3547 | 0.013907 | 44260.7116 | 0.013907 | 105174.0648 | 0.013907 | 53010.6427 | 1401835.4591
0.11695 | 959232.9575 | 0.11607 | 44268.9519 | 0.7358 | 61948.3619 | 0.7358 | 137952.4079 | 0.7358 | 56852.3797 | 1260255.0589
0.45834 | 1019724.1862 | 0.43843 | 47542.131 | 0.71802 | 61450.2026 | 0.71802 | 137388.1892 | 0.71802 | 56748.2039 | 1322852.9129
0.99373 | 1180603.1624 | 0.40658 | 47292.6618 | 0.52094 | 56731.9848 | 0.52094 | 131667.2211 | 0.52094 | 55761.5234 | 1472056.5536
0.34624 | 1001946.0355 | 0.62472 | 48962.2986 | 0.70852 | 61190.4385 | 0.70852 | 137093.9785 | 0.70852 | 56693.8817 | 1305886.6327
0.01659 | 922308.8909 | 0.3503 | 46826.533 | 0.62198 | 58995.7039 | 0.62198 | 134602.1072 | 0.62198 | 56234.9156 | 1218968.1507
0.56808 | 1039018.8018 | 0.094161 | 43924.5178 | 0.2008 | 50590.2652 | 0.2008 | 119660.4416 | 0.2008 | 54440.3431 | 1307634.3695
0.1015 | 955180.601 | 0.63734 | 49068.0456 | 0.53612 | 57055.6405 | 0.53612 | 132125.2261 | 0.53612 | 55829.2067 | 1249258.7199
0.41697 | 1012965.4541 | 0.73143 | 49923.1621 | 0.9903 | 74116.133 | 0.9903 | 151733.7118 | 0.9903 | 59396.9216 | 1348135.3826
0.039608 | 934470.7535 | 0.73806 | 49988.6867 | 0.36407 | 53648.09 | 0.36407 | 126473.2104 | 0.36407 | 55116.6148 | 1219697.3555
0.54152 | 1034141.35 | 0.098679 | 43998.6028 | 0.76515 | 62809.1478 | 0.76515 | 138927.3402 | 0.76515 | 57032.3885 | 1336908.8293
0.065346 | 944276.1871 | 0.83522 | 51066.6872 | 0.27836 | 52114.2381 | 0.27836 | 123148.3408 | 0.27836 | 54784.5735 | 1225390.0267
0.14122 | 965090.1984 | 0.5759 | 48568.9723 | 0.54048 | 57149.6371 | 0.54048 | 132255.6562 | 0.54048 | 55848.8635 | 1258913.3274
0.88117 | 1115561.9229 | 0.80161 | 50664.7399 | 0.28771 | 52282.7531 | 0.28771 | 123534.0191 | 0.28771 | 54822.6372 | 1396866.0721
0.27513 | 990851.1857 | 0.72139 | 49825.4221 | 0.37671 | 53881.3853 | 0.37671 | 126928.9549 | 0.37671 | 55165.4019 | 1276652.35
0.70826 | 1067696.4799 | 0.032957 | 42648.5071 | 0.2132 | 50851.6929 | 0.2132 | 120258.7682 | 0.2132 | 54499.3936 | 1335954.8418
0.17402 | 972252.698 | 0.50447 | 48032.2662 | 0.74244 | 62138.7509 | 0.74244 | 138168.0438 | 0.74244 | 56892.1941 | 1277483.9531
0.96958 | 1157275.6237 | 0.15356 | 44790.1348 | 0.30487 | 52585.43 | 0.30487 | 124225.6252 | 0.30487 | 54890.8937 | 1433767.7074
0.35008 | 1002528.2809 | 0.17771 | 45092.4908 | 0.037962 | 45735.1091 | 0.037962 | 108548.5013 | 0.037962 | 53343.6751 | 1255248.0572
0.77593 | 1084050.3323 | 0.72625 | 49872.4486 | 0.43786 | 55044.6968 | 0.43786 | 129032.3931 | 0.43786 | 55408.6753 | 1373408.5461
0.066616 | 944704.3549 | 0.48939 | 47923.223 | 0.60881 | 58684.7273 | 0.60881 | 134233.7661 | 0.60881 | 56169.8837 | 1241715.9551
0.75406 | 1078524.1379 | 0.47889 | 47846.3829 | 0.55256 | 57412.2212 | 0.55256 | 132614.0328 | 0.55256 | 55903.7754 | 1372300.5502
0.6877 | 1063114.1946 | 0.38396 | 47109.4346 | 0.39165 | 54160.1411 | 0.39165 | 127457.7572 | 0.39165 | 55223.6957 | 1347065.2233
0.38574 | 1008021.3156 | 0.88863 | 51801.9991 | 0.87439 | 66621.4277 | 0.87439 | 143245.1554 | 0.87439 | 57829.618 | 1327519.5158
0.76992 | 1082506.1359 | 0.37433 | 47029.8362 | 0.86181 | 66114.3078 | 0.86181 | 142670.7877 | 0.86181 | 57723.5683 | 1396044.636
0.21803 | 980876.1662 | 0.57742 | 48580.8512 | 0.058613 | 46641.131 | 0.058613 | 110622.1033 | 0.058613 | 53548.3246 | 1240268.5763
0.19786 | 977044.0547 | 0.39982 | 47238.4362 | 0.046094 | 46115.785 | 0.046094 | 109419.7499 | 0.046094 | 53429.6611 | 1233247.6868
0.99912 | 1192728.3795 | 0.11861 | 44306.7783 | 0.55375 | 57438.2167 | 0.55375 | 132649.0396 | 0.55375 | 55909.2116 | 1483031.6258
0.65155 | 1055407.2353 | 0.83946 | 51120.2183 | 0.8852 | 67078.4652 | 0.8852 | 143762.7992 | 0.8852 | 57925.1943 | 1375293.9124
0.98749 | 1172608.2786 | 0.48385 | 47882.7877 | 0.6666 | 60091.6934 | 0.6666 | 135849.532 | 0.6666 | 56464.1105 | 1472896.4022
0.37345 | 1006111.2011 | 0.38039 | 47080.0306 | 0.6381 | 59383.8638 | 0.6381 | 135047.8392 | 0.6381 | 56316.0882 | 1303939.0228
0.4814 | 1023603.3456 | 0.60021 | 48761.7964 | 0.43803 | 55048.0827 | 0.43803 | 129038.1404 | 0.43803 | 55409.3834 | 1311860.7485
0.54297 | 1034403.9421 | 0.25413 | 45933.0022 | 0.45245 | 55331.5828 | 0.45245 | 129512.2827 | 0.45245 | 55468.6693 | 1320649.4791
0.19935 | 977332.8704 | 0.5811 | 48609.7575 | 0.79692 | 63803.9073 | 0.79692 | 140054.0117 | 0.79692 | 57240.414 | 1287040.9609
0.885 | 1116935.4646 | 0.35238 | 46844.3901 | 0.11223 | 48422.2705 | 0.11223 | 114698.577 | 0.11223 | 53950.643 | 1380851.3453
0.74167 | 1075501.9938 | 0.097299 | 43976.1528 | 0.046333 | 46126.4036 | 0.046333 | 109444.0527 | 0.046333 | 53432.0596 | 1328480.6625
0.019449 | 924155.4096 | 0.60082 | 48766.761 | 0.19901 | 50552.0621 | 0.19901 | 119573.0065 | 0.19901 | 54431.7139 | 1197478.953
0.072236 | 946551.8347 | 0.28063 | 46194.067 | 0.56437 | 57672.4057 | 0.56437 | 132960.6602 | 0.56437 | 55958.1856 | 1239337.1531
0.55704 | 1036972.9283 | 0.17316 | 45037.0879 | 0.90156 | 67812.3781 | 0.90156 | 144594.0342 | 0.90156 | 58078.6712 | 1352495.0997
0.45791 | 1019652.6552 | 0.69254 | 49554.0156 | 0.94387 | 70062.1135 | 0.94387 | 147142.1005 | 0.94387 | 58549.1392 | 1344960.0241
0.054454 | 940417.9228 | 0.86349 | 51437.9352 | 0.15058 | 49438.9635 | 0.15058 | 117025.4705 | 0.15058 | 54180.2906 | 1212500.5825
0.56258 | 1037995.8733 | 0.54743 | 48350.0402 | 0.34909 | 53374.705 | 0.34909 | 125922.962 | 0.34909 | 55059.4442 | 1320703.0246
0.66103 | 1057387.8567 | 0.69949 | 49618.1779 | 0.8552 | 65856.9717 | 0.8552 | 142379.3271 | 0.8552 | 57669.7538 | 1372912.0873
0.84904 | 1104827.4245 | 0.59628 | 48730.2371 | 0.69479 | 60822.3011 | 0.69479 | 136677.0235 | 0.69479 | 56616.8962 | 1407673.8824
0.030829 | 930411.5581 | 0.32967 | 46646.4029 | 0.35622 | 53504.495 | 0.35622 | 126186.434 | 0.35622 | 55086.5861 | 1211835.476
0.56419 | 1038294.3644 | 0.61418 | 48875.3315 | 0.50977 | 56497.1076 | 0.50977 | 131325.954 | 0.50977 | 55712.4055 | 1330705.1631
0.6251 | 1050020.9506 | 0.68597 | 49493.9897 | 0.67346 | 60266.4843 | 0.67346 | 136047.5014 | 0.67346 | 56500.663 | 1352329.5889
0.008831 | 916276.7104 | 0.46543 | 47746.6082 | 0.92479 | 68969.1786 | 0.92479 | 145904.2347 | 0.92479 | 58320.583 | 1237217.3149
0.39102 | 1008849.2916 | 0.70193 | 49640.8341 | 0.45069 | 55296.7726 | 0.45069 | 129454.805 | 0.45069 | 55461.3897 | 1298703.0931
0.29501 | 994076.7257 | 0.22642 | 45645.1669 | 0.2705 | 51970.4667 | 0.2705 | 122819.293 | 0.2705 | 54752.0989 | 1269263.7512
0.36681 | 1005085.8274 | 0.42502 | 47438.2073 | 0.36599 | 53683.3466 | 0.36599 | 126542.8818 | 0.36599 | 55123.9878 | 1287874.2508
0.2326 | 983534.3262 | 0.8047 | 50700.1513 | 0.081547 | 47474.3445 | 0.081547 | 112529.0694 | 0.081547 | 53736.5284 | 1247974.4198
0.2013 | 977711.9007 | 0.031962 | 42620.3898 | 0.55685 | 57506.3965 | 0.55685 | 132740.4563 | 0.55685 | 55923.4695 | 1266502.6128
0.20605 | 978622.3252 | 0.69479 | 49574.7189 | 0.38208 | 53981.0845 | 0.38208 | 127120.0085 | 0.38208 | 55186.2511 | 1264484.3882
0.52181 | 1030614.8828 | 0.094343 | 43927.5375 | 0.34147 | 53236.7846 | 0.34147 | 125638.402 | 0.34147 | 55030.6021 | 1308448.2089
0.54019 | 1033901.2531 | 0.23894 | 45777.2447 | 0.61548 | 58841.6343 | 0.61548 | 134420.8981 | 0.61548 | 56202.6963 | 1329143.7266
0.34899 | 1002362.5631 | 0.37394 | 47026.5659 | 0.28857 | 52297.9916 | 0.28857 | 123568.8953 | 0.28857 | 54826.0792 | 1280082.0951
0.087662 | 951282.1551 | 0.77163 | 50334.0573 | 0.28017 | 52146.9909 | 0.28017 | 123223.3017 | 0.28017 | 54791.9716 | 1231778.4766
0.054743 | 940525.0909 | 0.45171 | 47643.4702 | 0.63882 | 59401.4886 | 0.63882 | 135067.8011 | 0.63882 | 56319.7739 | 1238957.6247
0.89543 | 1120790.257 | 0.66538 | 49309.9138 | 0.95688 | 70919.3828 | 0.95688 | 148113.0498 | 0.95688 | 58728.4125 | 1447861.016
0.69912 | 1065638.7995 | 0.37735 | 47054.8976 | 0.94697 | 70256.831 | 0.94697 | 147362.6389 | 0.94697 | 58589.8588 | 1388903.0258
0.30477 | 995620.2144 | 0.46741 | 47761.3722 | 0.70532 | 61103.8206 | 0.70532 | 136995.8744 | 0.70532 | 56675.768 | 1298157.0495
0.99065 | 1176319.0614 | 0.28057 | 46193.4363 | 0.79695 | 63804.8321 | 0.79695 | 140055.0592 | 0.79695 | 57240.6074 | 1483612.9965
0.95093 | 1145737.0068 | 0.83815 | 51103.6215 | 0.67433 | 60288.7971 | 0.67433 | 136072.7731 | 0.67433 | 56505.3291 | 1449707.5276
0.67509 | 1060377.0591 | 0.15579 | 44818.9571 | 0.94798 | 70321.3299 | 0.94798 | 147435.6909 | 0.94798 | 58603.3469 | 1381556.3839
0.59578 | 1044264.8699 | 0.8095 | 50755.8358 | 0.85517 | 65855.7519 | 0.85517 | 142377.9455 | 0.85517 | 57669.4987 | 1360923.9017
0.46227 | 1020377.9844 | 0.91357 | 52206.4673 | 0.17054 | 49916.669 | 0.17054 | 118118.7895 | 0.17054 | 54288.1932 | 1294908.1035
0.5547 | 1036543.1764 | 0.63988 | 49089.5476 | 0.35305 | 53446.6756 | 0.35305 | 126069.5695 | 0.35305 | 55074.4948 | 1320223.4638
0.7272 | 1072062.2201 | 0.083992 | 43750.9874 | 0.78374 | 63382.4005 | 0.78374 | 139576.6101 | 0.78374 | 57152.2679 | 1375924.4861
0.71068 | 1068245.4799 | 0.61538 | 48885.1153 | 0.29232 | 52364.7392 | 0.29232 | 123721.6599 | 0.29232 | 54841.156 | 1348058.1503
0.73407 | 1073682.8032 | 0.56217 | 48462.457 | 0.87766 | 66757.6334 | 0.87766 | 143399.423 | 0.87766 | 57858.1015 | 1390160.4181
0.12284 | 960706.5019 | 0.10131 | 44040.9298 | 0.65398 | 59774.5736 | 0.65398 | 135490.3598 | 0.65398 | 56397.794 | 1256410.1591
0.72987 | 1072690.048 | 0.94921 | 52905.2718 | 0.62558 | 59081.778 | 0.62558 | 134702.2628 | 0.62558 | 56252.9155 | 1375632.2762
0.49567 | 1026046.7919 | 0.24356 | 45825.1374 | 0.36965 | 53750.8785 | 0.36965 | 126675.5328 | 0.36965 | 55138.1101 | 1307436.4507
0.29512 | 994093.3323 | 0.2062 | 45423.7563 | 0.26705 | 51906.6631 | 0.26705 | 122673.2664 | 0.26705 | 54737.6871 | 1268834.7052
0.71927 | 1070215.1946 | 0.91667 | 52260.6804 | 0.04427 | 46033.5306 | 0.04427 | 109231.4952 | 0.04427 | 53411.0817 | 1331151.9823
0.536 | 1033146.9547 | 0.060684 | 43308.3324 | 0.54943 | 57343.936 | 0.54943 | 132521.6745 | 0.54943 | 55889.4955 | 1322210.3931
0.33543 | 1000315.3426 | 0.017234 | 42136.7218 | 0.37948 | 53932.7447 | 0.37948 | 127027.6468 | 0.37948 | 55176.1423 | 1278588.5981
0.18482 | 974463.0136 | 0.5307 | 48224.561 | 0.33083 | 53045.6501 | 0.33083 | 125235.9491 | 0.33083 | 54990.6053 | 1255959.7791
0.013948 | 920455.9242 | 0.2984 | 46362.1735 | 0.2215 | 51022.3124 | 0.2215 | 120649.2631 | 0.2215 | 54537.9326 | 1193027.6059
0.28926 | 993155.2679 | 0.82635 | 50956.8942 | 0.6259 | 59089.2487 | 0.6259 | 134710.9195 | 0.6259 | 56254.4778 | 1294166.8083
0.75711 | 1079279.28 | 0.424 | 47430.2596 | 0.90095 | 67783.8714 | 0.90095 | 144561.7473 | 0.90095 | 58072.7099 | 1397127.8681
0.614 | 1047815.2101 | 0.28877 | 46271.7045 | 0.56307 | 57643.6397 | 0.56307 | 132922.7435 | 0.56307 | 55952.17 | 1340605.4678
0.1284 | 962063.3524 | 0.57682 | 48576.1824 | 0.69509 | 60830.3864 | 0.69509 | 136686.1809 | 0.69509 | 56618.587 | 1264774.6891
0.83944 | 1101848.6639 | 0.11793 | 44296.7313 | 0.46843 | 55650.0261 | 0.46843 | 130028.7778 | 0.46843 | 55535.2626 | 1387359.4617
0.91392 | 1128133.0596 | 0.96341 | 53252.2978 | 0.13749 | 49108.391 | 0.13749 | 116268.893 | 0.13749 | 54105.6219 | 1400868.2633
0.50807 | 1028198.6629 | 0.13935 | 44601.0184 | 0.18169 | 50171.3177 | 0.18169 | 118701.6011 | 0.18169 | 54345.7125 | 1296018.3126
0.50011 | 1026813.8555 | 0.8378 | 51099.1462 | 0.37553 | 53859.4511 | 0.37553 | 126886.6288 | 0.37553 | 55160.815 | 1313819.8966
0.63893 | 1052813.1805 | 0.96551 | 53308.9196 | 0.63715 | 59360.79 | 0.63715 | 135021.7056 | 0.63715 | 56311.2629 | 1356815.8586
0.9052 | 1124582.0525 | 0.24553 | 45845.4967 | 0.66323 | 60006.4462 | 0.66323 | 135752.9804 | 0.66323 | 56446.2835 | 1422633.2593
0.71766 | 1069844.5856 | 0.26455 | 46037.2317 | 0.18786 | 50308.899 | 0.18786 | 119016.4818 | 0.18786 | 54376.789 | 1339583.987
0.09425 | 953174.2854 | 0.67064 | 49356.3282 | 0.3418 | 53242.7793 | 0.3418 | 125650.8707 | 0.3418 | 55031.8557 | 1236456.1194
0.48369 | 1023991.8624 | 0.26316 | 46023.4952 | 0.74339 | 62166.1359 | 0.74339 | 138199.0603 | 0.74339 | 56897.9209 | 1327278.4747
0.18403 | 974303.522 | 0.29508 | 46331.2008 | 0.39822 | 54283.759 | 0.39822 | 127687.0129 | 0.39822 | 55249.5469 | 1257855.0416
0.98574 | 1170754.4598 | 0.11494 | 44252.0543 | 0.90702 | 68070.922 | 0.90702 | 144886.8629 | 0.90702 | 58132.7383 | 1486097.0373
0.61627 | 1048264.3482 | 0.067217 | 43439.8956 | 0.044214 | 46030.954 | 0.044214 | 109225.5982 | 0.044214 | 53410.4997 | 1300371.2957
0.19303 | 976098.5763 | 0.51538 | 48111.5823 | 0.43737 | 55035.1071 | 0.43737 | 129016.1048 | 0.43737 | 55406.6699 | 1263668.0404
0.70671 | 1067344.4027 | 0.21957 | 45571.2815 | 0.59706 | 58411.7651 | 0.59706 | 133901.8775 | 0.59706 | 56112.8015 | 1361342.1283
0.023069 | 926307.4924 | 0.13237 | 44504.5677 | 0.35417 | 53467.0673 | 0.35417 | 126110.8777 | 0.35417 | 55078.7591 | 1205468.7642
0.049799 | 938651.8459 | 0.58804 | 48664.5752 | 0.64758 | 59616.0396 | 0.64758 | 135310.8031 | 0.64758 | 56364.6411 | 1238607.9048
0.70771 | 1067570.2767 | 0.41411 | 47352.4501 | 0.50668 | 56432.4521 | 0.50668 | 131230.6616 | 0.50668 | 55698.8847 | 1358284.7252
0.65615 | 1056364.6747 | 0.71435 | 49757.9585 | 0.49642 | 56219.763 | 0.49642 | 130912.9761 | 0.49642 | 55654.4068 | 1348909.779
0.79396 | 1088813.9149 | 0.87362 | 51580.2224 | 0.71921 | 61482.9728 | 0.71921 | 137425.3049 | 0.71921 | 56755.0569 | 1396057.472
0.07256 | 946656.3174 | 0.19823 | 45333.4511 | 0.63589 | 59330.1949 | 0.63589 | 134987.0468 | 0.63589 | 56304.8648 | 1242611.8751
0.80156 | 1090883.8615 | 0.28054 | 46193.1372 | 0.29493 | 52410.8184 | 0.29493 | 123827.1208 | 0.29493 | 54851.5642 | 1368166.5021
0.27021 | 990034.291 | 0.46409 | 47736.64 | 0.47054 | 55692.4876 | 0.47054 | 130096.4066 | 0.47054 | 55544.1422 | 1279103.9675
0.75457 | 1078650.828 | 0.80048 | 50651.7796 | 0.48393 | 55963.6383 | 0.48393 | 130521.6094 | 0.48393 | 55600.8457 | 1371388.701
0.75177 | 1077959.4887 | 0.88303 | 51717.4957 | 0.42486 | 54792.2982 | 0.42486 | 128598.1939 | 0.42486 | 55355.8933 | 1368423.3699
0.22169 | 981551.1306 | 0.085594 | 43778.9884 | 0.097401 | 47982.8768 | 0.097401 | 113692.9417 | 0.097401 | 53851.3941 | 1240857.3315
0.22139 | 981497.0242 | 0.45938 | 47701.3237 | 0.78984 | 63575.6228 | 0.78984 | 139795.4551 | 0.78984 | 57192.6749 | 1289762.1007
0.85596 | 1107036.619 | 0.78432 | 50471.1478 | 0.10488 | 48208.3669 | 0.10488 | 114209.0182 | 0.10488 | 53902.3271 | 1373827.479
0.18726 | 974951.1165 | 0.32797 | 46631.293 | 0.29326 | 52381.3771 | 0.29326 | 123759.7387 | 0.29326 | 54844.9141 | 1252568.4394
0.26506 | 989173.238 | 0.44161 | 47566.573 | 0.2908 | 52337.7801 | 0.2908 | 123659.9589 | 0.2908 | 54835.0665 | 1267572.6166
0.52956 | 1031992.1395 | 0.8732 | 51574.1582 | 0.50537 | 56405.1942 | 0.50537 | 131190.3102 | 0.50537 | 55693.1845 | 1326854.9865
0.3267 | 998999.4269 | 0.29761 | 46354.8009 | 0.079998 | 47422.1123 | 0.079998 | 112409.5264 | 0.079998 | 53724.7303 | 1258910.5969
0.6006 | 1045196.5265 | 0.63002 | 49006.4969 | 0.41152 | 54536.1282 | 0.41152 | 128145.4644 | 0.41152 | 55302.3227 | 1332186.9387
0.75465 | 1078670.4142 | 0.98062 | 53782.5269 | 0.1612 | 49696.8386 | 0.1612 | 117615.6662 | 0.1612 | 54238.5386 | 1354003.9845
0.29723 | 994430.0817 | 0.69812 | 49605.4578 | 0.94524 | 70147.5598 | 0.94524 | 147238.8776 | 0.94524 | 58567.0078 | 1319988.9847
0.19842 | 977152.6093 | 0.073229 | 43555.4239 | 0.40851 | 54478.8949 | 0.40851 | 128042.5991 | 0.40851 | 55290.354 | 1258519.8812
0.84312 | 1102980.5609 | 0.58397 | 48632.3194 | 0.56236 | 57627.884 | 0.56236 | 132901.9332 | 0.56236 | 55948.8751 | 1398091.5725
0.90847 | 1125892.1742 | 0.84565 | 51199.6837 | 0.65424 | 59781.2159 | 0.65424 | 135497.883 | 0.65424 | 56399.183 | 1428770.1398
0.048669 | 938210.9242 | 0.67697 | 49412.8388 | 0.29066 | 52335.2238 | 0.29066 | 123654.1083 | 0.29066 | 54834.4891 | 1218447.5842
0.10254 | 955462.746 | 0.73937 | 50001.768 | 0.32921 | 53016.6088 | 0.32921 | 125173.9516 | 0.32921 | 54984.4866 | 1238639.561
0.81316 | 1094121.0489 | 0.58749 | 48660.1851 | 0.47864 | 55856.1292 | 0.47864 | 130354.383 | 0.47864 | 55578.3632 | 1384570.1094
0.9549 | 1147981.7349 | 0.18821 | 45217.4388 | 0.12874 | 48878.2704 | 0.12874 | 115742.2186 | 0.12874 | 54053.6429 | 1411873.3057
0.069822 | 945767.5099 | 0.42356 | 47426.8058 | 0.042367 | 45945.8454 | 0.042367 | 109030.8111 | 0.042367 | 53391.2756 | 1201562.2478
0.48039 | 1023431.2701 | 0.99721 | 54661.9323 | 0.59606 | 58388.642 | 0.59606 | 133873.3864 | 0.59606 | 56107.9659 | 1326463.1967
0.85902 | 1108027.4082 | 0.37836 | 47063.2523 | 0.76864 | 62914.7353 | 0.76864 | 139046.9292 | 0.76864 | 57054.4691 | 1414106.7941
0.60027 | 1045132.5019 | 0.038597 | 42800.4259 | 0.46586 | 55598.401 | 0.46586 | 129946.1665 | 0.46586 | 55524.4667 | 1329001.962
0.91472 | 1128467.8347 | 0.33251 | 46671.4985 | 0.71681 | 61416.7962 | 0.71681 | 137350.3528 | 0.71681 | 56741.2179 | 1430647.7002
0.198 | 977071.2179 | 0.79698 | 50612.0257 | 0.26831 | 51929.9756 | 0.26831 | 122726.6214 | 0.26831 | 54742.9529 | 1257082.7935
0.75316 | 1078302.6489 | 0.67265 | 49374.2609 | 0.31574 | 52776.9745 | 0.31574 | 124653.4982 | 0.31574 | 54933.1216 | 1360040.504
0.80156 | 1090882.234 | 0.029288 | 42542.5776 | 0.93748 | 69677.9822 | 0.93748 | 146707.0307 | 0.93748 | 58468.8091 | 1408278.6335
0.92985 | 1135124.4621 | 0.95226 | 52975.181 | 0.3584 | 53544.1832 | 0.3584 | 126266.1854 | 0.3584 | 55094.8857 | 1423004.8974
0.32393 | 998579.69 | 0.92745 | 52457.394 | 0.79299 | 63676.695 | 0.79299 | 139909.9303 | 0.79299 | 57213.8112 | 1311837.5205
0.45281 | 1018805.9897 | 0.65027 | 49178.3582 | 0.63223 | 59241.5135 | 0.63223 | 134886.1055 | 0.63223 | 56286.3197 | 1318398.2866
0.45015 | 1018365.1336 | 0.77747 | 50396.6633 | 0.62566 | 59083.5065 | 0.62566 | 134704.2663 | 0.62566 | 56253.277 | 1318802.8467
0.75185 | 1077979.4142 | 0.7649 | 50262.8536 | 0.7229 | 61585.2434 | 0.7229 | 137541.1373 | 0.7229 | 56776.4438 | 1384145.0923
0.88305 | 1116230.9794 | 0.26236 | 46015.5009 | 0.32047 | 52860.9198 | 0.32047 | 124837.6479 | 0.32047 | 54951.2959 | 1394896.3438
0.55011 | 1035704.1464 | 0.60621 | 48810.3468 | 0.35768 | 53531.078 | 0.35768 | 126239.893 | 0.35768 | 55092.1451 | 1319377.6094
0.1618 | 969671.3969 | 0.86618 | 51475.1604 | 0.42279 | 54752.2954 | 0.42279 | 128528.3105 | 0.42279 | 55347.5279 | 1259774.6911
0.84344 | 1103080.4431 | 0.49511 | 47964.719 | 0.43576 | 55003.69 | 0.43576 | 128962.6283 | 0.43576 | 55400.0999 | 1390411.5802
0.54639 | 1035025.9369 | 0.50773 | 48055.8449 | 0.39114 | 54150.6342 | 0.39114 | 127439.995 | 0.39114 | 55221.7076 | 1319894.1187
0.76483 | 1081212.5649 | 0.76023 | 50214.0697 | 0.47986 | 55880.8712 | 0.47986 | 130393.0255 | 0.47986 | 55583.5373 | 1373284.0687
0.82083 | 1096317.9136 | 0.38235 | 47096.1721 | 0.4661 | 55603.3782 | 0.4661 | 129954.1498 | 0.4661 | 55525.5075 | 1384497.1212
0.104 | 955856.7551 | 0.12451 | 44392.9937 | 0.092369 | 47826.2906 | 0.092369 | 113334.5645 | 0.092369 | 53816.0249 | 1215226.6288
0.17032 | 971482.5107 | 0.83099 | 51014.0134 | 0.58281 | 58086.0362 | 0.58281 | 133494.9942 | 0.58281 | 56044.6846 | 1270122.2392
0.84171 | 1102545.2206 | 0.45279 | 47651.6648 | 0.71962 | 61494.2149 | 0.71962 | 137438.0378 | 0.71962 | 56757.4078 | 1405886.5458
0.62165 | 1049331.07 | 0.70946 | 49711.5325 | 0.50631 | 56424.8459 | 0.50631 | 131219.4123 | 0.50631 | 55697.2941 | 1342384.1547
0.19185 | 975864.5548 | 0.67691 | 49412.2787 | 0.90463 | 67956.978 | 0.90463 | 144757.8091 | 0.90463 | 58108.9102 | 1296100.5307
0.23947 | 984759.3572 | 0.48153 | 47865.7505 | 0.036267 | 45650.7649 | 0.036267 | 108355.4638 | 0.036267 | 53324.6237 | 1239955.96
0.97243 | 1159325.2135 | 0.57534 | 48564.5822 | 0.62764 | 59130.9533 | 0.62764 | 134759.1388 | 0.62764 | 56263.1991 | 1458043.087
0.10269 | 955504.6512 | 0.26761 | 46067.3936 | 0.79083 | 63607.3364 | 0.79083 | 139831.3742 | 0.79083 | 57199.3068 | 1262210.0622
0.57892 | 1041051.7545 | 0.59124 | 48690.0091 | 0.7628 | 62738.1508 | 0.7628 | 138846.9284 | 0.7628 | 57017.5415 | 1348344.3843
0.25517 | 987493.4124 | 0.88304 | 51717.6842 | 0.8051 | 64072.2106 | 0.8051 | 140357.894 | 0.8051 | 57296.522 | 1300937.7233
0.19732 | 976938.9156 | 0.020765 | 42267.2694 | 0.83758 | 65198.4972 | 0.83758 | 141633.5342 | 0.83758 | 57532.0527 | 1283570.2691
0.2067 | 978746.5606 | 0.16767 | 44969.3731 | 0.62609 | 59093.8557 | 0.62609 | 134716.255 | 0.62609 | 56255.4412 | 1273781.4856
0.75788 | 1079471.9325 | 0.40233 | 47258.6114 | 0.50701 | 56439.3512 | 0.50701 | 131240.858 | 0.50701 | 55700.3274 | 1370111.0805
0.82463 | 1097423.1168 | 0.70493 | 49668.9056 | 0.78244 | 63341.2663 | 0.78244 | 139530.0212 | 0.78244 | 57143.6659 | 1407106.9757
0.79289 | 1088524.6405 | 0.97877 | 53716.3917 | 0.45387 | 55359.6276 | 0.45387 | 129558.4412 | 0.45387 | 55474.5341 | 1382633.635
0.61767 | 1048540.8264 | 0.12841 | 44448.8396 | 0.17062 | 49918.5298 | 0.17062 | 118123.0483 | 0.17062 | 54288.6136 | 1315319.8577
0.53653 | 1033242.4975 | 0.61589 | 48889.3548 | 0.40619 | 54434.7988 | 0.40619 | 127962.9078 | 0.40619 | 55281.1325 | 1319810.6915
0.99529 | 1183196.0116 | 0.33807 | 46720.3936 | 0.95811 | 71006.7888 | 0.95811 | 148212.0465 | 0.95811 | 58746.691 | 1507881.9315
0.33365 | 1000048.2021 | 0.41585 | 47366.2623 | 0.062467 | 46791.3139 | 0.062467 | 110965.8251 | 0.062467 | 53582.2475 | 1258753.8509
0.32591 | 998880.3793 | 0.76845 | 50300.3277 | 0.060739 | 46724.5854 | 0.060739 | 110813.1044 | 0.060739 | 53567.1751 | 1260285.5719
0.49752 | 1026366.0973 | 0.62424 | 48958.3324 | 0.25685 | 51715.646 | 0.25685 | 122236.0877 | 0.25685 | 54694.5407 | 1303970.7041
0.41741 | 1013036.9009 | 0.16261 | 44906.0694 | 0.13351 | 49004.6862 | 0.13351 | 116031.5452 | 0.13351 | 54082.1973 | 1277061.3991
0.019677 | 924296.3884 | 0.72086 | 49820.289 | 0.98857 | 73869.4947 | 0.98857 | 151454.3675 | 0.98857 | 59345.3442 | 1258785.8839
0.90819 | 1125781.1723 | 0.65482 | 49217.6859 | 0.9868 | 73635.7622 | 0.9868 | 151189.6404 | 0.9868 | 59296.4657 | 1459120.7264
0.89849 | 1121957.573 | 0.29898 | 46367.59 | 0.37935 | 53930.444 | 0.37935 | 127023.2381 | 0.37935 | 55175.6611 | 1404454.5062
0.26661 | 989432.4868 | 0.6046 | 48797.2892 | 0.82667 | 64808.6238 | 0.82667 | 141191.9608 | 0.82667 | 57450.5218 | 1301680.8823
0.49611 | 1026121.9999 | 0.0589 | 43271.1786 | 0.32376 | 52919.3111 | 0.32376 | 124964.5652 | 0.32376 | 54963.8217 | 1302240.8765
0.35705 | 1003589.3179 | 0.2793 | 46181.2105 | 0.56439 | 57672.9905 | 0.56439 | 132961.43 | 0.56439 | 55958.3079 | 1296363.2568
0.87587 | 1113699.976 | 0.79347 | 50572.6318 | 0.2171 | 50932.1977 | 0.2171 | 120443.0185 | 0.2171 | 54517.5778 | 1390165.4018
0.79319 | 1088607.3512 | 0.4701 | 47781.3867 | 0.89411 | 67470.9013 | 0.89411 | 144207.2752 | 0.89411 | 58007.2611 | 1406074.1755
0.92611 | 1133416.6571 | 0.13097 | 44485.0275 | 0.082429 | 47503.8677 | 0.082429 | 112596.6389 | 0.082429 | 53743.197 | 1391745.3882
0.23476 | 983921.2777 | 0.1387 | 44592.1631 | 0.31128 | 52698.2397 | 0.31128 | 124478.9326 | 0.31128 | 54915.8933 | 1260606.5064
0.12909 | 962231.8681 | 0.15636 | 44826.3664 | 0.66335 | 60009.5429 | 0.66335 | 135756.4877 | 0.66335 | 56446.9311 | 1259271.1962
0.013478 | 920107.9409 | 0.5447 | 48329.3377 | 0.41423 | 54587.9493 | 0.41423 | 128238.0544 | 0.41423 | 55313.1596 | 1206576.4419
0.29125 | 993475.2164 | 0.55047 | 48373.0359 | 0.5979 | 58431.2934 | 0.5979 | 133925.8931 | 0.5979 | 56116.8853 | 1290322.3242
0.37482 | 1006322.2391 | 0.13719 | 44571.3947 | 0.30384 | 52567.3331 | 0.30384 | 124184.6329 | 0.30384 | 54886.848 | 1282532.4479
0.36694 | 1005105.902 | 0.8539 | 51308.029 | 0.25336 | 51649.3485 | 0.25336 | 122084.3534 | 0.25336 | 54679.5657 | 1284827.1987
0.38449 | 1007827.1121 | 0.73544 | 49962.7012 | 0.27965 | 52137.5322 | 0.27965 | 123201.6538 | 0.27965 | 54789.8351 | 1287918.8343
0.43132 | 1015281.2892 | 0.25808 | 45972.8221 | 0.35388 | 53461.8253 | 0.35388 | 126100.2684 | 0.35388 | 55077.6629 | 1295893.8679
0.28255 | 992068.341 | 0.63902 | 49082.3217 | 0.24387 | 51466.9489 | 0.24387 | 121666.8974 | 0.24387 | 54638.3658 | 1268922.8747
0.064651 | 944040.0955 | 0.21988 | 45574.6131 | 0.79309 | 63679.7712 | 0.79309 | 139913.4143 | 0.79309 | 57214.4545 | 1250422.3486
0.2932 | 993787.7831 | 0.19569 | 45304.325 | 0.95579 | 70842.8065 | 0.95579 | 148026.3189 | 0.95579 | 58712.3988 | 1316673.6323
0.62483 | 1049966.8536 | 0.14611 | 44692.1824 | 0.1628 | 49734.9886 | 0.1628 | 117702.9797 | 0.1628 | 54247.1558 | 1316344.1601
0.081181 | 949349.9569 | 0.45164 | 47642.9491 | 0.41819 | 54663.9123 | 0.41819 | 128372.8493 | 0.41819 | 55329.0451 | 1235358.7127
0.79031 | 1087831.9071 | 0.43786 | 47537.7802 | 0.42077 | 54713.3825 | 0.42077 | 128460.0454 | 0.42077 | 55339.3904 | 1373882.5056
0.57257 | 1039857.34 | 0.98255 | 53854.7418 | 0.96953 | 71888.3047 | 0.96953 | 149210.4577 | 0.96953 | 58931.0349 | 1373741.8791
0.66136 | 1057457.5076 | 0.0023944 | 41298.2432 | 0.97887 | 72743.789 | 0.97887 | 150179.3852 | 0.97887 | 59109.935 | 1380788.86
0.50587 | 1027815.4234 | 0.71083 | 49724.4515 | 0.62968 | 59180.0935 | 0.62968 | 134815.7255 | 0.62968 | 56273.4754 | 1327809.1693
0.71059 | 1068224.9832 | 0.60553 | 48804.7646 | 0.20778 | 50738.3425 | 0.20778 | 119999.3444 | 0.20778 | 54473.7904 | 1342241.2251
0.25944 | 988222.4485 | 0.30883 | 46458.5879 | 0.6049 | 58593.583 | 0.6049 | 134123.8499 | 0.6049 | 56150.8235 | 1283549.2928
0.58875 | 1042918.0518 | 0.032005 | 42621.6006 | 0.61704 | 58878.478 | 0.61704 | 134464.4592 | 0.61704 | 56210.4012 | 1335092.9909
0.8377 | 1101317.5031 | 0.96758 | 53366.633 | 0.65049 | 59688.1266 | 0.65049 | 135392.4493 | 0.65049 | 56379.716 | 1406144.4279
0.52577 | 1031316.7625 | 0.95263 | 52983.8649 | 0.71041 | 61241.6064 | 0.71041 | 137151.9316 | 0.71041 | 56704.582 | 1339398.7474
0.087569 | 951255.0216 | 0.78713 | 50502.0465 | 0.094212 | 47884.1171 | 0.094212 | 113466.9113 | 0.094212 | 53829.0866 | 1216937.183
0.52282 | 1030794.1786 | 0.54498 | 48331.5071 | 0.92814 | 69150.1894 | 0.92814 | 146109.2488 | 0.92814 | 58358.4363 | 1352743.5601
0.54723 | 1035178.2378 | 0.55292 | 48391.6605 | 0.32772 | 52990.0847 | 0.32772 | 125117.1283 | 0.32772 | 54978.8786 | 1316655.9899
0.42277 | 1013899.0074 | 0.10507 | 44100.4964 | 0.29452 | 52403.7229 | 0.29452 | 123810.8813 | 0.29452 | 54849.9615 | 1289064.0695
0.71115 | 1068352.2696 | 0.95109 | 52948.0164 | 0.1504 | 49434.602 | 0.1504 | 117015.4885 | 0.1504 | 54179.3054 | 1341929.6819
0.66109 | 1057401.6007 | 0.23511 | 45737.2224 | 0.0014812 | 42737.8053 | 0.0014812 | 101688.6066 | 0.0014812 | 52666.6532 | 1300231.8882
0.84485 | 1103516.0529 | 0.2708 | 46098.6931 | 0.54732 | 57297.8125 | 0.54732 | 132458.9597 | 0.54732 | 55879.8501 | 1395251.3684
0.023724 | 926678.1498 | 0.38491 | 47117.2439 | 0.50916 | 56484.2469 | 0.50916 | 131307.0463 | 0.50916 | 55709.7161 | 1217296.403
0.4957 | 1026051.928 | 0.44126 | 47563.8324 | 0.12186 | 48692.1258 | 0.12186 | 115316.1915 | 0.12186 | 54011.5971 | 1291635.6748
0.38129 | 1007327.6541 | 0.80158 | 50664.3492 | 0.592 | 58295.393 | 0.592 | 133757.8848 | 0.592 | 56088.4656 | 1306133.7467
0.80271 | 1091200.2067 | 0.25848 | 45976.8291 | 0.14862 | 49390.3922 | 0.14862 | 116914.3059 | 0.14862 | 54169.3194 | 1357651.0533
0.31974 | 997939.1255 | 0.074814 | 43585.0814 | 0.25942 | 51764.0832 | 0.25942 | 122346.9454 | 0.25942 | 54705.4816 | 1270340.7173
0.67329 | 1059989.9964 | 0.50625 | 48045.1103 | 0.6006 | 58493.7377 | 0.6006 | 134002.4033 | 0.6006 | 56129.9437 | 1356661.1914
0.011754 | 918778.2882 | 0.27615 | 46150.8473 | 0.069453 | 47052.1275 | 0.069453 | 111562.7462 | 0.069453 | 53641.1593 | 1177185.1685
0.046134 | 937202.3833 | 0.36422 | 46945.1037 | 0.36914 | 53741.3163 | 0.36914 | 126656.8136 | 0.36914 | 55136.1105 | 1219681.7274
0.27902 | 991491.0392 | 0.16202 | 44898.5071 | 0.80235 | 63981.2968 | 0.80235 | 140254.9244 | 0.80235 | 57277.51 | 1297903.2775
0.8615 | 1108840.7324 | 0.54969 | 48367.1205 | 0.92493 | 68976.5424 | 0.92493 | 145912.575 | 0.92493 | 58322.123 | 1430419.0932
0.7159 | 1069440.4407 | 0.36525 | 46953.8106 | 0.4298 | 54887.8654 | 0.4298 | 128763.9533 | 0.4298 | 55375.8785 | 1355421.9486
0.83496 | 1100489.5076 | 0.82248 | 50909.8366 | 0.5249 | 56815.9918 | 0.5249 | 131787.4445 | 0.5249 | 55779.0911 | 1395781.8715
0.0076695 | 915168.6003 | 0.38565 | 47123.2655 | 0.29172 | 52354.0063 | 0.29172 | 123697.0955 | 0.29172 | 54838.7316 | 1193181.6993
0.49297 | 1025581.2589 | 0.038704 | 42803.206 | 0.99057 | 74156.6424 | 0.99057 | 151779.593 | 0.99057 | 59405.3929 | 1353726.0932
0.3417 | 1001259.5101 | 0.77165 | 50334.2764 | 0.98587 | 73518.5425 | 0.98587 | 151056.8765 | 0.98587 | 59271.9526 | 1335441.1581
0.76725 | 1081825.3041 | 0.46904 | 47773.5282 | 0.37112 | 53777.9292 | 0.37112 | 126728.3756 | 0.37112 | 55143.767 | 1365248.9042
0.65486 | 1056096.2748 | 0.28686 | 46253.5915 | 0.060027 | 46696.7804 | 0.060027 | 110749.4674 | 0.060027 | 53560.8945 | 1313357.0087
0.10531 | 956206.895 | 0.4068 | 47294.3875 | 0.44752 | 55234.16 | 0.44752 | 129350.904 | 0.44752 | 55448.2961 | 1243534.6426
0.033983 | 931929.4169 | 0.55617 | 48416.4674 | 0.16192 | 49713.9121 | 0.16192 | 117654.7422 | 0.16192 | 54242.3951 | 1201956.9337
0.899 | 1122154.7142 | 0.011112 | 41873.3731 | 0.28757 | 52280.105 | 0.28757 | 123527.9585 | 0.28757 | 54822.039 | 1394658.1898
0.99444 | 1181741.4455 | 0.66288 | 49287.9294 | 0.37266 | 53806.3749 | 0.37266 | 126783.7649 | 0.37266 | 55149.7156 | 1466769.2303
0.093741 | 953030.3675 | 0.29727 | 46351.619 | 0.20306 | 50638.4506 | 0.20306 | 119770.723 | 0.20306 | 54451.2271 | 1224242.3872
0.21296 | 979929.4604 | 0.19091 | 45248.992 | 0.79262 | 63664.7661 | 0.79262 | 139896.4195 | 0.79262 | 57211.3166 | 1285950.9546
0.59671 | 1044444.6019 | 0.54066 | 48298.9625 | 0.3056 | 52598.1397 | 0.3056 | 124254.3553 | 0.3056 | 54893.7291 | 1324489.7885
0.58944 | 1043048.5741 | 0.07623 | 43611.3151 | 0.4236 | 54768.0166 | 0.4236 | 128555.8102 | 0.4236 | 55350.8155 | 1325334.5314
0.48474 | 1024171.5697 | 0.55861 | 48435.1327 | 0.66794 | 60125.7164 | 0.66794 | 135888.0666 | 0.66794 | 56471.2254 | 1325091.7108
0.95643 | 1148872.546 | 0.42411 | 47431.104 | 0.6698 | 60172.9631 | 0.6698 | 135941.5786 | 0.6698 | 56481.1057 | 1448899.2974
0.68223 | 1061920.641 | 0.13132 | 44489.881 | 0.67114 | 60207.2645 | 0.67114 | 135980.4287 | 0.67114 | 56488.2789 | 1359086.494
0.26597 | 989325.489 | 0.62446 | 48960.1381 | 0.33627 | 53143.1917 | 0.33627 | 125442.531 | 0.33627 | 55011.0298 | 1271882.3796
0.37715 | 1006684.2273 | 0.60747 | 48820.5519 | 0.48756 | 56037.63 | 0.48756 | 130635.6785 | 0.48756 | 55616.3189 | 1297794.4066
0.75763 | 1079408.9938 | 0.41206 | 47336.2003 | 0.23906 | 51373.0573 | 0.23906 | 121452.0088 | 0.23906 | 54617.1578 | 1354187.418
0.79598 | 1089360.9522 | 0.54459 | 48328.5354 | 0.95198 | 70582.9675 | 0.95198 | 147732.0235 | 0.95198 | 58658.0609 | 1414662.5395
0.12749 | 961843.8314 | 0.17037 | 45002.8366 | 0.51859 | 56682.3054 | 0.51859 | 131595.6732 | 0.51859 | 55751.1344 | 1250875.7809
0.036108 | 932912.555 | 0.44249 | 47573.297 | 0.14171 | 49216.5401 | 0.14171 | 116516.4126 | 0.14171 | 54130.0503 | 1200348.8549
0.86446 | 1109820.2875 | 0.22437 | 45623.0918 | 0.48047 | 55893.1117 | 0.48047 | 130412.108 | 0.48047 | 55586.097 | 1397334.6962
0.81253 | 1093941.0642 | 0.46628 | 47752.9625 | 0.12148 | 48681.6042 | 0.12148 | 115292.111 | 0.12148 | 54009.2206 | 1359676.9625
0.55739 | 1037038.3887 | 0.89894 | 51963.0872 | 0.95302 | 70653.1086 | 0.95302 | 147811.4658 | 0.95302 | 58672.7289 | 1366138.7791
0.60088 | 1045250.2205 | 0.082492 | 43724.5184 | 0.12029 | 48648.8331 | 0.12029 | 115217.1081 | 0.12029 | 54001.8183 | 1306842.4985
0.44714 | 1017870.044 | 0.21555 | 45527.3713 | 0.37324 | 53817.0616 | 0.37324 | 126804.5269 | 0.37324 | 55151.9504 | 1299170.9542
0.023439 | 926517.2194 | 0.46891 | 47772.5709 | 0.16493 | 49785.3344 | 0.16493 | 117818.2056 | 0.16493 | 54258.5278 | 1196151.858
0.12969 | 962375.2781 | 0.082489 | 43724.4599 | 0.67674 | 60350.8362 | 0.67674 | 136143.039 | 0.67674 | 56518.3028 | 1259111.916
0.81702 | 1095218.8336 | 0.26323 | 46024.1453 | 0.27327 | 52021.2811 | 0.27327 | 122935.5913 | 0.27327 | 54763.5767 | 1370963.4281
0.83318 | 1099953.0033 | 0.58987 | 48679.0522 | 0.55971 | 57569.4251 | 0.55971 | 132824.4568 | 0.55971 | 55936.6501 | 1394962.5875
0.74077 | 1075285.7548 | 0.95229 | 52975.9847 | 0.70213 | 61018.0198 | 0.70213 | 136898.6958 | 0.70213 | 56657.8252 | 1382836.2803
0.52697 | 1031530.5992 | 0.49439 | 47959.5247 | 0.8462 | 65515.7878 | 0.8462 | 141992.8998 | 0.8462 | 57598.405 | 1344597.2164
0.29535 | 994129.9467 | 0.68597 | 49493.9903 | 0.71576 | 61388.0301 | 0.71576 | 137317.7722 | 0.71576 | 56735.2023 | 1299064.9417
0.14338 | 965584.2782 | 0.98898 | 54131.1921 | 0.040548 | 45860.2437 | 0.040548 | 108834.8954 | 0.040548 | 53371.9402 | 1227782.5495
0.51742 | 1029839.5344 | 0.059829 | 43290.589 | 0.84403 | 65435.2961 | 0.84403 | 141901.7343 | 0.84403 | 57581.5724 | 1338048.7262
0.0087945 | 916242.9789 | 0.35789 | 46891.5034 | 0.89497 | 67509.7846 | 0.89497 | 144251.3147 | 0.89497 | 58015.3924 | 1232910.974
0.16169 | 969647.3545 | 0.56446 | 48480.158 | 0.37745 | 53895.0919 | 0.37745 | 126955.3503 | 0.37745 | 55168.2683 | 1254146.2229
0.21292 | 979922.6794 | 0.19986 | 45352.0954 | 0.92741 | 69110.2919 | 0.92741 | 146064.0606 | 0.92741 | 58350.0928 | 1298799.2201
0.010891 | 918075.4464 | 0.76803 | 50295.8764 | 0.42295 | 54755.4772 | 0.42295 | 128533.8798 | 0.42295 | 55348.1933 | 1207008.873
0.86776 | 1110923.6021 | 0.08995 | 43853.8558 | 0.11096 | 48385.6995 | 0.11096 | 114614.8772 | 0.11096 | 53942.3825 | 1371720.4171
0.014877 | 921126.0505 | 0.97524 | 53597.6985 | 0.95728 | 70947.7674 | 0.95728 | 148145.1984 | 0.95728 | 58734.3484 | 1252551.0631
0.17103 | 971631.0693 | 0.17808 | 45096.8567 | 0.84451 | 65453.1653 | 0.84451 | 141921.9731 | 0.84451 | 57585.3093 | 1281688.3735
0.59936 | 1044957.5719 | 0.1031 | 44069.4403 | 0.58747 | 58191.9472 | 0.58747 | 133628.6099 | 0.58747 | 56066.8328 | 1336914.4022
0.10167 | 955228.7793 | 0.39767 | 47221.053 | 0.11094 | 48385.0621 | 0.11094 | 114613.4184 | 0.11094 | 53942.2385 | 1219390.5513
0.58079 | 1041404.7126 | 0.40761 | 47300.8463 | 0.52848 | 56892.1679 | 0.52848 | 131895.6396 | 0.52848 | 55795.0211 | 1333288.3874
Average | 1032474.4241 |  | 47764.3161 |  | 56916.2318 |  | 129729.5602 |  | 55781.1793 | 1322665.7115
StdDev | 61741.4881 |  | 2856.3032 |  | 7049.0893 |  | 11050.5683 |  | 1499.8874 | 66115.169
[10 empty] | 1173534.4044 | `
1515470.4385
1150000
1175000
1200000
1225000
1250000
1275000
1300000
1325000
1350000
1375000
1400000
1425000
1450000
1475000
1500000
1525000

## Descriptive
Mean | 1322665.7115
Standard Error | 2090.7452
Median | 1318857.7853
Mode | #N/A
Standard Deviation | 66115.169
Sample Variance | 4371215565.3251
Kurtosis | -0.40861
Skewness | 0.25954
Range | 341936.0341
Minimum | 1173534.4044
Maximum | 1515470.4385
Sum | 1322665711.4855
Count | 1000

## Histogram
Bin | Frequency
1150000 | 0
1175000 | 1
1200000 | 16
1225000 | 44
1250000 | 81
1275000 | 115
1300000 | 139
1325000 | 143
1350000 | 132
1375000 | 101
1400000 | 100
1425000 | 61 | 933
1450000 | 33
1475000 | 20
1500000 | 10
1525000 | 4
More | 0 | 1000