UNIVERSITY OF SOUTHERN CALIFORNIA

Marshall School of Business

Department Information and Operations Management

IOM580 - Project Management

Spring 2009

Dr. Ardavan Asef-Vaziri

Final Exam

March 3, 2009

Time: 2 Hours

Name: (please print)

This exam consists of 12 questions and 4 problems. Each question weights at 5 points; each problem weights at 10 points. Eight pages including this page.

This is an open-book, open-notes exam. You may use a simple calculator.

No laptops nor PDAs are allowed.

Sharing materials with other students is not allowed.

Please sign here to indicate that you have adhered to university policies regarding ethical behavior in preparing for and completing this exam.

Good Luck

Please write in a way that I can read it. Thanks

Please write in a way that I can read it. Thanks

Please write in a way that I can read it. Thanks

P1[16  points]. In formulation of  the Southern Care Hospital case as a linear program model, we defined a set of binary variables Xij such that

Xij = 1 if task i  is assigned to employee  j and 0 otherwise.

a) Write the required constraints for this problem.

b) What difficulty did we have in solving the problem using the solver and how did we resolve it?

c) The number of  employees assigned to this project was restricted to  4.  How this constraint was implemented in the model?  What was the main difference between the decision variables defined for this constraint and our original Xij decision variables?

d) The number of  the black belt employees assigned to this project was restricted to  1.How did we handled this part of the model?

P2 [16  points]. Consider the following project.

| Activity | Activity duration (days) | Activity | Activity duration (days) |
| --- | --- | --- | --- |
| A | 4 | F | 5 |
| B | 5 | G | 3 |
| C | 4 | H | 4 |
| D | 2 | I | 2 |
| E | 4 |  |  |

A

B

C

D

E

G

H

F

I

| Activity | A | B | C | D | E | F | G | H | I |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Earliest Start |  |  |  |  |  |  |  |  |  |
| Latest Start |  |  |  |  |  |  |  |  |  |

a) Fill the earliest start row in the above table.

b) Fill the latest start row in the above table.

c1) Suppose extra budget is allocated to this project. With this extra money you can either reduce the duration of H or G by 2 days. Which activity should you invest? Why?

c2) Given your decision. What is the new duration of the project?

P3 [12 points]. Given the following network

START

END

D

C

B

A

| Activity | Time |  |
| --- | --- | --- |
|  | Mean | Variance |
| A | 4 | 2 |
| B | 12 | 4 |
| C | 10 | 5 |
| D | 3 | 1 |

- What is the probability to complete the critical path in 17 days?

- What due date has a 90% probability (or greater) of being met by the critical path?

c) What project due date has a 90% probability (or greater) of being met?

P4 [16 points].  Suppose that you had a project that was targeted to finish in 12 months, at a cost of $600K. At the end of month three, the EV stats look like this:

| Month | BCWS | ACWP | BCWP |
| --- | --- | --- | --- |
| 3 | 100K | 120K | 75K |

- What is your optimistic estimate for budget  to completion (ETC) of this project

BAC = 600-75 = 525

Or

CV = 75-120 = -45

EAC= 600+45 = 645

ETC = 645-120 = 525

- What is your pessimistic estimate for budget  to completion (ETC) of this project

CPI = 75/120 =  0.625

EAC = 600/0.625 = 960

960-120 = 840

- What is your optimistic estimate for  time  to completion of this project

SPI = 75/100 = 0.75

3=3/0.75 = 4  4-3 = 1

12-3+1 = 10

- What is your pessimistic estimate for time  to completion of this project

SPI = 75/100 = 0.75

Time at completion = 12/0.75 = 16 months

Time to Completion = 16-3 = 13 months

P5[8 points].    A project has two sequential tasks. They both follow Triangular  distribution with  duration parameters of:  optimistic 3 days, most likely 5 days, and pessimistic 9 days.

a) Using rand() = 0.2  generate a random instance of the duration of the first task.

b) Using rand() = 0.7  generate a random instance of the duration of the first task.

P6[12 points] .   The board of directors of IOM580 Development Corporation is considering capital investments to be included in their Program. There are 25 candidate projects to be included in the  project portfolio. Partial selection of a project is NOT  possible.

A binary variable Xi  has been defined which is  1 if project i  is included in the portfolio and is 0 otherwise. Write the following constraints

- Neither project 8 and project 9 can be undertaken unless one of the projects 1 or  2 is undertaken .

- If project 11 in undertaken both projects 3 and 4 must be undertaken.

- If both projects 3 and 4 are undertaken, project 11 must be undertaken.

P7[ 8 points].    We have one unit of each of the three resources of Resource A, Resource B, and Resource C.  The contract of the following project indicates that we must finish the project in 20  weeks. Compute the project buffer.

| Task | Precedence | Duration | Resource |
| --- | --- | --- | --- |
| Task1 | - | 5 weeks | Resource A |
| Task2 | - | 8 weeks | Resource B |
| Task3 | Task1 | 7 weeks | Resource B |
| Task4 | Task2 | 4 weeks | Resource A |
| Task5 | Task3 and Task4 | 3 weeks | Resource C |

P8 [8 points]. Draw activity on ARROW (AOA) network for the following project

Task	Preceding

Task

START

D	START

A	START

F	D,A

E	D

G	F,E

B	F

H	G

C	H

END	C,B

P9 [4 points].  Solve problem 23 of chapter 6 on page 233.