UNIVERSITY OF SOUTHERN CALIFORNIA

Marshall School of Business

Department Information and Operations Management

IOM580 - Project Management

Spring 2009

Dr. Ardavan Asef-Vaziri

Mid-Term Exam

March 3, 2009

Time: 90  Minutes

Name: (please print)

This exam consists of 12 questions and 4 problems. Each question weights at 5 points; each problem weights at 10 points. Eight pages including this page.

This is an open-book, open-notes exam. You may use a simple calculator.

No laptops nor PDAs are allowed.

Sharing materials with other students is not allowed.

Please sign here to indicate that you have adhered to university policies regarding ethical behavior in preparing for and completing this exam.

Good Luck

Please write clearly. Thanks

Q1. Using a project management example:

(a) Clearly define sub-optimization.

(b) Explain how we should measure the efficiency of a subsystem.

Q2. Explain the main difference between the two types of matrix organization:

(a) Strong (or hard)

(b) Weak (or soft).

Q3. There is a danger in letting the client “visit” the project operation too frequently, not the least of which is “scope creep” or informal changes to the project’s performance specifications.

- How might the danger of scope creep be monitored and controlled?

(i)

(ii)

(iii)

- Besides scope creep, what other dangers might arise in letting the client “visit” the project operation too frequently?

Q4. How should a PM decide which problems (or potential problems) deserve reporting to management and which are not worth the trouble?

Q5. Discuss how you would go about getting competent staff from a functional department.

(i)

(ii)

(iii)

Q6. Contrast Gantt charts and precedence diagrams to Design Matrix Structure.

Q7. Would you expect a task in a manufacturing plant that uses lots of complex equipment to have a learning curve coefficient closer to 70 percent, or to 95 percent? Explain clearly.

Q8. What went wrong with the purchasing manager’s assistant’s solution (outlined in Section 4.3) to the problem of having an inadequate supply of hard-to-obtain parts? You need to explain two points.

a)

b)

Q9. Clearly describe for what purpose we use the following metrics, explain the two main benefits of each one.

a) Mean Absolute Deviation.

(i)

(ii)

b) Tracking Signal.

(i)

(ii)

Q10.  Project USC is composed of two sequential activities A and B, where activity A is predecessor of activity B. Project UCLA is composed of two parallel activities C and D which are predecessors of activity E. Duration of each of these 5 activities follows uniform distribution with parameters 8 and 12 days. Obviously, average duration of each of activities A, B, C, D, and E is 10 days.

A

B

Project USC

Project UCLA

C

E

D

Duration of which project is longer? Why? Explain clearly.

Q11. Definition: Coefficient of variation is defined as standard deviation divided by mean.

Question: In bottom up budgeting, the coefficient of variation is higher at higher levels of the WBS. Is this true or false? Explain clearly.

Q12. The two most important information shown in Wheelwright and Clark (1992) project positioning graph are:

(i)

(ii)

P1. Present values of the investment of a project (cash outflow) that has normal distribution with a mean of 100 and standard deviation of 20. Present values of the cash inflow due to operations of the project that has a mean of 200 and standard deviation of 50.

a) Compute the mean and standard deviation of NPV of the project.

b) Compute probability of having a negative NPV.

P2. Let us give a new definition for NPV and assume NPV is computed at the end of year 2, as opposed to the end of year 0. Accordingly;

[NPV] is defined as value of all positive and negative cash flow at the end of year 2.

[PV] is defined as value of a specific cash flow at the end of year 2.

The discount rate is 10 percent.

a) Initial investment of a project at the end of Year 1 has a mean of 100 and standard deviation of 30. Compute the mean and standard deviation of [PV] of the initial investment.

b) The net cash inflow of the project at the end of Year 3 has a mean of 150 and standard deviation of 40.  Compute the mean and standard deviation of [PV] of the cash inflow.

P3.  A project has two sequential tasks. The first task follows Uniform distribution with parameters 50 and 100 days. The second task follows Normal distribution with a mean of 100 and standard deviation of 15 days.

a) Using rand() = .65, generate a random instance of the duration of the first task.

b) Using rand() = .56, generate a random instance of the duration of the second task.

P4.  The IOM580 Development Corporation is considering taking part in one or more of three different development projects-A, B, and C-that are about to be launched. Each project requires a significant investment over the next few years and then would be sold upon completion. For simplicity, we assume the interest rate is equal to ZERO (i =0).  The projected cash flows (in millions of dollars) associated with each project are shown in the table below.

| Year | Project A | Project B | Project C |
| --- | --- | --- | --- |
| 1 | -4 | -8 | -10 |
| 2 | -6 | -8 | -7 |
| 3 | -6 | -4 | -7 |
| 4 | 24 | -4 | -5 |
| 5 | 0 | 30 | -3 |
| 6 | 0 | 0 | 44 |

IOM580 has $10 million available now and expects to receive $6 million from other projects by the end of each year (1 through 6) that would be available for the ongoing investments the following year in projects A, B, and C. By acting now, the company may participate in each project either fully, fractionally (with other development partners), or not at all. If IOM580 participates at less than 100 percent, then all the cash flows associated with that project are reduced proportionally. Company policy requires ending each year with a cash balance of at least $1 million.

Develop a linear programming model to help IOM580 to select the optimal mix of investment in order to maximize NPV.

- Clearly define the decision variables

- Using your decision variables, write the objective function.

- Write the budget constraint for year 1

- Write the budget constraint for year 2