###### Chapter 3: Planning the Project

###### True/False

- 1. 	Defining resource needs is NOT necessary on small projects.

- Answer: False

- Response: See page 74

- Level: medium

- 2. 	A representative of senior management should be invited to the project launch meeting.

- Answer: True

- Response: See page 77

- Level: medium

- 3. 	The primary purpose of the launch meeting is to develop the project plan and budget.

- Answer: False

- Response: See pages 77 and 78

- Level: medium

- 4.	When planning, it is best for the project manager to breakdown and define the different levels of the project plan.

- Answer: False

- Response: See page 79

- Level: medium

- 5. 	The initial project meeting is just to coordinate the project, so areas of responsibility do NOT need to be discussed.

- Answer: False

- Response: See page 77

- Level: medium

6. 	The project plan should begin with a complete description of all agreements made with the client or any third party.

Answer: False

Response: See page 73

Level: medium

7. 	As a rule of thumb, the lowest level tasks in a typical project should NOT take longer than two days to complete.

Answer: False

Response: See page 79

Level: medium

8. 	The start and finish date of a project must be specified before the action plan can be completed.

Answer: False

Response: See page 83

Level: medium

9. 	Procedures for monitoring, collecting, and storing data on project performance should be discussed in the Schedules section of the project master plan.

Answer: False

Response: See page 73

Level: medium

10. 	The details of the project work force are discussed in the Resource Requirements section of the project master plan.

Answer: False

Response: See page 74

Level: medium

11. 	It is acceptable to restrict the launch meeting to brainstorming a problem.

Answer: True

Response: See page 77

Level: medium

12. 	The action plan should identify the project’s deliverable.

Answer: True

Response: See page 79

Level: easy

13. 	It is NOT possible to overdo it when it comes to project planning.

Answer: False

Response: See page 72

Level: medium

14.	A work breakdown structure is similar to an organizational chart of a project.

Answer: True

Response: See page 87

Level: easy

15. 	Lack of planning is a major contributor to project’s failure.

Answer: True

Response: See page 72

Level: medium

16. 	You can depict who is responsible for a task on a Linear Responsibility Chart.

Answer: True

Response: See pages 88 and 90

Level: medium

17. 	The “responsible” designation in the linear responsibility chart highlights individuals that should get progress reports.

Answer: False

Response: See page 90

Level: medium

18. 	Taken together, the Linear Responsibility Chart and the Work Breakdown Structure may be used to determine the importance of each task listed.

Answer: False

Response: See pages 87 to 91

Level: medium

19. 	The salary requirements of human resources are a required element in the project plan.

Answer: False

Response: See page 81

Level: medium

20. 	The Work Breakdown Structure is one way to separate project activities by their level of importance.

Answer: False

Response: See pages 87 and 88

Level: medium

21. 	Multidisciplinary teams are almost certain to operate in an environment of conflict.

Answer: True

Response: See page 94

Level: easy

22. 	Concurrent engineering is typically only applicable to new product development projects.

Answer: False

Response: See page 95

Level: medium

23. 	For a self-directed team to be successful, team members must be given their authority and mission by senior management.

Answer: True

Response: See page 100

Level: medium

24.	A limitation of traditional project management planning tools is that they do NOT address the flow of information.

Answer: True

Response: See page 89

Level: medium

25.	The process of managing the way different departments or groups work together is called integration management.

Answer: True

Response: See page 95

Level: easy

26. 	Another name for concurrent engineering is simultaneous engineering.

Answer: True

Response: See page 95

Level: easy

27. 	Precedence diagrams are useful in helping understand what information is needed from one task to complete other tasks.

Answer: False

Response: See page 89

Level: medium

28.	Mind mapping is a whole-brain approach that is particularly applicable to project management.

Answer: True

Response: See page 91

Level: easy

29.	One of the problems with mind mapping is that it is relatively difficult to convert into work breakdown structure (WBS).

Answer: False

Response: See page 93

Level: medium

30. 	The Design Structure Matrix can be used to identify potential rework situations due to the flow of information in a project.

Answer: True

Response: See page 98 and 99

Level: Medium

31. 	While the Design Structure Matrix can help identify potential rework situations, typically nothing can be done to avoid them.

Answer: False

Response: See page 99

Level: medium

32. 	A disadvantage of empowerment is the lack of timely feedback.

Answer: False

Response: See page 100

###### Level: medium

###### Multiple Choice

### 33. 	The results of the launch meeting include:

### a) finalizing the project team

### b) finalizing the project’s schedule

### c) finalizing the project’s budget

### d) the project’s scope is understood

e) selecting the project champion

Answer: d

Response: See page 77

Level: medium

34. 	Which of the following is NOT an element of the project master plan?

a) schedules

b) project charter

c) resource requirements

### d) personnel

e) potential problems

Answer: b

Response: See pages 78 and 79

Level: medium

35. 	What is the primary purpose of creating a work breakdown structure?

a) to draw the project plan as a chart or tree

b) to make sure important tasks aren’t overlooked

c) so that all team members can see what others are working on

d) to assign budget numbers to tasks

e) to identify important precedence relationships

Answer: b

Response: See page 87

Level: medium

36. 	Which of the following is used to show linkages between people and tasks?

### a) the Work Breakdown Structure

b) the Linear Responsibility Chart

c) the Project Action Plan

d) the Project Resource Diagram

e) the Concurrent Engineering Chart

Answer: b

Response: See page 90

Level: medium

37. 	The process of managing the way different groups work together on a project is called:

### a) concurrent engineering

b) integration management

c) interface management

d) transdisciplinary engineering

e) simultaneous engineering

Answer: c

Response: See page 96

Level: difficult

38. 	Which of the following is NOT a category in the linear responsibility chart?

a) Responsible

b) Support

c) Validate

d) Notification

e) Approval

Answer: c

Response: See page 90

Level: medium

39. 	The first task of a newly appointed project manager is

a) to negotiate the project’s budget

b) to negotiate with functional managers for key resources

c)  to develop a work breakdown structure for the project

d) to review the project objectives with senior management

e) to develop a linear responsibility chart for the project

Answer: d

Response: See page 77

Level: medium

40.	Which of the following is NOT typically included in the project action plan?

a) potential barriers

b) immediate predecessor tasks

c) estimated resources

d) individuals tasks are assigned to

e) estimated task duration

Answer: a

Response: See pages 80 and 81

Level: medium

41.	 A(n) __________________ shows the set of all tasks in a project arranged by task level?

a) Linear Responsibility Chart

b) Work Breakdown Structure

c) Gantt chart

d) Design Structure Matrix

e) Aggregate Project Portfolio

Answer: b

Response: See page 87

Level: easy

42. 	According to the text, the use of sticky-notes can be particularly useful for constructing a(n)

a) Linear Responsibility Chart

b) Work Breakdown Structure

c) Gantt chart

d) Design Structure Matrix

e) Aggregate Project Portfolio

Answer: b

Response: See page 87

Level: medium

43	In order to prepare a mind map, you need to start with:

a) the maximum allowable cost of the project

b) a definition of role of the working professional programs (WPPs)

c) a means of evaluating the results

d) the most detailed tasks

e) a statement of the project’s objectives

Answer: e

Response: See page 91

Level: easy

44. 	SMT standards for

a) staff, management, and technicians

b) strategic management of technology

c) significant management task

d) structured matrix template

e) self-managed teams

Answer: e

Response: See page 99

Level: medium

45. 	SDT stands for

a) study, design, test

b) self-directed team

c) significantly delayed task

d) standard design task

e) standard development tool

Answer: b

Response: See page 99

Level: medium

46. 	Which of the following is NOT an important advantage of empowerment?

a) high quality solutions

b) micromanagement avoided

c) high degree of worker specialization

d) synergistic solutions

e) timely feedback

Answer: c

Response: See page 100

Level: medium

47. 	Entries above the diagonal in the Design Structure Matrix indicate

a) tasks that need to be shortened

b) tasks that have no resources assigned to them

c) tasks that are on the critical path

d) potential rework situations

e) tasks with no predecessors

Answer: d

Response: See page 99

Level: medium

48. 	In the Design Structure Matrix

a) the rows correspond to tasks and the columns correspond to resources

b) both the rows and columns correspond to tasks

c) the rows correspond to tasks and the columns correspond to functional departments

d) the rows correspond to resources and the columns correspond to tasks

e) the rows correspond to resources and the columns correspond to functional

departments

Answer: b

Response: See page 98

Level: medium

# Short Answer

49. 	What is the primary function of a project plan?

Response: See pages 72 and 73

50. 	List 9 categories of information needed in a project master plan.

Response: See pages 73 and 74

51. 	List some of the results of the project launch meeting.

Response: See pages 77 and 78

52. 	Define Hierarchical Planning.

Response: See pages 79 and 80

53. 	What is included in the project action plan?

Response: See pages 80 to 85

54.	What are the key concepts behind mind mapping?

Response: See pages 91

55. 	Why is it important to use participative management and empowered teams on a project?

Response: See pages 99 and 100

56. 	Explain how to construct the Design Structure Matrix.

Response: See pages 97 to 99

57. 	What are some options for eliminating potential rework situations when they are discovered with the Design Structure Matrix?

Response: See page 99

58. 	What is concurrent engineering?

Response: See page 95

59. 	What is integration management?  Why is it important?

Response: See page 95