###### Chapter 4: Budgeting the Project

###### True/False

1. 	The project’s budget is merely the sum of its resource costs.

Answer: False

Response: See page 107

Level: medium

2. 	A budget is a plan for allocating resources to project activities.

Answer: True

Response: See page 107

Level: easy

3. 	Overhead and indirect charges should NOT be assigned to a project.

Answer: False

Response: See page 110

Level: medium

4. 	Most organizations use top-down budgeting.

Answer: True

Response: See pages 110 and 111

Level: medium

5. 	Because project budgeting is for a special case and the organization’s budgeting  process is for routine work, the project manager need NOT be familiar with the organization’s accounting system.

Answer: False

Response: See page 110

Level: medium

6. 	Budget cuts are usually disastrous to an exponential life-cycle project.

Answer: True

Response: See pages 113 and 114

Level: medium

7. 	Activity budgets show expenses by task and expected time period of the expenditure.

Answer: False

Response: See page 116

Level: medium

8. 	There is no way other than guessing to estimate the impact of learning on a project’s task.

Answer: False

Response: See pages 117 to 120

Level: easy

9. 	Calculating the Tracking Signal can not only reveal if estimates are biased, it can also tell how severe the bias is.

Answer: True

Response: See pages 121 and 122

Level: medium

10. 	By very careful planning, a project manager can do away with cost uncertainty.

Answer: False

Response: See page 124

Level: medium

11. 	Expected value is a tool for risk analysis.

Answer: True

Response: See page 131

Level: medium

12. 	Traditional organizational budgets are task-oriented, rather than activity-oriented.

Answer: False

Response: See page 116

Level: medium

13. 	Learning curve theory states that performance of labor per unit will improve by a percentage each time production increases by the same percentage.

Answer: False

Response: See page 118

Level: medium

14. 	Learning curve theory states that performance of labor per unit will improve by a fixed percentage each time production doubles.

Answer: True

Response: See page 118

Level: medium

15. 	Individual elements of project budgets are generally more accurate in bottom-up budgeting.

Answer: True

Response: See page 111

Level: medium

16. 	The project budget acts as a project control.

Answer: True

Response: See page 107

Level: medium

17.	A budget is a plan for allocating resources.

Answer: True

Response: See page 107

Level: medium

18.	Budgeting a project is often more difficult than budgeting routine activities.

Answer: True

Response: See page 116

Level: medium

19. 	The project manager recognizes an expense when an invoice is actually paid.

Answer: False

Response: See page 110

Level: medium

20. 	A key advantage of top-down budgeting is that the overall budget costs can be estimated quite accurately.

Answer: True

Response: See page 110

Level: medium

21. 	With top-down budgeting, overlooking a small but important task can often cause a serious budgetary problem.

Answer: False

Response: See page 110

Level: medium

22. 	Organizational tradition has little or no impact on the firm’s project budgeting.

Answer: False

Response: See Page 110

Level: medium

23.	Bottom-up budgets are usually more accurate in the detailed tasks.

Answer: True

Response: See page 111

Level: medium

24. 	For projects with S-shaped life cycles, top-down budgeting is most likely unacceptable.

Answer: False

Response: See page 114

Level: medium

25. 	Mechanical tasks typically have higher learning rates than more mental tasks.

Answer: False

Response: See page 118

Level: medium

26. 	Random errors will tend to cancel out.

Answer: True

Response: See page 121

Level: medium

27. 	The result of game theory analysis is a Risk Priority Number.

Answer: False

Response: See page 130

Level: medium

28. 	Organizations can use both top-down and bottom-up budgeting.

Answer: True

Response: See page 111

Level: medium

29. 	Learning curves can be used to help improve cost estimates.

Answer: True

Response: See pages 118 and 119

Level: easy

30. 	Top-down budgeting typically results in better acceptance of the budget.

Answer: False

Response: See page 111

Level: medium

31.	Contingency planning is generally begun at that point in time when an organization finds itself in serious financial trouble.

Answer: False

Response: See page 137

Level: easy

Multiple Choice

32. 	Why is it necessary to consider the learning curve of resources on a project?

a) to estimate labor costs properly

b) to improve project team morale

c) because it always takes less time to do a task after someone has done it a few times

d) collective bargaining contracts require it

e) All of the above

Answer: a

Response: See page 118

Level: easy

33. 	The budgeting approach based on the collective judgments of top and middle managers is called:

a) top-down budgeting

b) bottom-up budgeting

c) activity budgeting

d) program budgeting

e) life cycle budgeting

Answer: a

Response: See page 110

Level: medium

34. 	A requirement of top-down budgeting is:

### a) involvement of the project team

b) estimating the detailed level of the project’s tasks

c) applying the learning curve to labor time estimates

d) all of the above

e) none of the above

Answer: e

Response: See pages 110 and 111

Level: medium

35. 	A problem with bottom-up budgeting is:

a) individual team members overstate their budget needs

b) lack of involvement from the project team

c) underestimating the project task’s budget requirements

d) all of the above

e) none of the above

Answer: a

Response: See page 111

Level: medium

36.	Which of the following statements is NOT true about a firm and its project accounting?

a) each firm has its own rules with regard to the allocation of overhead

b) most firms must comply with the Sarbane-Oxley Act

c) the project manager must rely on the accounting department to make special

allowances for his/her project

d) most firms have their own accounting idiosyncrasies

e) unexpected charges may suddenly appear when the PM least expects it

Answer: c

Response: See page 110

Level: medium

37. 	The name given to the budget process that aggregates income and expenditures across projects is:

### a) activity-oriented budget

b) top-down budget

c) bottom-up budget

d) program-oriented budget

e) activity-based costing

Answer: d

Response: See page 116

Level: medium

38. 	The first unit requires 10 hours to complete.  If the industry uses an 80 percent learning rate, how long should the third unit take?

a) 10 hours

b) 9 hours

c) 8 hours

d) 7.02 hours

e) 6.40 hours

Answer: d

Response: See page 119

Level: medium

39. 	The first unit required 6 hours.  If the industry uses a 90 percent learning rate, how long should the fourth unit take?

a) 6 hours

b) 4.86 hours

c) 3.75 hours

d) 3.34 hours

e) 2.67 hours

Answer: b

Response: See page 119

Level: medium

40. 	FMEA stands for

a) Financial Methods and Efficiency Analysis

b) Failure Modes and Effect Analysis

c) Full Monetary Expenditure Accrual

d) Financial Measurement of Expenses Accrued

e) Factor Mode and Efficiency Analysis

Answer: b

Response: See page 128

Level: medium

41. 	Which of the following is most closely associated with FMEA?

a) risk priority number

b) game theory

c) expected value

d) simulation

e) program budgeting

Answer: a

Response: See pages 128 and 129

Level: medium

42.	Which of the following is NOT a sub-process associated with risk management?

a) risk identification

b) risk measurement

c) qualitative risk analysis

d) quantitative risk analysis

e) risk response planning

Answer: b

Response: See pages 127 and 128

Level: medium

43. 	Which of the following is NOT true regarding top-down budgeting?

a) It is based on the collective judgments of top and middle managers.

b) Overall project costs are estimated by top and middle managers and then passed on

to the next lower level.

c) The overall budget cost is generally not very accurate.

d) Overlooking small but important tasks can lead to a serious budgetary problem.

e) All of the above are true concerning top-down budgeting.

Answer: c

Response: See pages 110 and 111

Level: medium

44. 	Which of the following is NOT true regarding bottom-up budgeting?

a) The method tends to be inaccurate in the detailed tasks.

b) The WBS is used to identify the elemental tasks.

c) It is rarely used.

d) It is a good managerial training technique.

e) All of the above are true concerning top-down budgeting.

Answer: a

Response: See page 111

Level: medium

45.	A task is expected to take 20 hours of labor at $25 per hour.  The required material cost is $500 and the organization charges 30% of direct labor for overhead.  The total task cost is:

a) $500

b) $1,150

c) $1,250

d) $1,300

e) $1,500

Answer: b

Response: See page 112

Level: medium

46. 	There is a 30 percent chance that a new product development project will result in sales of $500,000 and a 70 percent chance that the project will result in sales of $100,000.  What is the expected value of this project?

a) $220,000

b) $240,000

c) $300,000

d) $320,000

e) $340,000

Answer: a

Response: See page 130

Level: medium

# Short Answer

47. 	Define Top-down and Bottom-Up budgeting.

Response: See pages 110 and 111

48. 	List the steps in performing FMEA.

Response: See pages 128 and 129

49. 	Define the term learning rate.

Response: See pages 118 and 119

50. 	Risk management includes what three areas?

Response: See page 127

51. 	What is the Game Theory approach?

Response: See page 130

52. 	Explain how you would use the shape of a project’s life cycle to resolve budget conflicts between a superior and subordinate.

Response: See pages 112 and 113

53. 	Briefly contrast the three different perspectives cost can be viewed from.

Response:  See page 110

54. 	Contrast activity versus program budgeting.

Response: See page 116

55. 	Briefly explain how learning curves can help improve the cost estimating process.

Response: See pages 117 to 120

56. 	Explain how budget uncertainly changes as the project progresses.

Response: See pages 124 and 125

57.	What are the key elements of contingency planning?

Response: See page 137