Chapter 5: Scheduling the Project

###### True/False

1. 	When it was originally developed, PERT used certain (deterministic) methods to estimate activity duration.

Answer: False

Response: See page 146

Level: medium

2. 	AON and AOA networks can both be used to depict any project network.

Answer: True

Response: See page 147

Level: medium

3. 	The shortest time to complete a network is equal to the duration of the longest path through the network.

Answer: True

Response: See page 150

Level: medium

4. 	Critical path tasks always have zero slack.

Answer: True

Response: See page 151

Level: medium

5. 	To manage a project successfully, the project manager need only pay close attention to tasks on the critical path.

Answer: False

Response: See page 152

Level: medium

6. 	“Merger” is a term used to describe the situation in which two or more paths in a network join together.

Answer” True

Response: See page 166

Level: easy

7. 	If task duration estimates are carefully made, the project manager needs to only examine the critical path when conducting a risk analysis.

Answer: False

Response: See page 157

Level: medium

8. 	The actual project duration will be known with certainty after the project is completed.

Answer: True

Response: See page 172

Level: medium

9. 	Milestones on a Gantt chart are tasks with a duration of zero.

Answer: True

Response: See pages 173 to 177

Level: medium

10. 	It is easiest to see lead and lag time in a project task on a PERT/CPM networks.

Answer: False

Response: See page 178

Level: medium

11. 	A start-to-finish linkage is the most common way of linking to successive task.

Answer: False

Response: See page 178

Level: medium

12. 	The formula for the expected time of an activity in a network assumes that the optimistic, pessimistic, and most likely time estimates have a Beta distribution.

Answer: True

Response: See page 155

Level: medium

13. 	A project schedule is a project action plan converted into a timetable.

Answer: True

Response: See page 145

Level: medium

14. 	A Gantt chart can NOT depict a critical path, only a PERT/CPM chart can.

Answer: False

Response: See page 145

Level: medium

15. 	The difference between the LST and EST is called slack.

Answer: True

Response: See page 151

Level: medium

16. 	A disadvantage of Gantt charts is that they are hard to draw.

Answer: False

Response: See page 173

Level: medium

17. 	The difference between LST and LFT is called slack.

Answer: False

Response: See page 151

Level: medium

18. 	Standard PERT/CPM networks allow for probabilistic branching.

Answer: False

Response: See page 179

Level: medium

19. 	Technical dependencies are often harder to see on a Gantt chart than on a PERT/CPM network.

Answer: True

Response:  See page 173

Level: medium

20. 	The difference between EST and LFT is called slack.

Answer: False

Response: See page 151

Level: medium

21. 	The difference between LFT and EFT is called slack.

Answer: True

Response: See page 151

Level: medium

22. 	A big advantage of AON networks is that they are easier to draw.

Answer: True

Response: See page 147

Level: medium

23. 	The tasks of project planning, project budgeting, and project scheduling are largely separable from one another.

Answer: False

Response: See page 145

Level: medium

24. 	An event is a series of connected activities.

Answer: False

Response: See page 146

Level: easy

25. 	A disadvantage of using beta distribution to approximate activity times is that it is generally less flexible than the normal distribution.

Answer: False

Response: See page 155

Level: medium

26. 	The simulation approach is generally preferred over the statistical method.

Answer: True

Response: See pages 171 and 172

Level: medium

27. 	Technical dependencies are generally easier to see on a Gantt chart than on PERT/CPM networks.

Answer: False

Response: See page 173

Level: medium

28. 	The start-to-finish linkage is used in situations where is it desirable for two or more activities to finish at the same time.

Answer: False

Response: See page 179

Level: medium

29. 	GERT allows for probabilistic branching from nodes.

Answer: True

Response: See page 179

Level: medium

30. 	Another name for total slack is free slack.

Answer: False

Response: See page 154

Level: medium

Multiple Choice

31. 	What is it a milestone?

### a) a significant event in the project

b) a mark on a chart that depicts project progress

c) an activity on the critical path

d) an activity with an uncertain completion time

e) all of the above

Answer: a

Response: See page 177

Level: medium

32. 	What is project slack?

a) The amount of time a non-critical task can be delayed without making the project

late.

b) The amount of time the critical path of a project can be delayed without making the

project late.

c) The amount of time an activity on the critical path can be delayed without making the

project late.

d) The difference between how long the project would take if all tasks were completed

based on their pessimistic versus optimistic time estimates.

### e) None of the above.

Answer: b

Response: See page 152

Level: medium

33. 	For which purpose is simulation NOT used with regard to project scheduling?

### a) to overcome the limitations associated with statistical techniques used to develop

### probability of completion time estimates

b) to investigate the range of project completion times

c) to investigate the distribution of project completion times

d) to verify the accuracy of the optimistic, pessimistic and most likely time estimates

e) all of the above

Answer: d

Response: See page 172

Level: medium

34. 	Technical dependencies on a project plan are easiest to see on a:

### a) Gantt chart

b) GERT chart

c) PERT/CPM chart

d) Work Breakdown Structure

e) Linear Responsibility Chart

Answer: c

Response: See page 173

Level: medium

35. 	PERT was originally used for what type of project?

### a) construction

b) R & D

c) military

d) computer software development

e) advertising

Answer: c

Response: See page 146

Level: medium

36. 	Which of the following is NOT an element of the Gantt chart?

### a) actual progress

b) variance of the critical path

c) the current date

d) scheduled milestones

e) all of the above are elements

Answer: b

Response: See pages 173 to 177

Level: medium

37. 	Which of the following is typically used as the best estimate of task duration?

### a) expected time

b) pessimistic time

c) optimistic time

d) most likely time

e) none of the above

Answer: a

Response: See page 155

Level: medium

38. 	Which of the following terms is most closely associated with a task required by the project?

a) activity

b) event

c) milestone

d) network

e) path

Answer: a

Response: See page 146

Level: easy

39. 	What is the expected time to complete a task with an optimistic, most likely, and pessimistic times of 3, 4, and 7 days respectively?

a) 3

b) 4

c) 4.3

d) 4.7

e) 7

Answer: c

Response: See page 155

Level: medium

40. 	What is the standard deviation of a task with optimistic, most likely, and pessimistic times of 3, 4, and 7 days respectively assuming the estimates were made at the 99% plus level?

a) .444

b) .667

c) 1.212

d) 1.469

e) 1.540

Answer: b

Response: See page 155

Level: medium

41. 	The amount of time a noncritical task can be delayed without delaying the project is called?

a) surplus

b) flop

c) slack

d) critical time

e) safety

Answer: c

Response: See page 151

Level: medium

42. 	Slack is calculated as?

a) LFT - EST

b) LFT - LST

c) LST - LFT

d) LFT - EFT

e) EFT - EST

Answer: d

Response: See page 151

Level: medium

43. 	Which of the following linkages is used to start two or more activities at the same time?

a) finish-to-start

b) start-to-start

c) finish-to-finish

d) start-to-finish

e) They can all be used to start two or more activities at the same time.

Answer: b

Response: See page 178

Level: easy

44. 	Which of the following is an extension to PERT/CPM?

a) CERT

b) FMEA

c) Gantt Charts

d) GERT

e) network diagrams

Answer: d

Response: See page 179

Level: medium

45. 	An identifiable state resulting from the completion of one or more activities is called?

a) an event

b) an activity

c) a milestone

d) a path

e) the critical path

Answer: a

Response: See page 146

Level: medium

###### Short Answer

46. 	Define the term Critical Path.

Response: See page 146

47. 	What is activity slack?

Response: See page 151

48. 	What is a Gantt chart?

Response: See page 173

49. 	What are the four methods of linking steps in a project using precedence diagramming?

Response: See pages 178 and 179

50. 	Contrast “total slack” and “free slack”

Response: See pages 151 and 152

51. 	Contrast the traditional statistical approach to calculating the probability of completing a project by a specified time with the simulation approach.

Response: See pages 167 to 172

52. 	What are some of the ways that GERT extends PERT/CPM?

Response: See page 179

53. 	What assumptions are made about the probabilities of the optimistic and pessimistic times in the standard formula for calculating the variance of a particular activity?  Explain how the formula can be modified to accommodate different assumptions.

Response: See page 155

54. 	Explain why the term “critical path” has less meaning in cases where the activity times are not known with certainty.

Response: See pages 157 and 172

55. 	What is a merger and what problems do mergers create?

Response: See pages 166 and 167