Chapter 6: Allocating Resources to the Project

###### True/False

1. 	The amount of resources a project can use depends in part on the timing of the allocation.

Answer: True

Response: See page 190

Level: medium

2. 	Projects often compete with each other for the same resources.

Answer: True

Response: See page 190

Level: easy

3. 	For resources that are consumed when used, the problem is which project gets to use the resource first and which must wait.

Answer: False

Response: See page 190

Level: medium

4. 	Trade-offs must be made in order to optimize the use of limited resources.

Answer: True

Response: See page 190

Level: medium

5. 	If resources were not scarce, the resource allocation problem would be concerned solely with profit maximization.

Answer: True

Response: See page 191

Level: medium

6. 	If resources were not scarce, the resource allocation problem would be concerned solely with cost minimization.

Answer: False

Response: See page 191

Level: difficult

7. 	A project that must be completed by a fixed time is referred to as resource constrained.

Answer: False

Response: See page 191

Level: medium

8. 	All projects are carried out under conditions of uncertainty.

Answer: True

Response: See page 191

Level: medium

9. 	All tasks can be crashed to some extent.

Answer: False

Response: See page 192

Level: medium

10. 	The time to complete a task with normal or standard-practice resource usage is referred to as the crash duration.

Answer: False

Response: See pages 191 and 192

Level: medium

11. 	When crashing a task, the usual assumption is that a task is crashed the full amount or none at all.

Answer: False

Response: See page 192

Level: medium

12. 	Often it is beneficial to crash activities NOT on the critical path.

Answer: False

Response: See page 192

Level: medium

13. 	It is considered good management to crash the least costly activities before the more costly ones.

Answer: True

Response: See page 192

Level: medium

14. 	The CPM method cannot be used when task durations are probabilistic.

Answer: False

Response: See page 195

Level: medium

15. 	The variance of the normal time can be quite different from the variance of the crash time.

Answer: True

Response: See page 195

Level: medium

16. 	Because of the human judgment required, spreadsheets typically offer little in terms of facilitating the task of crashing a project.

Answer: False

Response: See page 197

Level: medium

17. 	Fast-tracking a project is used primarily in the pharmaceutical industry.

Answer: False

Response: See page 202

Level: medium

18. 	When the work is routine, fast-tracking rarely causes serious problems.

Answer: True

Response: See page 202

Level: medium

19. 	Resource loading refers to the amounts of specific resources that are scheduled for use on specific activities or projects at specific times.

Answer: False

Response: See page 202

Level: medium

20. 	Resource loading refers to the amounts of specific resources that are scheduled for use on specific activities or projects at specific times.

Answer: True

Response: See page 202

Level: easy

21. 	One limitation of MSP is that all resources must share the same availability calendar.

Answer: False

Response: See page 204

Level: medium

22. 	MSP allows the PM to create an individual availability calendar for each resource on the project

Answer: True

Response: See page 204

Level: medium

23. 	A task’s duration is a function of both the amount of labor required to complete the task as well as the calendar time required to complete it.

Answer: True

Response: See page 210

Level: medium

24. 	A resource allocation decision may be intended to avoid a future problem rather than correct a current problem.

Answer: True

Response: See page 212

Level: medium

25. 	In general, steady state demand for human resources is highly desirable.

Answer: True

Response: See page 212

Level: medium

26. 	Pools of like resources from which labor can be added temporarily to projects tend to increase costs for the firm as a whole.

Answer: False

Response: See page 212

Level: medium

27. 	Pools of like workers are most useful when labor is subdivided into highly specialized subtasks.

Answer: False

Response: See page 212

Level: difficult

28. 	Applying “line balancing” techniques to balance the capacity of a project typically yields significant benefits.

Answer: False

Response: See page 216

Level: medium

29. 	A limitation associated with traditional approaches to project management is that the dependency between resources and tasks is often ignored.

Answer: True

Response: See page 230

Level: medium

30. 	The as late as possible priority rule is considered the standard scheduling rule.

Answer: False

Response: See page 217

Level: medium

Multiple Choice

31.  	Allocating specific, limited resources to specific activities is called

### a) resource allocation

b) resource leveling

c) resource tracking

d) expediting a project

e) crashing a project

Answer: a

Response: See page 190

Level: easy

32. 	The primary cause of concern in resource allocation is

### a) labor cost

b) resource scarcity

c) lack of solution methodologies

d) parallel activities

e) equipment downtime

Answer: b

Response: See page 191

Level: medium

33. 	A project that cannot go over budget is considered

### a) time constrained

b) schedule constrained

c) resource constrained

d) performance constrained

e) critically constrained

Answer: c

Response: See page 191

Level: medium

34. 	The task duration with standard-practice resource usage is referred to as the

### a) expected task duration

b) nominal task duration

c) crash duration

d) normal task duration

e) planned task duration

Answer: d

Response: See page 191

Level: medium

35. 	A task has a normal duration of 9 days and a crash duration of 7 days.  Its normal cost is $40 and its crash cost is $100.  What is the crash cost per day?

### a) $140

b) $70

c) $50

d) $40

e) $30

Answer: e

Response: See page 192

Level: medium

36. 	Which of the following is NOT associated with the spreadsheet model used to solve the crashing problem?

### a) Minimize the total cost of completing the project.

b) Minimize the number of activities crashed.

c) Complete the project by a specified time.

d) Maintain the precedence relationships specified in the network diagram.

e) Bounds on the amount each task can be crashed.

Answer: b

Response: See pages 197 to 202

Level: medium

37. 	Starting the building phase before the design and planning phases is called

### a) operations overlapping

b) concurrent engineering

c) fast-tracking

d) concurrent construction

e) construction overlapping

Answer: c

Response: See page 202

Level: medium

38. 	Which of the following priority rules makes resources available so that activities start on their LSTs whenever possible without increasing the project’s duration?

### a) as soon as possible

b) as late as possible

c) shortest task duration first

d) minimum slack first

e) most critical successor

Answer: b

Response: See page 217

Level: medium

39.	Which of the following rules maximizes the number of tasks that can be completed by a system in a given period of time?

### a) as soon as possible

b) as late as possible

c) shortest task duration first

d) minimum slack first

e) most critical successor

Answer: c

Response: See page 218

Level: medium

40. 	Several projects can be linked together with

### a) virtual activities

b) nominal activities

c) pseudoactivities

d) ER links

e) critical chains

Answer: c

Response: See page 218

Level: medium

41.  	Which of the following is NOT commonly used to help select a priority rule?

### a) schedule slippage

b) resource utilization

c) in-process inventory

d) cost overruns

e) all of the above are used

Answer: d

Response: See page 220

Level: medium

42.   	Which of the following is a measure of the amount by which a project is delayed by application of a leveling rule?

### a) schedule inflation

b) schedule progression

c) schedule efficacy

d) schedule efficiency

e) schedule slippage

Answer: e

Response: See page 220

Level: medium

43.	According to research, the best overall priority rule is

### a) as soon as possible

b) as late as possible

c) shortest task duration first

d) minimum slack first

e) most critical successor

Answer: d

Response: See page 220

Level: medium

44.	The practice of assigning project team members to multiple projects is called

### a) concurrent engineering

b) parallel activities

c) fast-tracking

d) project crashing

e) multitasking

Answer: e

Response: See page 226

Level: medium

45.	The safety time added to chains other than the critical chain is called

### a) feeding buffer

b) project buffer

c) path buffer

d) critical buffer

e) team buffer

Answer: a

Response: See page 230

Level: medium

###### Short Answer

46. 	Explain how you would use a spreadsheet to crash a project.  Specifically discuss what the objective is and what types of constraints would be needed.

Response: See pages 197 to 201

47. 	What is fast-tracking a project?

Response: See page 202

48. 	What is resource loading?

Response: See pages 202 to 208

49. 	What is resource leveling?  Why is it needed?

Response: See pages 209 - 215

50. 	List and briefly explain five priority rules used to assign preference to activities when allocating scarce resources.

Response: See pages 217 – 218

51. 	Explain how you would choose a priority rule.

Response: See page 220

52. 	Explain how the commonly made assumption of known activity times can lead to unrealistic project deadlines.

Response: See page 225

53. 	What is the student syndrome?  In what ways can it create problems for a project?

Response: See pages 225 to 226

54. 	What is the effect of not reporting the early completion of project activities?

Response: See page 226

55. 	Briefly overview Goldratt’s common chain of events.

Response: See page 229