Chapter 7: Monitoring and Controlling the Project

###### True/False

1. 	Project monitoring and control can be thought of as opposite sides of project selection and planning.

Answer: True

Response: See page 238

Level: medium

2. 	Control is the collection, recording, and reporting of project information.

Answer: False

Response: See page 238

Level: medium

3. 	The purpose of control is to ensure that all interested parties have the information they need.

Answer: False

Response: See page 238

Level: medium

4. 	The most important use of data gathered from monitoring is learning from mistakes.

Answer: False

Response: See page 238

Level: medium

5. 	The most important use of data gathered from monitoring is control.

Answer: True

Response: See page 238

Level: medium

6. 	The plan-monitor-control cycle constitutes a “closed loop” process.

Answer: True

Response: See page 239

Level: medium

7. 	It is often the case with particularly challenging or uncertain projects that the planning-monitoring-controlling effort is minimized so that the “real work” can be done.

Answer: True

Response: See page 239

Level: easy

8. 	In order to manage for overall project success, control should be exercised at a very high and aggregated level and not get bogged down with unnecessary details.

Answer: False

Response: See page 240

Level: medium

9. 	In order to manage for overall project success, control must be exercised at the detailed work level for each aspect of project performance.

Answer: True

Response: See page 240

Level: medium

10. 	Mechanisms to gather and store data rarely need to be designed.

Answer: False

Response: See page 240

Level: medium

11. 	One way of linking planning and control is to monitor project progress on the MSP Gantt chart.

Answer: True

Response: See page 240

Level: medium

12. 	Too often, intensity of activity is measured instead of results.

Answer: True

Response: See page 240

Level: medium

13. 	A common mistake is to focus too much on results and not enough on the intensity of activity.

Answer: False

Response: See page 240

Level: medium

14. 	Raw numbers represent a simple tally of the occurrence of an event.

Answer: False

Response: See page 241

Level: medium

15. 	Statistical quality control techniques can be helpful for determining what size variances are significant.

Answer: True

Response: See page 242

Level: medium

16. 	An important use of data analysis is to identify who to properly blame for poor project performance.

Answer: False

Response: See page 243

Level: medium

17.	Frequent blame is considered a good motivational tool to keep project team members on track.

Answer: False

Response: See page 243

Level: medium

18. 	Everyone associated with the project should receive the same information.

Answer: False

Response: See page 243

Level: medium

19. 	In general, it is preferable to have periodic reports.

Answer: False

Response: See page 243

Level: medium

20. 	An overload of reporting is just as dangerous as underreporting.

Answer: True

Response: See page 244

Level: medium

21. 	Exception reports are prepared to disseminate the results of a special study.

Answer: False

Response: See page 244

Level: medium

22. 	Exception reports are primarily intended for unexpected situations.

Answer: True

Response: See page 244

Level: medium

23. 	Project review meetings are always important.

Answer: True

Response: See page 245

Level: medium

24. 	Weekly progress report meetings should be rarely held.

Answer: True

Response: See page 245

Level: medium

25. 	Remarks should be directly attributed to individuals in the meeting minutes.

Answer: False

Response: See page 246

Level: medium

26. 	To maximize efficiency, project team meetings should follow Robert’s Rules of Order.

Answer: False

Response: See page 246

Level: medium

27. 	Earned value is a measure for overall project progress in terms of performance, budget and schedule.

Answer: True

Response: See page 247

Level: medium

28. 	Lower expenditures than expected at a given point in time is always good.

Answer: False

Response: See page 247

Level: medium

29. 	According to the text, there is no satisfactory way to measure accurately the percent of completion of most tasks.

Answer: True

Response: See page 248

Level: medium

30. 	The percentage of an activity’s budget actually spent by a given date is typically a good indicator of the percent of that activity’s completion.

Answer: False

Response: See page 248

Level: medium

Multiple Choice

31. 	Which of the following is NOT an objective mentioned in the text for data gathered from monitoring?

### a) promoting team members

b) keeping management informed

c) auditing

d) learning from mistakes

e) control

Answer: a

Response: See page 238

Level: medium

32. 	The plan-monitor-control cycle is best described as

### a) an open loop process

b) a closed-loop process

c) an ad-hoc process

d) an informal process

e) a hierarchical process

Answer: b

Response: See page 239

Level: medium

33. 	Which of the following is used when it is especially difficult to find a direct measure of a variable?

### a) frequency count

b) raw numbers

c) surrogates

d) subjective numeric ratings

e) verbal characterizations

Answer: c

Response: See page 241

Level: medium

34. 	Which of the following is most closely associated with ordinal rankings?

### a) frequency counts

b) raw numbers

c) indicators

d) subjective numeric rankings

e) surrogates

Answer: d

Response: See page 241

Level: medium

35. 	Which of the following is NOT a distinct type of report?

### a) exception

b) special analysis

c) critical incident

d) routine

e) all of the above are distinct types of reports

Answer: c

Response: See page 244

Level: medium

36. 	Which of the following was NOT listed in the text as a convention for estimating task progress?

### a) 50% when task is started and another 50% when it is completed

b) 100 percent when task is completed and 0% before that

c) using the ratio of cost expended to total cost budgeted

d) using the ratio of time expended to the total time scheduled

e) all of the above were mentioned

Answer: e

Response: See page 248

Level: medium

37. 	The cost/spending variance is calculated as

### a) AC - EV

b) EV- PV

c) PV - EV

d) AC - PV

e) EV - AC

Answer: e

Response: See page 249

Level: medium

38. 	Estimated (remaining cost) to completion (ETC) is calculated as

### a) (BAC – EV)/CPI

b) (BAC – EV)/SPI

c) (BAC + EV)/CPI

d) (BAC + EV)/SPI

e) (BAC – AC)/CPI

Answer: a

Response: See page 249

Level: medium

39. 	In earned value analysis

### a) it is desirable to have negative variances for both schedule and spending.

b) it is desirable to have positive variances for both schedule and spending.

c) the schedule variance should be positive and the spending variance negative.

d) the schedule variance should be negative and the spending variance positive.

e) ideally both variances would equal zero.

Answer: b

Response: See page 249

Level: medium

40. 	Which of the following is NOT a primary mechanism by which the PM exerts control?

### a) reviews

b) personnel assignments

c) audit reports

d) resource allocation

e) all of the above are mechanisms by which the PM exerts control

Answer: c

Response: See page 257

Level: medium

41. 	Which of the following is NOT a component of a control system?

### a) effector

b) sensor

c) decision maker

d) leveler

e) standard

Answer: d

Response: See page 258

Level: difficult

42. 	Which of the following is NOT a tool used to aid the PM in project control?

### a) variance analysis

b) trend projections

c) earned value analysis

d) control charts

e) discounted cash flow analysis

Answer: e

Response: See page 262

Level: medium

43. 	The most common source of changes to a project based on the natural tendency of the client and project team members to improve the project’s output is called

### a) scope creep

b) projectitis

c) multitasking

d) dynamic scoping

e) unfreezing

Answer: a

Response: See page 263

Level: medium

44. 	Which of the following is NOT true regarding meetings?

### a) A written agenda should be distributed in advance of the meeting.

b) The agenda should announce pre-set starting and stopping times.

c) It is appropriate to be flexible and extend a meeting’s stopping time if issues come up

that were not on the agenda.

d) Don’t penalize those who show up on time by making them wait for those who are

late.

e) All of the above are true.

Answer: c

Response: See page 245

Level: medium

45. 	The first step in setting up a monitoring system is to:

### a) identify personnel

b) identify all project milestones

c) identify key factors to be controlled

d) identify reports required

e) develop a change request form

Answer: c

Response: See page 240

Level: medium

###### Short Answer

46. 	Explain why project monitoring and control can be thought to be opposite sides of project selection and planning.

Response: See page 238

47. 	List and briefly describe the five data formats discussed in the text.

Response: See page 241

48. 	List and briefly describe the three distinct types of reports.

Response: See page 244

49. 	List the benefits of reports beyond the purpose of control.

Response: See page 244

50. 	What actions can you take to help avoid the common problems associated with meetings?

Response: See pages 245 and 246

51. 	Define the terms monitoring and control.

Response: See page 238

52. 	What is the best way to estimate percent completion of activities for finding earned value?

Response: See page 248

53. 	What is earned value?

Response: See pages 247 and 248

54. 	Explain how an earned value chart can be used to help monitor and control a project.

Response: See pages 248 and 249

55. 	Why is control difficult?

Response: See page 254