Chapter 8: Evaluating and Terminating the Project

###### True/False

1. 	Project evaluation should only appraise the progress and performance of a project relative to the project’s initial plan and not relative to a revised plan.

Answer: False

Response: See pages 272 and 273

Level: medium

2. 	Project evaluation appraises the performance of a project relative to the project’s initial or revised plan.

Answer: True

Response: See pages 262 and 273

Level: easy

3. 	Project evaluation should be limited to an after-the fact analysis.

Answer: False

Response: See page 273

Level: medium

4. 	Project evaluation should NOT be limited to an after-the-fact analysis.

Answer: True

Response: See page 273

Level: easy

5. 	The primary purpose of project evaluation is to given feedback to senior management for decision and control purposes.

Answer: True

Response: See page 273

Level: medium

6. 	The original criteria for selecting and funding the project are largely irrelevant for project evaluation.

Answer: False

Response: See page 273

Level: medium

7. 	According to research, future potential is an important dimension of project success.

Answer: True

Response: See page 273

Level: difficult

8. 	Measuring the project’s performance against a planned budget and schedule is generally straightforward.

Answer: True

Response: See page 274

Level: medium

9. 	Measuring a project’s success on budget, schedule, and performance is typically more complicated than measuring revenues or qualitative, subjective factors.

Answer: False

Response: See page 274

Level: medium

10. 	The formal audit is a special type of project evaluation.

Answer: True

Response: See page 275

Level: medium

11. 	The project audit is typically broader than the traditional management audit.

Answer: True

Response: See page 275

Level: medium

12. 	The project audit focuses its attention on the organization’s management systems and operations.

Answer: False

Response: See page 275

Level: medium

13. 	The timing of an audit depends on the purpose of the audit.

Answer: True

Response: See page 275

Level: easy

14. 	Early project audits usually focus on the project’s budget and schedule.

Answer: False

Response: See page 275

Level: medium

15. 	Later project audits are typically of less value to the project team and of more interest to general management.

Answer: True

Response: See page 275

Level: medium

16. 	The general audit is usually performed by a person or team with special technical skills.

Answer: False

Response: See page 275

Level: medium

17. 	Project audits are typically very useful in the initiation project state.

Answer: True

Response: See page 276

Level: medium

18. 	Project audits are typically very useful at the master schedule project state.

Answer: False

Response: See page 276

Level: medium

19. 	The use of forms to collect data during a project audit is generally considered NOT to be good management practice since they can limit the audit team’s flexibility.

Answer: False

Response: See page 276

Level: medium

20. 	The Request for Proposal may contain valuable information for a project audit.

Answer: True

Response: See page 276

Level: medium

21. 	A discussion of the potential for project failure and monetary loss should be included in the audit report.

Answer: True

Response: See page 279

Level: medium

22. 	The way project termination is managed can impact the project’s success.

Answer: True

Response: See page 280

Level: medium

23. 	Poor up-front planning is a fundamental reason for project failure.

Answer: True

Response: See page 281

Level: easy

24. 	Naming the wrong project manager is a fundamental reason for project failure.

Answer: True

Response: See page 281

Level: medium

25. 	Termination-by-integration occurs when an “in-house” project is successfully completed and institutionalized as a new, formal part of the organization.

Answer: False

Response: See page 281

Level: medium

26. 	It is best for the project manager and project team to make the termination decision.

Answer: False

Response: See page 282

Level: medium

27. 	Project termination should be treated as a mechanistic process.

Answer: False

Response: See page 282

Level: medium

28. 	It is generally advisable to have the project manager serve as the termination manager.

Answer: False

Response: See page 282

Level: medium

29. 	The project final report is a history of the project.

Answer: True

Response: See page 283

Level: medium

30.  	Organizational structure should be addressed in the project final report.

Answer: True

Response: See page 284

Level: medium

Multiple Choice

31.  	Which of the following is concerned with appraising a project relative to its initial or revised plan?

### a) project evaluation

b) project termination

c) project monitoring

d) project control

e) project planning

Answer: a

Response: See page 272

Level: medium

32. 	According to research, which of the following is NOT an important dimension of project success?

### a) project efficiency

b) project team cohesiveness

c) customer impact/satisfaction

d) business/direct success

e) future potential

Answer: b

Response: See page 273

Level: difficult

33.  	According to the text, which of the following is NOT an item to consider for project evaluation report recommendations?

### a) communication with the client and senior management

b) locating opportunities for technological advances

c) locating opportunities to crash the project

d) improving the project-management process

e) improving the organization’s used of projects

Answer: c

Response: See page 274

Level: difficult

34. 	According to the text, which of the following is NOT a common level of depth for an audit.

### a) the general audit

b) the detailed audit

c) technical audit

d) aggregate audit

e) All of the above are common levels of depth for an audit.

Answer: d

Response: See page 275

Level: medium

35. 	Which of the following audits is typically performed by a person or team with special technical skills?

### a) the general audit

b) the detailed audit

c) the aggregate audit

d) the quality audit

e) the technical audit

Answer: e

Response: See page 275

Level: easy

36.  	In which of the following project states is the value of the project audit of rather limited usefulness?

### a) master schedule

b) initiation

c) feasibility study

d) preliminary plan/schedule budget

e) The value of the project audit is very useful in all of the above project states.

Answer: a

Response: See page 276

Level: difficult

37. 	Which of the following is NOT a typical step in a project audit?

### a) familiarize the audit team with the requirements of the project

b) collect benchmark data from other similar projects

c) audit the project on-site

d) write-up the audit report in the required format

e) distribute the report

Answer: b

Response: See page 276

Level: medium

38. 	Which of the following was NOT mentioned in the text as a valuable source of information for a project audit?

### a) the project’s Request for Proposal

b) minutes from the project selection committee

c) benchmark data from other similar projects

d) minutes of senior management committees that initiated the project

e) All of the above were mentioned in the text as valuable sources of information for a

project audit.

Answer: c

Response: See page 276

Level: medium

39.  	Which of the following was NOT a major section listed in the text for the audit report?

### a) current status

b) future project status

c) critical management issues

d) financial analysis

e) risk analysis and risk management

Answer: d

Response: See pages 278 and 279

Level: medium

40.  	Which of the following is NOT a type of project termination mentioned in the text?

### a) project extinction

b) termination-by-addition

c) termination-by-integration

d) termination-by-starvation

e) termination-by-elimination

Answer: e

Response: See pages 281 an 282

Level: medium

41.  	Which of the following is most closely associated with the output of a project becoming a standard part of the operating systems of the sponsoring firm or client?

### a) termination-by-addition

b) termination-by-extinction

c) termination-by-integration

d) termination-by-starvation

e) termination-by-elimination

Answer: c

Response: See pages 281 and 282

Level: medium

42.  	Which of the following is NOT a main duty of the termination manager?

a) Oversee the closing of the project’s books

b) Complete the project final report

c) Ascertain any product support requirements

d) Ensure completion of work

e) Ensure that documentation is complete

Answer: b

Response: See page 283

Level: difficult

43.  	Which of the following is typically NOT included in the project final report?

### a) administrative performance

b) project performance

c) organizational structure

d) project teamwork

e) risk analysis and risk management

Answer: e

Response: See pages 284

Level: medium

44.  	Which of the following is NOT part of a termination project?

### a) on-site audit

b) personnel reports

c) reassignment plan

d) final payments

e) supplier notifications

Answer: a

Response: See page 282

Level: medium

45.  	A data collection form to support a project audit would include data from all the following categories except

### a) financial data

b) technical data

c) managerial data

d) risk management data

e) All of the above categories would be included in the data collection form.

Answer: d

Response: See page 277

Level: medium

###### Short Answer

46. 	What criteria should be included in evaluating a project?

Response: See pages 273 and 274

47. 	List several key items to consider for project evaluation report recommendations.

Response: See page 273

48. 	Briefly describe and contrast general audits, detailed audits, and technical audits.

Response: See page 275

49. 	Briefly describe the value of project audits for alternative project states.

Response: See page 276

50. 	What are the steps in a project audit?

Response: See page 276

51. 	What content should be included in the audit report?

Response: See pages 278 and 279

52. 	Briefly describe the four types of project termination.

Response: See pages 281 and 282

53. 	Contrast termination-by-addition with termination-by-integration.

Response: See pages 281 and 282

54. 	What are the main duties of the termination manager?

Response: See page 283

55. 	What issues should be addressed in the project final report?

Response: See pages 283 and 284