## Slide 1: Resource and Task Assignments
Lesson 3

## Slide 2: Skills Matrix
Skills | Matrix Skill
Assign work resources to tasks | Make individual resource assignments Assign multiple resources simultaneously
Add more resource assignments to tasks | Add resources to a task Use a Smart Tag to assign resources to tasks

## Slide 3: Skills Matrix
Skills | Matrix Skill
Assign material resources to tasks | Assign a material resource to a task
Assign cost resources to tasks | Assign a cost resource to a task

## Slide 4: Software Orientation
Assign Resources dialog box activated using the Resources pane of the Project Guide
Microsoft Project’s Assign Resources Dialog Box

## Slide 5: Software Orientation
Assign Resources dialog box activated using the Assign Resources button on the Standard toolbar
Note the Units column in this dialog box—used to assign material resources
Microsoft Project’s Assign Resources Dialog Box (cont.)

## Slide 6: Assigning Work Resources to Tasks
The Assign Resources dialog box is activated
Click Resources on the Project Guide
Click Assign people and equipment to tasks
Click Assign resources
Make Individual Resource Assignments

## Slide 7: Assigning Work Resources to Tasks
In the Assign Resources pane…
…click the Assign Resources link…
…to activate the Assign Resources dialog box
Make Individual Resource Assignments (cont.)

## Slide 8: Assigning Work Resources to Tasks
Select the name of the desired resource in the Assign Resources dialog box
Click the name of the desired task
Click the Assign button in the Assign Resources dialog box
Make Individual Resource Assignments (cont.)

## Slide 9: Assigning Work Resources to Tasks
Select the name of the desired task
Select the name of the desired resource
Click the Assign button
Make Individual Resource Assignments (cont.)

## Slide 10: Assigning Work Resources to Tasks
Resource name appears next to task bar
Check mark shows resource has been assigned to task
Cost of resource assignment for selected task
Resource assignment data is added to Review Information section
Make Individual Resource Assignments (cont.)

## Slide 11: Assigning Multiple Resources
Select the names of the desired resources in the Assign Resources dialog box
Click the name of the desired task
Click the Assign button in the Assign Resources dialog box
Assign Multiple Resources Simultaneously

## Slide 12: Assigning Multiple Resources
Resource name appears next to task bar
Check mark shows resources have been assigned to task
Resource assignment data is added to Review Information section
Cost of resource assignment for selected task
Task to which resources are assigned
Assign Multiple Resources Simultaneously (cont.)

## Slide 13: Adding More Resource Assignments
Add Resources to a Task
When you assign a resource to a task, the result is work
Work is the total amount of effort a resource or resources will spend to complete a task
Project calculates work using a scheduling formula
Duration  Units = Work

## Slide 14: Adding More Resource Assignments
Add Resources to a Task (cont.)
With effort-driven scheduling, the duration of a task increases or decreases as you remove or assign resources to a task
  Work does not change
  Project can adjust successor tasks based on new task durations

## Slide 15: Adding More Resource Assignments
Add Resources to a Task (cont.)
You have already started to define resource assignments for tasks in your plan
  You now want to assign additional resources to one or more of these tasks
  Effort-driven scheduling causes duration to be adjusted when you add resources

## Slide 16: Adding More Resource Assignments
Add Resources to a Task (cont.)
Select the name(s) of the desired resource(s) in the Assign Resources dialog box
Click the name of the desired task
Click the Assign button in the Assign Resources dialog box

## Slide 17: Adding More Resource Assignments
Add Resources to a Task (cont.)
Task duration decreases as additional resources are assigned
Change Highlighting shows changes
Duration and work changes can be monitored here

## Slide 18: Adding More Resource Assignments
A Smart Tag can be used to assign additional resources to a task
Provides options for adjusting work or duration
  A Smart Tag is only available until you perform another action!
Use a Smart Tag to Assign Resources to Tasks

## Slide 19: Adding More Resource Assignments
Click the name of the desired task
Select the name(s) of the desired resource(s) in the Assign Resources dialog box
Click the Assign button in the Assign Resources dialog box
Use a Smart Tag to Assign Resources to Tasks (cont.)

## Slide 20: Adding More Resource Assignments
A small triangle appears to indicate that there is a Smart Tag activated for this task
Point to or mouse over the task to activate the Smart Tag indicator
Smart Tag indicator
Triangle indicator
Use a Smart Tag to Assign Resources to Tasks (cont.)

## Slide 21: Adding More Resource Assignments
Click the Smart Tag Actions button
Select the desired option from the Smart Tag list
Smart Tag Actions button
Use a Smart Tag to Assign Resources to Tasks (cont.)

## Slide 22: Adding More Resource Assignments
When you select the second option in the Smart Tag options list, pay careful attention to the “before” and “after” duration and work values
“Before” values
“After” values
Use a Smart Tag to Assign Resources to Tasks (cont.)

## Slide 23: Assigning Material Resources to Tasks
Click the Show/Hide Project Guide button to close the Project Guide
  Provides greater viewing area onscreen
Click the Assign Resources button on the Standard toolbar
Show/Hide Project Guide button
Assign Resources button
Assign a Material Resource to a Task

## Slide 24: Assigning Material Resources to Tasks
Click the name of the desired task
Select the Units field for the desired resource in the Assign Resources dialog box
Key the desired number of units for the selected material resource
Click Assign
Assign a Material Resource to a Task (cont.)

## Slide 25: Assigning Material Resources to Tasks
Material resource label displayed in the units column
Material resource listed next to task bar
Assign a Material Resource to a Task (cont.)

## Slide 26: Assigning Material Resources to Tasks
Two ways to handle cost and consumption of a material resource
  Assign a fixed unit quantity
  Assign a variable rate quantity
Assign a Material Resource to a Task (cont.)

## Slide 27: Assigning Cost Resources to Tasks
Assign a Cost Resource to a Task
Click the Assign Resources button, if necessary
Click the name of the desired task
Select the desired cost resource in the Assign Resources dialog box
Key the cost in the Cost column for the selected cost resource

## Slide 28: Assigning Cost Resources to Tasks
Cost resource assigned
Cost of Cost resource
Cost resource appears next to task bar
Assign a Cost Resource to a Task (cont.)

## Slide 29: Assigning Cost Resources to Tasks
Examples of cost resources
  Travel expenses
  Lodging expenses
  Asset costs
  Other fixed resource costs
Assign a Cost Resource to a Task (cont.)

## Slide 30: Summary
Assign work resources to tasks
Assign more resource assignments to tasks
Assign material resources to tasks
Assign cost resources to tasks
You Learned How to