## Slide 1: Project Plan Tracking – Fundamentals
Lesson 8

## Slide 2: Skills Matrix
Skills | Matrix Skill
Establish a project baseline | Establish a project baseline
Track a project as scheduled | Track a project as scheduled

## Slide 3: Skills Matrix
Skills | Matrix Skill
Enter the completion percentage for a task | Enter the completion percentage for a task
Track timephased actual work | Track timephased actual work

## Slide 4: Skills Matrix
Skills | Matrix Skill
Identify over budget tasks and resources | Identify over budget tasks and resources
Identify time and schedule problems | Reschedule uncompleted work

## Slide 5: Software Orientation
Tasks and subtasks
Scheduled and actual work for task
Scheduled and actual work for task
Scheduled work before timephased actual work is entered
Microsoft Project’s Task Usage View

## Slide 6: Establishing a Project Baseline
Establish a Project Baseline
Click Done
Click Track on the Project Guide
Click the Save a baseline to compare with later versions link
Click the Save Baseline button

## Slide 7: Establishing a Project Baseline
Establish a Project Baseline (cont.)
Click View on the menu bar
Click the Show/Hide Project Guide button
Click More Views
The More Views dialog box is activated

## Slide 8: Establishing a Project Baseline
Establish a Project Baseline (cont.)
Click Apply
Select Task Sheet
Click View
Point to Table: Summary
Click Variance

## Slide 9: Establishing a Project Baseline
Establish a Project Baseline (cont.)
“Scheduled” columns
“Baseline” columns
“Variance” columns

## Slide 10: Establishing a Project Baseline
Baseline — Collection of key values in the project plan
At this point, the Start and Baseline Start and the Finish and Baseline Finish values are identical
Establish a Project Baseline (cont.)

## Slide 11: Establishing a Project Baseline
  No actual work has occurred
  No changes to scheduled work have been made
  After work begins or adjustments are made, differences are displayed in the Variance column
Establish a Project Baseline (cont.)

## Slide 12: Establishing a Project Baseline
Specific values are saved in the baseline
Establish a Project Baseline (cont.)
Task Fields | Start field Finish field Duration field Work and timephased Work fields Cost and timephased Cost fields
Resource Fields | Work and timephased Work fields Cost and timephased Cost fields
Assignment Fields | Start field Finish field Work and timephased Work fields Cost and timephased Cost fields
Timephased fields are task, resource, and assignment values distributed over time

## Slide 13: Establishing a Project Baseline
You should save a baseline when
  You have developed the project plan as much as possible
  You have not started to enter actual values
Establish a Project Baseline (cont.)

## Slide 14: Establishing a Project Baseline
The first phase of a project is planning: developing and communicating the details of a project before work begins
The second phase of a project is tracking: collecting, entering, and analyzing actual project performance data
  These details are called actuals: project work completed and recorded in a Microsoft Project file
Establish a Project Baseline (cont.)

## Slide 15: Establishing a Project Baseline
There are various levels of detail used to track progress, depending on requirements of the
  Project manager
  Stakeholders
  Sponsor (the individual or organization that provides financial support and supports the project team within the larger organization)
Establish a Project Baseline (cont.)

## Slide 16: Establishing a Project Baseline
Levels of tracking
  Record project work as scheduled
  Record each task’s percentage of completion
  Record the actuals
  Track assignment-level work by time period
Establish a Project Baseline (cont.)

## Slide 17: Tracking a Project as Scheduled
Track a Project as Scheduled
Click Gantt Chart
Click View on the menu bar
Click Tools
Point to Tracking
Click Update Project

## Slide 18: Tracking a Project as Scheduled
Track a Project as Scheduled (cont.)
Key February 11, 2008
Select Update work as completed through
Click OK
Select the name of task 5
Click the Scroll to Task button

## Slide 19: Tracking a Project as Scheduled
Track a Project as Scheduled (cont.)
Check mark means task has been completed
Progress bar indicates the portion of the task that has been completed

## Slide 20: Tracking a Project as Scheduled
Track a Project as Scheduled (cont.)
A progress bar in the Gantt Chart view shows how much of each task has been completed
A check mark indicates tasks that have been completed

## Slide 21: Entering the Completion Percentage
Click Track on the Project Guide
Click the Prepare to track the progress of your project link
Expand the table so that the Work and % Work Complete columns are visible
Enter the Completion Percentage for a Task

## Slide 22: Entering the Completion Percentage
Select the Always track by entering the Percent of Work Complete button
Click Done
Click the Incorporate progress information into the project link
Enter the Completion Percentage for a Task (cont.)

## Slide 23: Entering the Completion Percentage
Key or select 100 in the % Work Complete column for task 5
Press Enter
Click Scroll to Task
Enter the Completion Percentage for a Task (cont.)

## Slide 24: Entering the Completion Percentage
Task 5 is 100% complete
Blue shaded boxes indicate values that have changed as a result of the last action performed (Change Highlighting)
Enter the Completion Percentage for a Task (cont.)

## Slide 25: Entering the Completion Percentage
Key or select 50 in the % Work Complete column for task 6
Press Enter
Click Done at the bottom of the Incorporate Progress pane
Enter the Completion Percentage for a Task (cont.)

## Slide 26: Entering the Completion Percentage
There are several ways to record progress as a percentage
  Use the Project Guide
  Use the Tracking Toolbar (ViewToolbars Tracking)
  Use the Update Task dialog box (ToolsTracking Update Tasks)
Enter the Completion Percentage for a Task (cont.)

## Slide 27: Entering the Completion Percentage
When you enter a percentage other than 0% complete
  Project changes the actual start date to match the task’s scheduled start date
  Project also calculates actual duration, remaining duration, actual costs, and so forth
Enter the Completion Percentage for a Task (cont.)

## Slide 28: Tracking Timephased Actual Work
Click the Prepare to track the progress of your project link
Click View on the menu bar
Click Task Usage
Click Always track by entering hours of work done per time period button
Click Done
Track Timephased Actual Work

## Slide 29: Tracking Timephased Actual Work
Click the minus sign (–) next to the name of task 1
Select the name of task 31
Click the Scroll to Task button
Track Timephased Actual Work (cont.)

## Slide 30: Tracking Timephased Actual Work
Work values for task 31
Track Timephased Actual Work (cont.)

## Slide 31: Tracking Timephased Actual Work
Click the yellow cell at the intersection of the Friday, May 2, column and the task 31 Act. Work row
Key 24h
Press Enter
Enter “24h” in this cell
Track Timephased Actual Work (cont.)

## Slide 32: Tracking Timephased Actual Work
Timephased actual work entered for task 31
Project distributes the work among assigned resources and rolls up the values to the summary task
Track Timephased Actual Work (cont.)

## Slide 33: Tracking Timephased Actual Work
Click the Actual Work cell for task 31
Key 24h
Press Enter
Track Timephased Actual Work (cont.)

## Slide 34: Tracking Timephased Actual Work
Click the cell at the intersection of the Tuesday, May 6, column and Jeff Pike’s actual work row for his assignment on task 33
Scroll the view so that all assignments for task 33 are visible
Track Timephased Actual Work (cont.)

## Slide 35: Tracking Timephased Actual Work
Enter the following actual work values
Resource Name | Tuesday’s Actual Work | Wednesday’s Actual Work
Jeff Pike | 1h | 7h
Sound Technician | 1h | 7h
Don Funk | 1h | 7h
musician | 1h | 7h
Track Timephased Actual Work (cont.)

## Slide 36: Tracking Timephased Actual Work
Individual actual work values rolled up to task actual work values
Individual work values entered for resources
Track Timephased Actual Work (cont.)

## Slide 37: Tracking Timephased Actual Work
Entering timephased values may be best if you have
  High-risk tasks
  Tasks that require hourly billing for labor
  Tasks in which stakeholders have a very strong interest
  Short duration tasks for which a variance (a deviation from the schedule or budget) could put the overall project at risk
Track Timephased Actual Work (cont.)

## Slide 38: Tracking Timephased Actual Work
There are various options for collecting actuals
  Collect actuals yourself
  Collect actuals through a formal reporting system
  Use Project’s e-mail-based collaboration features to collect assignment status data
Track Timephased Actual Work (cont.)

## Slide 39: Over Budget Tasks and Resources
Click Project Information
Click Project
Click Statistics
Identify Over Budget Tasks and Resources

## Slide 40: Over Budget Tasks and Resources
Current cost is the sum of the actual and remaining cost values
Baseline cost is the total planned cost of the project when the baseline was saved
Actual cost is the cost that has been incurred so far (after the indicated total work has been completed)
Remaining cost is the difference between the current cost and actual cost
Click Close when finished
Identify Over Budget Tasks and Resources (cont.)

## Slide 41: Over Budget Tasks and Resources
Point to Table: Variance
Click View on the menu bar
Click Cost
Click the Task Name column heading
Identify Over Budget Tasks and Resources (cont.)

## Slide 42: Over Budget Tasks and Resources
Click the Hide Subtasks button on the Formatting toolbar
Click the plus sign (+) next to task 27
Identify Over Budget Tasks and Resources (cont.)

## Slide 43: Over Budget Tasks and Resources
Note that Scene 2 has the greatest variance
Identify Over Budget Tasks and Resources (cont.)

## Slide 44: Over Budget Tasks and Resources
Click the Task Name column heading
Click the plus sign (+) next to task 37
Click the Show Subtasks button
Click Report on the Project Guide
Click the See project costs link
Identify Over Budget Tasks and Resources (cont.)

## Slide 45: Over Budget Tasks and Resources
The Project Costs pane provides access to filters that are most closely related to project costs
Identify Over Budget Tasks and Resources (cont.)

## Slide 46: Over Budget Tasks and Resources
Under the Apply a filter heading, select Cost Overbudget
Cost Overbudget filter applied
Click Done when finished
Identify Over Budget Tasks and Resources (cont.)

## Slide 47: Over Budget Tasks and Resources
Cost variance is another critical indicator of overall project health
Evaluating cost variance enables you to make incremental budget adjustments for individual tasks so that you don’t exceed the project budget
Identify Over Budget Tasks and Resources (cont.)

## Slide 48: Time and Schedule Problems
Reschedule Uncompleted Work
Click Go To
Click Edit
Key 47
Click OK
Scroll the Scene 3 summary task to the top of the view

## Slide 49: Time and Schedule Problems
Gantt Chart shows Scene 3 summary task and subtasks
Reschedule Uncompleted Work (cont.)

## Slide 50: Time and Schedule Problems
Point to Tracking
Click Tools
Click Update Project
Reschedule Uncompleted Work (cont.)

## Slide 51: Time and Schedule Problems
Select the Reschedule uncompleted work to start after option
Key or select 06/05/08 in the date box
Click OK
Reschedule Uncompleted Work (cont.)

## Slide 52: Time and Schedule Problems
Rescheduling causes task to be split
Reschedule Uncompleted Work (cont.)

## Slide 53: Time and Schedule Problems
Project handles tasks in relation to the scheduled restart date in the following ways
If the task does not have actual work recorded for it prior to the rescheduled date and there is no constraint in place, the entire task is rescheduled to begin after that date
Reschedule Uncompleted Work (cont.)

## Slide 54: Time and Schedule Problems
If the task has some actual work recorded prior to but not after the rescheduled date, the task is split so that all remaining work starts after the rescheduled date. The actual work is not affected.
If the task has some actual work recorded for it prior to as well as after the rescheduled date, the task is not affected.
Reschedule Uncompleted Work (cont.)

## Slide 55: Time and Schedule Problems
Keep in mind that a change in one part of the schedule — be it a time, cost, or scope change — can, and usually does, affect the schedule elsewhere
Reschedule Uncompleted Work (cont.)

## Slide 56: Summary
Establish a project baseline
Track a project as scheduled
Enter the completion percentage for a task
You Learned How to

## Slide 57: Summary
You Learned How to (cont.)
Track timephased actual work
Identify over budget tasks and resources
Identify time and schedule problems