## Slide 1: Working with Resource Pools
Lesson 16

## Slide 2: Skills Matrix
Skills | Matrix Skill
Develop a resource pool | Develop a resource pool
View assignment details in a resource pool | View assignment details in the resource pool

## Slide 3: Skills Matrix
Skills | Matrix Skill
Revise assignments in a sharer plan | Revise assignments in a sharer plan
Update resource information in a resource pool | Update working time for a resource in a resource pool

## Slide 4: Skills Matrix
Skills | Matrix Skill
Update working time for all projects in a resource pool | Update working time for all sharer plans via the resource pool
Add new project plans to a resource pool | Add new files to the resource pool

## Slide 5: Skills Matrix
Skills | Matrix Skill
Revise a sharer plan and update a resource pool | Revise a sharer plan and manually update the resource pool

## Slide 6: Software Orientation
Select whether you want to use resources from a sharer plan or a resource pool
The filename here is the file that will become a “sharer” plan
This drop-down list provides the files from which you can use resources
If there are resource detail conflicts between the sharer plan and the resource pool, you can select which one you want to take precedence
Microsoft Project’s Share Resources Dialog Box

## Slide 7: Developing a Resource Pool
Develop a Resource Pool
Click Save As
Click the New button on the Standard toolbar
Click the Show/Hide Project Guide
Click File

## Slide 8: Developing a Resource Pool
Develop a Resource Pool (cont.)
Locate the solution folder in the Save As box
Key Resource Pool 16 in the File name box
Click Save

## Slide 9: Developing a Resource Pool
Develop a Resource Pool (cont.)
Click Resource Sheet
Click Window on the menu bar
Click Arrange All
Click View

## Slide 10: Developing a Resource Pool
Develop a Resource Pool (cont.)
Before being linked to a resource pool, some resource names and details are duplicated across projects

## Slide 11: Developing a Resource Pool
Develop a Resource Pool (cont.)
Click Share Resources
Click on the title bar of the Don Funk Music Video 16 window
Click Tools
Point to Resource Sharing

## Slide 12: Developing a Resource Pool
Develop a Resource Pool (cont.)
Click Use resources under Resources for ‘Don Funk Music Video 16’
Select Resource Pool 16

## Slide 13: Developing a Resource Pool
Develop a Resource Pool (cont.)
Click OK

## Slide 14: Developing a Resource Pool
Develop a Resource Pool (cont.)
Click Share Resources
Click on the title bar of the Adventure Works Promo 16 window
Click Tools
Point to Resource Sharing

## Slide 15: Developing a Resource Pool
Develop a Resource Pool (cont.)
Click Use resources under Resources for ‘Adventure Works Promo 16’
Select Resource Pool 16

## Slide 16: Developing a Resource Pool
Develop a Resource Pool (cont.)
Select Pool takes precedence under the On conflict with calendar or resource information label
Click OK

## Slide 17: Developing a Resource Pool
Develop a Resource Pool (cont.)
After sharer plans have been linked to the resource pool, combined resource details appear in all files

## Slide 18: Developing a Resource Pool
Develop a Resource Pool (cont.)
Resource pool — Project plan from which other project plans gather their information
It can help you monitor how resources are utilized across multiple projects
It contains information about all resources’ task assignments from all plans linked to the pool

## Slide 19: Developing a Resource Pool
Develop a Resource Pool (cont.)
If you change resource information in the pool, all linked plans will use the updated information
Sharer plan — Project plan that is linked to the resource pool

## Slide 20: Developing a Resource Pool
Develop a Resource Pool (cont.)
Setting up a resource pool allows you to
  Enter resource information once, but use it in multiple plans
  View resources’ assignment details from multiple projects in a single place
  View assignment costs across multiple projects

## Slide 21: Developing a Resource Pool
Develop a Resource Pool (cont.)
Setting up a resource pool allows you to
  Identify resources that are overallocated across multiple projects
  Enter resource information in any of the individual plans or in the resource pool

## Slide 22: Developing a Resource Pool
Develop a Resource Pool (cont.)
Any Microsoft project plan can serve as a resource pool. However, it is best to specify a file that does not contain tasks.
Resource information can be maintained in the resource pool

## Slide 23: Developing a Resource Pool
Develop a Resource Pool (cont.)
Line manager — Manager of a group of resources (also called a functional manager)
Resource manager — Oversees resource usage in project activities specifically to manage the time and cost of resources

## Slide 24: Viewing Assignment Details
Select the name of resource 14
Double-click the title bar of the Resource pool 16 window
Click View
Click Resource Usage
Click the plus sign (+) next to the resource name
View Assignment Details in the Resource Pool

## Slide 25: Viewing Assignment Details
Video Editing Studio resource has been expanded to show all tasks to which it has been assigned
View Assignment Details in the Resource Pool (cont.)

## Slide 26: Viewing Assignment Details
Click Split
Click the Scroll to Task button
Scroll the timescale details until you can see the assignments for the Video Editing Studio for the weeks of July 6 and July 13, 2008
Click Window
View Assignment Details in the Resource Pool (cont.)

## Slide 27: Viewing Assignment Details
The Resource Form shows all of the details from sharer plans for the selected resource
The Resource Usage view shows all of the resources in the resource pool and their assignments
View Assignment Details in the Resource Pool (cont.)

## Slide 28: Viewing Assignment Details
Click Remove Split
Click Window
View Assignment Details in the Resource Pool (cont.)

## Slide 29: Viewing Assignment Details
Changing the view allows you to better view and analyze the information in the pool
One of the most important benefits of a resource pool is that it enables you to see how resources are allocated across multiple projects
You can pinpoint resources that are overallocated across multiple projects
View Assignment Details in the Resource Pool (cont.)

## Slide 30: Revising Assignments in a Sharer Plan
Click Window
Click on the name of resource 46, Arlene Huff
Click Window
Click Split
Click Don Funk Music Video 16
Revise Assignments in a Sharer Plan

## Slide 31: Revising Assignments in a Sharer Plan
Click Go To
Click View
Click Gantt Chart
Click Edit
Key 67
Click OK
Revise Assignments in a Sharer Plan (cont.)

## Slide 32: Revising Assignments in a Sharer Plan
Click Assign
Click on the name of task 67, Rough Audio Edit
Click the Assign Resources button
Select Arlene Huff
Click Close
Revise Assignments in a Sharer Plan (cont.)

## Slide 33: Revising Assignments in a Sharer Plan
Click Window
Click Resource Pool 16
Click the Scroll to Task button
Revise Assignments in a Sharer Plan (cont.)

## Slide 34: Revising Assignments in a Sharer Plan
Arlene Huff has been assigned to the Rough audio edit task for the Don Funk Music Video 16 project plan
Revise Assignments in a Sharer Plan (cont.)

## Slide 35: Revising Assignments in a Sharer Plan
Save each project plan
Leave Resource Pool 16 in the active window
Revise Assignments in a Sharer Plan (cont.)

## Slide 36: Revising Assignments in a Sharer Plan
Assignment — Matching of a resource to a task
The resource’s assignment details originate in a sharer plan
Project updates the resource pool with assignment details as you make them in the sharer plan
Revise Assignments in a Sharer Plan (cont.)

## Slide 37: Updating Resource Information
Click the General tab in the Resource Information dialog box
Scroll to select resource name 26, Jim Kim
Click the plus sign (+) next to Jim Kim’s name
Click the Resource Information button
Click the Change Working Times button
Update Working Time for a Resource in a Resource Pool

## Slide 38: Updating Resource Information
Click the first empty cell under the Name column heading on the Exceptions tab
Scroll until July 2008 is visible
Select July 10 and 11
Press Enter
Key Training Class
Update Working Time for a Resource in a Resource Pool (cont.)

## Slide 39: Updating Resource Information
July 10 and 11 have been set to nonworking
Update Working Time for a Resource in a Resource Pool (cont.)

## Slide 40: Updating Resource Information
Click OK
Click OK
Update Working Time for a Resource in a Resource Pool (cont.)

## Slide 41: Updating Resource Information
Because July 10 and 11 have been set to nonworking days for Jim Kim, no work is scheduled for these days
Update Working Time for a Resource in a Resource Pool (cont.)

## Slide 42: Updating Resource Information
Select the name resource 26, Jim Kim
Click Window
Click Adventure Works Promo 16
Click the Change Working Time button
Click the Resource Information button
Update Working Time for a Resource in a Resource Pool (cont.)

## Slide 43: Updating Resource Information
Review the notes next to the calendar
Scroll until July 2008 is visible
Click on July 10
Click Cancel
Click Cancel
Update Working Time for a Resource in a Resource Pool (cont.)

## Slide 44: Updating Resource Information
Resource pools offer a central location to enter resource details, such as working time and cost rates
Any updates you make to the pool are available in all sharer plans
Some large organizations have a program office to oversee a collection of projects, each of which is part of a complete deliverable and the organization’s strategic objectives
Update Working Time for a Resource in a Resource Pool (cont.)

## Slide 45: Update Working Time for All Projects
Click Change Working Time
Click Window
Click Resource Pool 16
Click Tools
Update Working Time for All Sharer Plans via the Resource Pool

## Slide 46: Update Working Time for All Projects
Select Standard (Project Calendar)
Scroll until July 2008 appears
Click on July 18
Update Working Time for All Sharer Plans (cont.)

## Slide 47: Update Working Time for All Projects
Click the first empty cell under the Name column heading on the Exceptions tab
Press Enter
Key Company Picnic
Update Working Time for All Sharer Plans (cont.)

## Slide 48: Update Working Time for All Projects
The date of the company picnic, July 18, is a nonworking day for the whole company
Click OK
Update Working Time for All Sharer Plans (cont.)

## Slide 49: Update Working Time for All Projects
Click Change Working Time
Click Window
Click Don Funk Music Video 16
Click Tools
Update Working Time for All Sharer Plans (cont.)

## Slide 50: Update Working Time for All Projects
Select Standard (Project Calendar)
Scroll until July 2008 appears
Notice that July 18 is flagged as a nonworking date
Click Cancel
Update Working Time for All Sharer Plans (cont.)

## Slide 51: Update Working Time for All Projects
Another key advantage of using resource pools is that when you change the base calendar for the resource pool, the change is updated for all sharer plans that use that calendar
Update Working Time for All Sharer Plans (cont.)

## Slide 52: Adding New Project Plans
Click Window
Click View
Click Resource Sheet
Click New
Click Remove Split
Click the Show/Hide Project Guide button
Add New Files to the Resource Pool

## Slide 53: Adding New Project Plans
Locate your solution folder in the Save in box
Click File
Click Save As
Click Save
Key Coho Winery Project 16 in the File name box
Add New Files to the Resource Pool (cont.)

## Slide 54: Adding New Project Plans
Point to Resource Sharing
Click the Assign Resources button
Click Tools
Click Share Resources
Add New Files to the Resource Pool (cont.)

## Slide 55: Adding New Project Plans
Select Use Resources under Resources for ‘Coho Winery Project 16’
Select Resource Pool 16A in the From list
Add New Files to the Resource Pool (cont.)

## Slide 56: Adding New Project Plans
Click OK
Add New Files to the Resource Pool (cont.)

## Slide 57: Adding New Project Plans
Click Close
Add New Files to the Resource Pool (cont.)

## Slide 58: Adding New Project Plans
You can create a project plan and make it a sharer plan at any time
  When initially entering tasks
  After you have assigned resources to tasks
  After work has begun
Add New Files to the Resource Pool (cont.)

## Slide 59: Revising a Sharer Plan and Updating a Resource Pool
Click the Assign Resources button
Click View
Click Gantt Chart
Click on the name of task 6
Select the name of Frank Zhang
Click Assign
Revise a Sharer Plan and Manually Update the Resource Pool

## Slide 60: Revising a Sharer Plan and Updating a Resource Pool
Point to Tools
Point to Resource Sharing
Click on the name of task 9
Select the name of Holly Dickson
Click Remove
Click Update Resource Pool
Revise a Sharer Plan and Manually Update the Resource Pool (cont.)

## Slide 61: Revising a Sharer Plan and Updating a Resource Pool
Click Close
Click on the name of task 3
Select the name of Arlene Huff
Click Assign
Revise a Sharer Plan and Manually Update the Resource Pool (cont.)

## Slide 62: Revising a Sharer Plan and Updating a Resource Pool
Frank Zhang added to task 6
Holly Dickson removed from task 9c
Change Highlighting (blue cells) shows the effects of the changes you made to resources
Revise a Sharer Plan and Manually Update the Resource Pool (cont.)

## Slide 63: Revising a Sharer Plan and Updating a Resource Pool
Click File
Click Close
Click Yes
Revise a Sharer Plan and Manually Update the Resource Pool (cont.)

## Slide 64: Revising a Sharer Plan and Updating a Resource Pool
Revise a Sharer Plan and Manually Update the Resource Pool (cont.)

## Slide 65: Revising a Sharer Plan and Updating a Resource Pool
Click OK
Click File
Click Close
Revise a Sharer Plan and Manually Update the Resource Pool (cont.)

## Slide 66: Revising a Sharer Plan and Updating a Resource Pool
If you are sharing a resource pool with other Project users across a network, whoever has the resource pool open as read-write prevents others from updating resource information
It is a good idea to open the resource pool as read-only and use the Update Resource Pool command as needed
Revise a Sharer Plan and Manually Update the Resource Pool (cont.)

## Slide 67: Summary
Develop a resource pool
View assignment details in a resource pool
Revise assignments in a sharer plan
You Learned How to

## Slide 68: Summary
You Learned How to (cont.)
Update resource information in a resource pool
Update working time for all projects in a resource pool

## Slide 69: Summary
You Learned How to (cont.)
Add new project plans to a resource pool
Revise a sharer plan and update a resource pool