## Slide 1: Project Basics
Lesson 1

## Slide 2: Skills Matrix
Skills | Matrix Skill
Start Microsoft Project Standard | Start Microsoft Project Standard
Create a project plan | Open a new project plan Specify a start date Save the project plan

## Slide 3: Skills Matrix
Skills | Matrix Skill
Define project calendars | Define the project calendar
Enter tasks and task details | Enter tasks Enter task durations Create a milestone

## Slide 4: Skills Matrix
Skills | Matrix Skill
Organize tasks into phases | Create summary tasks
Link tasks | Link two tasks Link several tasks at once Link the milestone tasks

## Slide 5: Skills Matrix
Skills | Matrix Skill
Document tasks | Enter a task note Add a hyperlink
Review the project plan’s duration | Check the project’s duration

## Slide 6: Software Orientation
Microsoft Project’s Opening Screen

## Slide 7: Starting Microsoft Project Standard
Start Microsoft Project
Click Microsoft Office Project 2007
Click the Start button
Click All Programs
Click Microsoft Office

## Slide 8: Starting Microsoft Project Standard
Start Microsoft Project (cont.)
Click New
Click File
The New Project task pane is activated

## Slide 9: Starting Microsoft Project Standard
Start Microsoft Project (cont.)
Click FileNew on menu bar to open New Project dialog box
Select Blank Presentation
Select or search for templates

## Slide 10: Creating a Project Plan
Open a New Project Plan
Click New
Click File
Click Blank Project

## Slide 11: Creating a Project Plan
In the Tasks pane, click the Set a date to schedule from link
Use the calendar to select a start date
Specify a Start Date
Scroll calendar to select desired start date

## Slide 12: Creating a Project Plan
On the Standard toolbar, click Save
  The Save As dialog box appears
Enter or select the file name and location
Click Save
SAVE FREQUENTLY TO PROTECT YOUR WORK!
Save the Project Plan

## Slide 13: Defining Project Calendars
Define the Project Calendar
Click the Define general working times link in the Tasks pane
Select the Standard calendar template
Click Continue to Step 2 and Continue to Step 3 links

## Slide 14: Defining Project Calendars
Define the Project Calendar (cont.)
Click the Change Working Time link under Set Holidays and Days Off
Select the desired date(s) on the calendar

## Slide 15: Defining Project Calendars
Define the Project Calendar (cont.)
Enter the Exception Time name, dates, and details, including recurrence info
Continue to Steps 4 and 5
Save and Finish

## Slide 16: Entering Tasks and Task Details
Enter Tasks
Click the List the tasks in the project link in the Tasks pane
Enter tasks in the cells below the Task Name column heading
Press Enter after each task name to advance to the next cell

## Slide 17: Entering Tasks and Task Details
Enter Tasks (cont.)
The default duration is one day; the question mark (1 day?) indicates an estimated duration
New tasks entered

## Slide 18: Software Orientation
Calendar Tab in Options Dialog Box
Changes the day on which the project week starts
Changes the month in which the project fiscal year begins
Changes the default start time and end time for scheduled tasks
Changes how many hours are scheduled for one day or one week or how many days are scheduled for one month

## Slide 19: Entering Tasks and Task Details
Enter durations in the cells below the Duration column heading
  Enter h for hours, d for days, w for weeks, and mo for months
  Enter a question mark after the time if the duration is estimated
Enter Task Durations
Bar lengths represent task durations

## Slide 20: Entering Tasks and Task Details
Durations can be shown as actual duration, estimated duration, or elapsed duration
Enter Task Durations (cont.)
If You Enter This Abbreviation | It Appears Like This | And Means
m | min | minute
h | hr | hour
d | day | day
w | wk | week
mo | mon | month
em | emin | elapsed minute
eh | ehr | elapsed hour
ed | eday | elapsed day
ew | ewk | elapsed week
emo | emon | elapsed month

## Slide 21: Entering Tasks and Task Details
A milestone represents a major event reached within the project
Select a task name or enter a new task name as the desired milestone
Create a Milestone

## Slide 22: Entering Tasks and Task Details
In the List Tasks pane, click the Make selected task a milestone checkbox
  A milestone is represented by a black diamond
  The duration of a milestone is 0 days
Click Done at the bottom of the List Tasks pane
Create a Milestone (cont.)

## Slide 23: Entering Tasks and Task Details
Create a Milestone (cont.)
…and is represented by a black diamond
A milestone has a duration of 0 days

## Slide 24: Organizing Tasks into Phases
Create Summary Tasks
In the Tasks pane, click the Organize tasks into phases link
Select the task that will be the summary task for the phase
  Select an existing task OR
  Insert a new task at the desired place in the task list

## Slide 25: Organizing Tasks into Phases
Create Summary Tasks (cont.)
Select the tasks or tasks to be indented under the summary task
In the Organize Tasks pane, choose the Click here to indent selected tasks to make them subtasks of the task above button

## Slide 26: Organizing Tasks into Phases
Create Summary Tasks (cont.)
Continue for all phases
Click Done at the bottom of the Organize Tasks pane
Summary task with subtasks

## Slide 27: Linking Tasks
Click the Schedule tasks link in the Tasks pane
Select the names of the two tasks to be linked
Choose the Click here to create a finish to start link button in the Schedule Tasks pane
Link Two Tasks

## Slide 28: Linking Tasks
Link Two Tasks (cont.)
Link line indicates tasks that have been linked

## Slide 29: Linking Tasks
Link Two Tasks (cont.)
This Task Relationship | Means | Looks Like This in the Gantt Chart | Example
Finish-to-start (FS) | The finish date of the predecessor task determines the start date of the successor task. |  | A music track must be recorded before it can be edited.
Start-to-start (SS) | The start date of the predecessor task determines the start date of the successor task. |  | Booking musicians and Booking dancers are related tasks and can occur simultaneously.
Finish-to-finish (FF) | The finish date of the predecessor task determines the finish date of the successor task. |  | Tasks that require the use of specific equipment must end when the equipment rental ends.
Start-to-finish (SF) (This type of relationship is rarely used.) | The start date of the predecessor task determines the finish date of the successor task. |  | The time when the production sound studio becomes available determines when rehearsals must end.
There are four types of task relationships

## Slide 30: Linking Tasks
Link Several Tasks at Once
Select the names of the tasks to be linked
Choose the Click here to create a finish to start link button in the Schedule Tasks pane
Link additional tasks as needed

## Slide 31: Linking Tasks
Link Several Tasks at Once (cont.)

## Slide 32: Linking Tasks
Link the Milestone Tasks
Select the names of the milestones to be linked
Choose the Click here to create a finish to start link button in the Schedule Tasks pane
Link additional milestones as needed
Click Done in the Schedule Tasks pane
Linked milestones

## Slide 33: Documenting Tasks
Enter a Task Note
Click the Link to or attach more task information link in the Tasks pane
Select the task to which a note will be added
Click the Add a note link in the Add Information pane
Enter the note details in the Notes tab of the Task Information dialog box

## Slide 34: Documenting Tasks
Enter a Task Note (cont.)
Point to the Note icon
  The note appears in a ScreenTip
  Double-click the note icon to see longer notes or additional task information

## Slide 35: Documenting Tasks
Add a Hyperlink
Select task to which a hyperlink is to be added
Click the Add a hyperlink link in the Add Information pane
Key hyperlink details or title in Text to display box
Key address in the Address box
Click OK

## Slide 36: Documenting Tasks
Add a Hyperlink (cont.)
Text displayed in the hyperlink ScreenTip
Hyperlink address

## Slide 37: Documenting Tasks
Add a Hyperlink (cont.)
Point to the Hyperlink icon
  Informational text appears in a ScreenTip
  Click the hyperlink icon to open a Web page in your browser

## Slide 38: Reviewing the Project Plan’s Duration
Check the Project’s Duration
Click Project Information
Click Project
The Project Information dialog box is activated
Click Statistics

## Slide 39: Reviewing the Project Plan’s Duration
Current start date
Current finish date
Current duration
Check the Project’s Duration (cont.)

## Slide 40: Reviewing the Project Plan’s Duration
Click Zoom
Click View
Click Entire Project
Click OK
Check the Project’s Duration (cont.)

## Slide 41: Reviewing the Project Plan’s Duration
Zoom using Entire Project so that the entire project is visible on the screen
Check the Project’s Duration (cont.)

## Slide 42: Summary
Start Microsoft Project Standard
Create a project plan
Define project calendars
Enter tasks and task details
You Learned How to

## Slide 43: Summary
You Learned How to (cont.)
Organize tasks into phases
Link tasks
Document tasks
Review the project plan’s duration