## Slide 1: Establishing Resources
Lesson 2

## Slide 2: Skills Matrix
Skills | Matrix Skill
Establish people resources | Establish individual people resources Establish a resource that represents multiple people
Establish equipment resources | Establish equipment resources

## Slide 3: Skills Matrix
Skills | Matrix Skill
Establish material resources | Establish material resources
Establish cost resources | Establish cost resources

## Slide 4: Skills Matrix
Skills | Matrix Skill
Establish resource pay rates | Enter resource cost information
Adjust resource working times | Establish nonworking times for an individual resource Establish a specific work schedule for a resource
Add resource notes | Attach a note to a resource

## Slide 5: Software Orientation
Microsoft Project’s Resource Sheet View

## Slide 6: Establishing People Resources
Enter resources in the Resource Name column
Click Resources on the Project Guide toolbar
Click the Specify people and equipment for the project link
Select Enter resource manually
Establish Individual People Resources

## Slide 7: Establishing People Resources
Enter resources in the Resource Name column
Click Done in the Specify Resources pane when finished
Establish Individual People Resources (cont.)

## Slide 8: Establishing People Resources
Key the maximum units for the new resource in the Max. Units field
Click View
Click Resource Sheet
Key the new group resource into the Resource Name column
Establish a Resource that Represents Multiple People

## Slide 9: Establishing People Resources
A group resource represents a group of people doing the same job
“Sound Technician” is the new group resource
Max. Units indicates the number of individual resources available
Establish a Resource that Represents Multiple People (cont.)

## Slide 10: Establishing Equipment Resources
Select the next empty cell in the Resource name column
Click Project
Click Resource Information
Click General
Establish Equipment Resources
Click the General tab in the Resource Information dialog box

## Slide 11: Establishing Equipment Resources
Also activate the Resource Information dialog box by
  Double-clicking a resource name
  Double-clicking an empty cell in the Resource Name column
  Clicking the Resource Information button on the Standard toolbar
Resource Information button
Establish Equipment Resources (cont.)

## Slide 12: Establishing Equipment Resources
Key the equipment resource name
Select Work as the resource Type
Click OK
Key the equipment resource name
Select Work as the resource Type
Establish Equipment Resources (cont.)

## Slide 13: Establishing Equipment Resources
Adjust Max. Units for the equipment resource, if necessary
Continue to enter equipment resources as needed
Adjust Max. Units for equipment resources
Establish Equipment Resources (cont.)

## Slide 14: Establishing Material Resources
Establish Material Resources
Key the material label in the Material Label field
Select the next empty cell in the Resource Name column
Key the material resource name
Select Material in the Type field

## Slide 15: Establishing Material Resources
The material label is the unit of measure used to track consumption
material label
Resource type
Establish Material Resources (cont.)

## Slide 16: Establishing Cost Resources
Establish Cost Resources
Select the next empty cell in the Resource Name column
Key the cost resource name
Select Cost in the Type field

## Slide 17: Establishing Cost Resources
Establish Cost Resources (cont.)
A cost resource doesn’t depend on the amount of work on a task or the duration of a task
Resource type

## Slide 18: Establishing Resource Pay Rates
Enter Resource Cost Information
Select the Std. Rate field for the desired resource
Key the rate (hourly, daily, weekly, monthly)
Press Enter
Hourly rate for Scott Seely

## Slide 19: Establishing Resource Pay Rates
For a material resource, the standard rate is per unit of consumption
Resource rates entered by hour, day, week, or month
Enter Resource Cost Information (cont.)

## Slide 20: Adjusting Resource Working Times
Click Tools on the menu bar
Click Change Working Times
The Change Working Times dialog box is activated
Establish Nonworking Times for an Individual Work Resource

## Slide 21: Adjusting Resource Working Times
Select the desired resource in the For calendar box
Select the desired exception dates on the calendar
Resource selected in the For calendar box
Exception dates selected on calendar
Establish Nonworking Times for an Individual Work Resource (cont.)

## Slide 22: Adjusting Resource Working Times
Key description of the exception time into the Name field
Click the Start field
  Selected exception dates appear automatically
Description of exception time
Exception start and finish dates
Establish Nonworking Times for an Individual Work Resource (cont.)

## Slide 23: Adjusting Resource Working Times
Click Tools on the menu bar
Click Change Working Times
The Change Working Times dialog box is activated
Establish a Specific Work Schedule for a Resource

## Slide 24: Adjusting Resource Working Times
Select the desired resource in the For calendar box
Scroll the calendar to the desired month
Resource selected in the For calendar box
Calendar scrolled to desired month
Establish a Specific Work Schedule for a Resource (cont.)

## Slide 25: Adjusting Resource Working Times
Click the Work Weeks tab
Click the Details button
  The Details dialog box is activated
Details button
Work Weeks tab
Establish a Specific Work Schedule for a Resource (cont.)

## Slide 26: Adjusting Resource Working Times
Select desired days in the Select day(s) box
Click the Set day(s) to these specific working times button
Key in working times
Press Enter
Key in the beginning and ending working times
Establish a Specific Work Schedule for a Resource (cont.)

## Slide 27: Adjusting Resource Working Times
Select the desired days in the Select day(s) box
Click the Set days to nonworking time button
Click OK
Establish a Specific Work Schedule for a Resource (cont.)

## Slide 28: Adjusting Resource Working Times
Modified working hours
Fridays are “grayed out” to indicate nonworking days
Name of resource calendar
Establish a Specific Work Schedule for a Resource (cont.)

## Slide 29: Adding Resource Notes
Attach a Note to a Resource
Attach additional information about a resource by attaching a note
  A resource note provides details regarding how and why a resource is scheduled the way that it is
  Use the Resource Notes button to add a resource note
Resource Notes button

## Slide 30: Adding Resource Notes
Attach a Note to a Resource (cont.)
Click the Resource Notes button on the Standard toolbar
Key desired information in the Notes box
Click OK
Resource name indicates to which resource the note will be attached

## Slide 31: Adding Resource Notes
Attach a Note to a Resource (cont.)
A note icon appears in the Indicators column
Point to the icon to see the note in a ScreenTip
Double-click the icon to display the full text of the note

## Slide 32: Summary
Establish people resources
Establish equipment resources
Establish material resources
Establish cost resources
You Learned How to

## Slide 33: Summary
You Learned How to (cont.)
Establish resource pay rates
Adjust resource working times
Add resource notes