## Slide 1: Managing Multiple Projects
Lesson 9

## Slide 2: Skills Matrix
Skills | Matrix Skill
Manage consolidated projects | Create a consolidated project plan
Create dependencies between projects | Link tasks from two different project plans

## Slide 3: Software Orientation
Consolidated project summary task
Consolidated project summary task
Consolidated Project Gantt Chart View

## Slide 4: Software Orientation
Inserted projects appear as summary tasks with gray Gantt bars
Inserted project icon
Consolidated Project Gantt Chart View (cont.)

## Slide 5: Software Orientation
The Gantt Chart view of a consolidated project allows you to see multiple projects collected in one project plan
  Can filter, sort, and group the data
  Can see relationships (dependencies) between projects
Consolidated Project Gantt Chart View (cont.)

## Slide 6: Managing Consolidated Projects
Click OK
Click Window
Click New Window
Select the names of both open projects
Create a Consolidated Project Plan

## Slide 7: Managing Consolidated Projects
Click View on the menu bar
Click the Show/Hide Project Guide button
Click Zoom
Click Entire Project
Click OK
Create a Consolidated Project Plan (cont.)

## Slide 8: Managing Consolidated Projects
Make sure Start, Duration, and Finish columns are visible. If necessary, double-click the right edge of columns that display pound signs (###).
Inserted project icon
Create a Consolidated Project Plan (cont.)

## Slide 9: Managing Consolidated Projects
Note
When you point to the Inserted Project icon in the Indicators column, Project displays the full path to the inserted file
Create a Consolidated Project Plan (cont.)

## Slide 10: Managing Consolidated Projects
Click Yes to All if prompted to save changes to inserted projects
Save the consolidated plan as Consolidated Project 9
Create a Consolidated Project Plan (cont.)

## Slide 11: Managing Consolidated Projects
Click Options
Click Tools on the menu bar
Select Show project summary task
Click OK
Create a Consolidated Project Plan (cont.)

## Slide 12: Managing Consolidated Projects
Consolidated project summary task
Create a Consolidated Project Plan (cont.)

## Slide 13: Managing Consolidated Projects
Project managers usually work on several complex projects at the same time
  People may be working on different tasks at different times and locations
Microsoft Project enables you to combine two projects to form a consolidated project
Create a Consolidated Project Plan (cont.)

## Slide 14: Managing Consolidated Projects
Consolidated project — Microsoft Project File that contains other Microsoft Project files
  Also known as a master project
Inserted project — Microsoft Project file that is inserted into another Microsoft Project file
  Also known as a subproject
Create a Consolidated Project Plan (cont.)

## Slide 15: Managing Consolidated Projects
Inserted projects do not actually reside within the consolidated project
  They are linked so that they can be viewed and edited from the consolidated project
Create a Consolidated Project Plan (cont.)

## Slide 16: Managing Consolidated Projects
If an inserted project is edited outside the consolidated project, the new information appears in the consolidated project the next time it is opened
When you save a consolidated project, changes you have made to inserted projects are saved in the source file as well
Create a Consolidated Project Plan (cont.)

## Slide 17: Managing Consolidated Projects
Using a consolidated project plan enables you to
  See all of your organization’s projects in a single view
  “Roll-up” project information to higher management levels
  Divide a large project into separate project plans
  See all of the information for YOUR project in one location
Create a Consolidated Project Plan (cont.)

## Slide 18: Managing Consolidated Projects
The Gantt bar for an inserted project is gray
An inserted project icon appears in the Indicators column
Any changes you made to inserted projects are saved in the source files as well
You can add an unlimited number of inserted projects (limited by real-life time and space constraints)
Create a Consolidated Project Plan (cont.)

## Slide 19: Creating Dependencies in Projects
Click Adventure Works Promo 9
Click Window
Click the name of task 9
Click Scroll to Task button
Link Tasks from Two Different Project Plans

## Slide 20: Creating Dependencies in Projects
Click Don Funk Music Video 9
Click Window
Click Edit  Go To
Key 69
Click OK
Link Tasks from Two Different Project Plans (cont.)

## Slide 21: Creating Dependencies in Projects
Click the Predecessors tab
Click the Task Information button
In the ID column, click the next empty cell below task 67
Key Adventure Works Promo 9\9
Link Tasks from Two Different Project Plans (cont.)

## Slide 22: Creating Dependencies in Projects
Task Information dialog box with predecessor task entered
Link Tasks from Two Different Project Plans (cont.)

## Slide 23: Creating Dependencies in Projects
Click OK
Press Enter
Project inserts the ghost task into the project plan
Link Tasks from Two Different Project Plans (cont.)

## Slide 24: Creating Dependencies in Projects
Ghost task
Change Highlighting indicates cells that have been affected by the previous action
Link Tasks from Two Different Project Plans (cont.)

## Slide 25: Creating Dependencies in Projects
Click Adventure Works Promo 9
Click Window
Review the ghost task and project plan
Link Tasks from Two Different Project Plans (cont.)

## Slide 26: Creating Dependencies in Projects
Click Consolidated Project 9
Click Window
Review the cross-project link and project plan
Link Tasks from Two Different Project Plans (cont.)

## Slide 27: Creating Dependencies in Projects
Consolidated files Gantt Chart showing link between Adventure Works task 9…
Link Tasks from Two Different Project Plans (cont.)

## Slide 28: Creating Dependencies in Projects
…and Don Funk Music Video task 70
Link Tasks from Two Different Project Plans (cont.)

## Slide 29: Creating Dependencies in Projects
Most projects have dependencies to other projects
Task relationships between project files are similar to links between tasks within a project file
  Remember that external predecessor and successor tasks have gray task names and Gantt bars
Link Tasks from Two Different Project Plans (cont.)

## Slide 30: Creating Dependencies in Projects
There are various reasons to create dependencies between projects
  The completion of a task in one project might enable the start of a task in another project
  A person or piece of equipment may be assigned to a task in one project, and you need to delay the start of a task in another project until the resource completes the first task
Link Tasks from Two Different Project Plans (cont.)

## Slide 31: Creating Dependencies in Projects
External predecessor and successor tasks are sometimes called ghost tasks because they are not linked to tasks within the project file, only to tasks in other project files
Link Tasks from Two Different Project Plans (cont.)

## Slide 32: Summary
Manage consolidated projects
Create dependencies between projects
You Learned How to