## Slide 1: Advanced Project Plan Tracking
Lesson 15

## Slide 2: Skills Matrix
Skills | Matrix Skill
Record actual start, finish, and duration values of tasks | Enter actual start date and duration for a task
Adjust remaining work or duration of tasks | Adjust actual and remaining work for a task

## Slide 3: Skills Matrix
Skills | Matrix Skill
Reschedule uncompleted work | Reschedule incomplete work
Save an interim plan | Save an interim project plan
Compare baseline, interim, and actual plans | Compare the baseline, interim, and actual project plans

## Slide 4: Skills Matrix
Skills | Matrix Skill
Report project status | Report project variance with a “Stoplight” view
Evaluate performance with earned value analysis | Set project status date and display the Earned Value table

## Slide 5: Software Orientation
Microsoft Project’s Earned Value Table

## Slide 6: Software Orientation
CPI – or Cost Performance Index, the ratio of budgeted to actual cost, or BCWP divided by ACWP
SPI – or Schedule Performance Index, the ratio of performed to schedule work, or BCWP divided by BCWS
Planned Value - PV (BCWS) – the value of the work scheduled to be completed as of the status date
Earned Value - EV (BCWP) – the portion of the budgeted cost that should have been spent to complete each task’s actual work performed up to the status date
AC (ACWP) – the actual cost incurred to complete each task’s actual work up to the status date
SV – or Schedule Variance, the difference between the budgeted cost of work performed and the budgeted cost of work scheduled
CV – or Cost Variance, the difference between the budgeted and actual cost of work performed
EAC – Estimate at Completion, the expected total cost of a task based on performance up to the status date
BAC – Budget at Completion, the total planned cost
VAC – Variance at Completion, the difference between the BAC (Budgeted At Completion) or baseline cost and EAC (Estimated At Completion)
Microsoft Project’s Earned Value Table (cont.)

## Slide 7: Recording Actual Values of Tasks
Click Tracking
Click the Show/Hide Project Guide button
Click View
Point to Toolbars
Enter Actual Start Date and Duration for a Task

## Slide 8: Recording Actual Values of Tasks
Click OK
Click Edit
Click Go To
Key 7 in the ID box
Enter Actual Start Date and Duration for a Task (cont.)

## Slide 9: Recording Actual Values of Tasks
Click Tools
Point to Tracking
Click Update Tasks
Enter Actual Start Date and Duration for a Task (cont.)

## Slide 10: Recording Actual Values of Tasks
Click OK
Key March 20, 2008, in the Start box under the Actual label
Key 2w in the Actual dur box
Enter Actual Start Date and Duration for a Task (cont.)

## Slide 11: Recording Actual Values of Tasks
Task 7 has a 2w duration
Task 7’s actual start date is March 20
Enter Actual Start Date and Duration for a Task (cont.)

## Slide 12: Recording Actual Values of Tasks
Click OK
In the Task Name column, select the name of task 8
Click the Update Tasks button
Key 13d in the Actual dur box
Click the Scroll to Task button
Enter Actual Start Date and Duration for a Task (cont.)

## Slide 13: Recording Actual Values of Tasks
…causing the finish date to be later than originally scheduled
Task 8’s start date did not change, but the actual duration was 13 days…
Enter Actual Start Date and Duration for a Task (cont.)

## Slide 14: Recording Actual Values of Tasks
In the Task Name column, select the name of task 10
In the Task Name column, select the name of task 9
Click the 100% Complete button
Click the Update Tasks button
Enter Actual Start Date and Duration for a Task (cont.)

## Slide 15: Recording Actual Values of Tasks
Click OK
Key 6d in the Actual dur box
Click the Scroll to Task button
Enter Actual Start Date and Duration for a Task (cont.)

## Slide 16: Recording Actual Values of Tasks
Task 9 is complete
Task 10’s actual duration was 6 days
Deadline marker at May 6 for task 27
Enter Actual Start Date and Duration for a Task (cont.)

## Slide 17: Recording Actual Values of Tasks
Tracking actuals is essential to a well-managed project
When you enter actual start, finish, or duration values, Project updates the schedule and calculates the task’s percentage of completion
Enter Actual Start Date and Duration for a Task (cont.)

## Slide 18: Recording Actual Values of Tasks
Project uses the following rules to update the project
  When you enter the actual start date, Project moves the scheduled finish date to match the actual start date
  When you enter an actual finish date, Project moves the scheduled finish date to match the actual finish date and assigns a completion percentage of 100%
Enter Actual Start Date and Duration for a Task (cont.)

## Slide 19: Recording Actual Values of Tasks
When you enter an actual duration for a task that is less than the scheduled duration, Project subtracts the actual duration from the scheduled duration to determine the remaining duration
When you enter a task’s actual duration that is equal to the scheduled duration, Project sets the task to 100% complete
Enter Actual Start Date and Duration for a Task (cont.)

## Slide 20: Recording Actual Values of Tasks
When you enter an actual duration that is longer than the scheduled duration, Project adjusts the scheduled duration to match the actual duration and sets the task to 100% complete.
Enter Actual Start Date and Duration for a Task (cont.)

## Slide 21: Recording Actual Values of Tasks
Keep in mind the following issues
  It is often difficult to evaluate a percentage of completion
  The portion of a task’s duration that has elapsed does not always equate to a percentage accomplished
  The resources assigned to a task might have different criteria for what determines the task’s completion than does the manager or the resources assigned to successor tasks
Enter Actual Start Date and Duration for a Task (cont.)

## Slide 22: Adjusting Remaining Work or Duration
Click the Show/Hide Project Guide button
Click View
Click Task Usage
Adjust Actual and Remaining Work for a Task

## Slide 23: Adjusting Remaining Work or Duration
The Task Usage view shows resources assigned to each task
Adjust Actual and Remaining Work for a Task (cont.)

## Slide 24: Adjusting Remaining Work or Duration
Click OK
Click Edit
Click Go To
Key 39 in the ID box
Adjust Actual and Remaining Work for a Task (cont.)

## Slide 25: Adjusting Remaining Work or Duration
Click on the divider bar between the Task Usage table and the Work table
Click View
Point to Table: Usage
Click Work
Drag the divider bar to the right to see all columns in the Work table
Adjust Actual and Remaining Work for a Task (cont.)

## Slide 26: Adjusting Remaining Work or Duration
Adjust Actual and Remaining Work for a Task (cont.)

## Slide 27: Adjusting Remaining Work or Duration
Key 20h in the Actual column for task 39
Press Tab
Adjust Actual and Remaining Work for a Task (cont.)

## Slide 28: Adjusting Remaining Work or Duration
When you enter an actual work value of 20h, Project distributes the work among the resources…
…and recalculates the remaining work value
Adjust Actual and Remaining Work for a Task (cont.)

## Slide 29: Adjusting Remaining Work or Duration
Key 54h in the Remaining column for task 39
Press Tab
Adjust Actual and Remaining Work for a Task (cont.)

## Slide 30: Adjusting Remaining Work or Duration
When you adjust the remaining work value to 54h, Project distributes the work among the resources…
…and recalculates the new % Work Complete value
Adjust Actual and Remaining Work for a Task (cont.)

## Slide 31: Adjusting Remaining Work or Duration
As you track actuals, you can also adjust duration as well as start and finish dates
Only an incomplete task can have a remaining work or duration value
Whenever you enter actual work values, Project calculates actual cost values
By default, Project calculates actual costs, and you cannot enter costs directly
Adjust Actual and Remaining Work for a Task (cont.)

## Slide 32: Adjusting Remaining Work or Duration
If you want to enter actual cost values
  Click Tools  Options  Calculation
  Select the Calculation mode of Manual
Once you turn off automatic calculation, you can enter or import costs in the Actual Costs field
Remember that manually entering costs prevents Project from calculating costs based on resource rates and task progress
Adjust Actual and Remaining Work for a Task (cont.)

## Slide 33: Rescheduling Uncompleted Work
Reschedule Incomplete Work
Double-click the name of task 39
Click View
Click Gantt Chart
Click the name of task 39

## Slide 34: Rescheduling Uncompleted Work
Click the General tab
Key 50% in the Percent complete box
Click OK
Reschedule Incomplete Work (cont.)

## Slide 35: Rescheduling Uncompleted Work
Progress bar shows 50% completion
Reschedule Incomplete Work (cont.)

## Slide 36: Rescheduling Uncompleted Work
Click Tools
Point to Tracking
Click Update Project
Reschedule Incomplete Work (cont.)

## Slide 37: Rescheduling Uncompleted Work
Click Reschedule uncompleted work to start after
Key 5/19/08 in the date box
Click OK
Reschedule Incomplete Work (cont.)

## Slide 38: Rescheduling Uncompleted Work
Task is split to account for delay
Reschedule Incomplete Work (cont.)

## Slide 39: Rescheduling Uncompleted Work
Sometimes, resolving a problem by rescheduling work will result in another problem later in the project
Schedule variance is usually the rule rather than the exception
A good project manager must take quick corrective action to stay on track
Reschedule Incomplete Work (cont.)

## Slide 40: Saving an Interim Plan
Save an Interim Project Plan
Click Set interim plan
Click Tools
Point to Tracking
Click Set Baseline

## Slide 41: Saving an Interim Plan
Click OK to save the project plan
Save an Interim Project Plan (cont.)

## Slide 42: Saving an Interim Plan
The Copy and Into boxes enable you to select start and finish values for tasks that you want to save in the specific interim start and finish fields
The fields are numbered Start1 through Start10 and Finish1 through Finish10
Save an Interim Project Plan (cont.)

## Slide 43: Saving an Interim Plan
It is useful to save an interim plan — a snapshot of current values — once you have saved the baseline and started tracking actuals, or any time you have adjusted the current schedule
An interim plan saves only the start and finish dates of tasks, not resource or assignment values
You can save up to 10 different interim plans during a project
Save an Interim Project Plan (cont.)

## Slide 44: Saving an Interim Plan
You might want to save an interim plan
  At the end of a major phase of work
  At preset time intervals
  Just before or after entering a large number of actuals
Save an Interim Project Plan (cont.)

## Slide 45: Comparing Project Plans
Click Copy
Click View
Click More Views
Select Tracking Gantt
Click OK
Key Interim Tracking Gantt in the Name box
Compare the Baseline, Interim, and Actual Project Plans

## Slide 46: Comparing Project Plans
Key Interim in the new cell directly below the Name column heading
Click Format
Click Bar Styles
Click the Insert Row button
Press Tab
Compare the Baseline, Interim, and Actual Project Plans (cont.)

## Slide 47: Comparing Project Plans
Click the cell under the To column heading and select Finish1
In the same row, click the cell under the Show For…Tasks column heading
Select Normal
Click the cell under the From column heading and select Start1
Compare the Baseline, Interim, and Actual Project Plans (cont.)

## Slide 48: Comparing Project Plans
On the Bars tab in the Pattern box under the Middle label, select the sixth option – the first diagonally striped bar
In the Color box, select Fuchsia
Compare the Baseline, Interim, and Actual Project Plans (cont.)

## Slide 49: Comparing Project Plans
Compare the Baseline, Interim, and Actual Project Plans (cont.)

## Slide 50: Comparing Project Plans
Click the Scroll to Task button
Click OK
Scroll the task list so that task 29 is the first task listed on your screen
Click on the name of task 29
Compare the Baseline, Interim, and Actual Project Plans (cont.)

## Slide 51: Comparing Project Plans
Actual path task bar (blue)
Interim project plan bar (fuchsia)
Critical path task bar (red)
Baseline bar (black)
Compare the Baseline, Interim, and Actual Project Plans (cont.)

## Slide 52: Reporting Project Status
Click Apply
Click View
Click More Views
Select Task Sheet
Report Project Variance with a “Stoplight” View

## Slide 53: Reporting Project Status
Click View
Point to Table: Music Video Schedule Table
Click Cost
Report Project Variance with a “Stoplight” View (cont.)

## Slide 54: Reporting Project Status
Click Tools
Point to Customize
Click Fields
Report Project Variance with a “Stoplight” View (cont.)

## Slide 55: Reporting Project Status
Click the Formula button under the Custom attributes label
Make sure that Task is selected under the Field label
Select Number in the Type box
Select Overbudget(Number3) in the Field list
Report Project Variance with a “Stoplight” View (cont.)

## Slide 56: Reporting Project Status
Click Cancel to close the Formula dialog box
Per the formula, if the task falls within 30% percent above baseline, the formula assigns the number 30 to the task; if within 20%, a 20; and if within 10%, a 10.
Report Project Variance with a “Stoplight” View (cont.)

## Slide 57: Reporting Project Status
Click the drop-down arrow and review the choices
Click the Graphical Indicators button in the Customize Fields dialog box under the Values to display label
Click the first cell under the Image column heading
Click Cancel
Report Project Variance with a “Stoplight” View (cont.)

## Slide 58: Reporting Project Status
Click Column
Click Cancel
Select the Fixed Cost column heading
Click Insert
Report Project Variance with a “Stoplight” View (cont.)

## Slide 59: Reporting Project Status
Click OK
Select Overbudget(Number3) in the Field list
Report Project Variance with a “Stoplight” View (cont.)

## Slide 60: Reporting Project Status
The yellow indicator alerts you that the variance is higher than you would like it to be
Report Project Variance with a “Stoplight” View (cont.)

## Slide 61: Reporting Project Status
Reporting project status can take several forms
  Status reports describing where the project is in terms of scope, cost, and schedule
    These are often referred to as the three sides of the project triangle
  Progress reports that provide specific accomplishments
  Forecasts that predict future performance
Report Project Variance with a “Stoplight” View (cont.)

## Slide 62: Evaluating with Earned Value Analysis
Click OK
Click Project
Click Project Information
Key 5/18/08 in the Status date box
Set Project Status Date and Display the Earned Value Table

## Slide 63: Evaluating with Earned Value Analysis
Select Earned Value
Click View
Point to Table: Cost
Click More Tables
Click Apply
Set Status Date and Display the Earned Value Table (cont.)

## Slide 64: Evaluating with Earned Value Analysis
Set Status Date and Display the Earned Value Table (cont.)

## Slide 65: Evaluating with Earned Value Analysis
Select SPI in the Field name box
Click on the name of the Planned Value-PV column
Click Insert
Click Column
Click OK
Set Status Date and Display the Earned Value Table (cont.)

## Slide 66: Evaluating with Earned Value Analysis
Click OK
Click Insert
Click Column
Select CPI in the Field name box
Set Status Date and Display the Earned Value Table (cont.)

## Slide 67: Evaluating with Earned Value Analysis
Set Status Date and Display the Earned Value Table (cont.)

## Slide 68: Evaluating with Earned Value Analysis
Status date — Date you want Project to use when calculating earned value numbers
Earned value analysis — Used to measure the project’s progress and help forecast its outcome
  Focuses on schedule and budget performance in relation to baseline plans
  Gives a more complete picture of overall project performance in relation to both time and cost
Set Status Date and Display the Earned Value Table (cont.)

## Slide 69: Evaluating with Earned Value Analysis
Think of the difference between earned value analysis and simple schedule/budget analysis in this way
  “What are the current performance results we are getting?” — simple variance analysis
  “Are we getting our money’s worth for the current performance results we are getting?” — earned value analysis
Set Status Date and Display the Earned Value Table (cont.)

## Slide 70: Evaluating with Earned Value Analysis
Earned value analysis allows you to identify
  The true cost of project results to date
  The performance trend that is likely to continue for the rest of the project
Set Status Date and Display the Earned Value Table (cont.)

## Slide 71: Evaluating with Earned Value Analysis
For Project to calculate earned value amounts, you must first
  Save a baseline plan so that Project can calculate the budgeted cost of work scheduled before you start tracking actual work
Set Status Date and Display the Earned Value Table (cont.)

## Slide 72: Evaluating with Earned Value Analysis
  Record actual work on assignments
  Set the status date so that Project can calculate actual project performance up to a certain point in time (if you don’t specify a status date, Project uses the current date)
Set Status Date and Display the Earned Value Table (cont.)

## Slide 73: Evaluating with Earned Value Analysis
Project uses the following three values to generate all other schedule indicator and cost indicator values
  Planned value (PV) or budgeted cost of work scheduled (BCWS)
  Actual cost of work performed (ACWP)
  Earned value (EV) or budgeted cost of work performed (BCWP)
Set Status Date and Display the Earned Value Table (cont.)

## Slide 74: Evaluating with Earned Value Analysis
Other key indicators of project performance
  Cost variance (CV)
  Schedule variance (SV)
  Cost Performance Index (CPI)
  Schedule Performance Index (SPI)
Set Status Date and Display the Earned Value Table (cont.)

## Slide 75: Evaluating with Earned Value Analysis
CPI and SPI allow you to evaluate a project’s performance and compare the performance of multiple projects in a consistent way
Set Status Date and Display the Earned Value Table (cont.)

## Slide 76: Evaluating with Earned Value Analysis
  CPI = 1 is interpreted as follows: for every dollar’s worth of work that has been paid for, $1 worth of work was actually accomplished
  SPI = 1 is interpreted as follows: for every dollar’s worth of work that was planned to be accomplished, $1 worth of work was accomplished
Set Status Date and Display the Earned Value Table (cont.)

## Slide 77: Summary
Record actual start, finish, and duration values of tasks
Adjust remaining work or duration of tasks
Reschedule uncompleted work
You Learned How to

## Slide 78: Summary
You Learned How to (cont.)
Save an interim plan
Compare baseline, interim, and actual plans

## Slide 79: Summary
You Learned How to (cont.)
Report project status
Evaluate performance with earned value analysis