## Slide 1: Fine-Tuning Tasks
Lesson 11

## Slide 2: Skills Matrix
Skills | Matrix Skill
Manage task constraints and dependencies | Explore the effects of constraints and dependencies on task scheduling
Set deadline dates | Set a deadline date for a task
Establish task priorities | Establish task priorities

## Slide 3: Software Orientation
Task Name
Specifies whether you want subtasks rolled up to the summary task bar
Can range from 0–100
Hides the task bar when viewing the Gantt Chart or Calendar views
Task Duration
Check here if Duration is estimated
Task Priority can range from 1–1000, default is 500
Project’s Task Information Dialog Box—General Tab

## Slide 4: Manage Constraints and Dependencies
Make sure you are in the Gantt Chart view
Review the start-to-finish dependency between tasks 3 and 4
Explore Effects of Constraints and Dependencies on Task Scheduling

## Slide 5: Manage Constraints and Dependencies
Start-to-finish dependency between tasks 3 and 4
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 6: Manage Constraints and Dependencies
Click the Task Information button
Select the name of task 4
Click the Advanced tab
Click OK
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 7: Manage Constraints and Dependencies
In the Constraint date box, key January 10, 2008
In the Constraint type box, select Start No Later Than
Click OK
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 8: Manage Constraints and Dependencies
The Planning Wizard appears
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 9: Manage Constraints and Dependencies
Click OK
Under You can, click Continue. A Start No Later Than constraint will be set.
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 10: Manage Constraints and Dependencies
Click Continue. Allow the scheduling conflict.
A second alert appears
Click OK
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 11: Manage Constraints and Dependencies
SNLT constraint applied
Task rescheduled to start on Thursday, January 10
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 12: Manage Constraints and Dependencies
Click Options
Click Tools
Click the Schedule tab
Clear the Tasks will always honor their constraint dates box
Click OK
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 13: Manage Constraints and Dependencies
Rest the mouse pointer on the calendar alert icon in the Indicators column
A ScreenTip appears
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 14: Manage Constraints and Dependencies
Calendar alert icon and Screen Tip notify you that Project will honor task relationship over constraint
Starting date is reset to original starting date
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 15: Manage Constraints and Dependencies
Click Options
Click Tools
Click the Schedule tab
Click the Tasks will always honor their constraint dates box
Click OK
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 16: Manage Constraints and Dependencies
There are four possible types of task relationships
  Finish-to-Start (FS)
  Start-to-Start (SS)
  Finish-to-Finish (FF)
  Start-to-Finish (SF)
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 17: Manage Constraints and Dependencies
There are three different types of constraints
  Flexible constraints
  Semi-flexible constraints
  Inflexible constraints
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 18: Manage Constraints and Dependencies
Flexible constraints
  As Soon As Possible (ASAP)
  As Late As Possible (ALAP)
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 19: Manage Constraints and Dependencies
Semi-flexible constraints
  Start No Earlier Than (SNET)
  Start No Later Than (SNLT)
  Finish No Earlier Than (FNET)
  Finish No Later Than (FNLT)
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 20: Manage Constraints and Dependencies
Inflexible constraints
  Must Start On (MSO)
  Must Finish On (MFO)
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 21: Manage Constraints and Dependencies
Usually use both constraints and dependencies within the same project
When possible, use task dependencies and avoid semi-flexible or inflexible constraints
Project always honors constraint dates over task dependencies
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 22: Manage Constraints and Dependencies
It is recommended to use the default behavior of honoring constraint dates
Always set task relationships first, then apply constraints only when necessary
Remember that constraints you apply affect the overall schedule, not just the task to which you have applied the constraint
Explore Effects of Constraints and Dependencies on Scheduling (cont.)

## Slide 23: Setting Deadline Dates
Click Go To
Click Edit
Key 26
Set a Deadline Date for a Task
Click OK

## Slide 24: Setting Deadline Dates
Click the Set deadlines and constraints link
Click Tasks on the Project Guide
Key 4/30/08 in the date box under Set a deadline
Set a Deadline Date for a Task (cont.)

## Slide 25: Setting Deadline Dates
Deadline marker assigned to task 26
Set a Deadline Date for a Task (cont.)

## Slide 26: Setting Deadline Dates
Click the Done link in the Deadlines and Constraints pane
Select the name of task 27
Key 6/23/08 in the date box under Set a deadline
Set a Deadline Date for a Task (cont.)

## Slide 27: Setting Deadline Dates
A common mistake of inexperienced Project users is to place semi-flexible or inflexible constraints on too many tasks
These constraints greatly limit scheduling flexibility
A better way is to use the default ASAP constraint and then enter a deadline for the task
Set a Deadline Date for a Task (cont.)

## Slide 28: Setting Deadline Dates
Deadline — The date value you enter for a task that indicates the latest date by which you want the task to be completed
  The deadline date itself does not constrain the task
Project displays a deadline marker on the Gantt chart and alerts you if the task’s finish date moves beyond the deadline
Set a Deadline Date for a Task (cont.)

## Slide 29: Establishing Task Priorities
Click the Task Information button
Select the name of task 6
Click the General tab
Establish Task Priorities
Key 1000 in the Priority box

## Slide 30: Establishing Task Priorities
Establish Task Priorities (cont.)
Task priority of 1000
Click OK when finished

## Slide 31: Establishing Task Priorities
Establish Task Priorities (cont.)
Resource leveling — Process of delaying a resource’s work on a task to resolve an overallocation
Resource leveling might
  Delay the start date of an assignment
  Delay the start date of entire task
  Split up the work on a task

## Slide 32: Establishing Task Priorities
Establish Task Priorities (cont.)
Task priority — Numeric ranking between 1 and 1000 of a task’s importance and appropriateness for leveling
Tasks with priority 0 are leveled first, so they are likely to be delayed by leveling
A task with a priority of 1000 is never delayed by leveling. Use this assignment with care.

## Slide 33: Summary
Manage task constraints and dependencies
Set deadline dates
Establish task priorities
You Learned How to