## Slide 1: Fine-Tuning Resources
Lesson 12

## Slide 2: Skills Matrix
Skills | Matrix Skill
Enter material resource consumption rates | Enter a variable consumption rate for a material resource
Enter costs per use for resources | Enter a cost per use for a resource

## Slide 3: Skills Matrix
Skills | Matrix Skill
Assign multiple pay rates for a resource | Assign multiple pay rates for a resource
Apply different cost rates to assignments | Apply a different cost rate to an assignment

## Slide 4: Skills Matrix
Skills | Matrix Skill
Specify resource availability at different times | Specify a resource’s availability over time
Resolve resource overallocations manually | Manually resolve a resource overallocation
Level overallocated resources | Use resource leveling to resolve an overallocation

## Slide 5: Entering Material Resource Rates
Click OK
Click Edit
Click Go To
Key 34 in the ID box
Enter a Variable Consumption Rate for a Material Resource

## Slide 6: Entering Material Resource Rates
Press Enter
Click the Assign Resources button
Click the Units field for DVD
Key 0.25/h in the Units field
Enter a Variable Consumption Rate for a Material Resource (cont.)

## Slide 7: Entering Material Resource Rates
Double-click the column divider between the Units and the Cost columns to expand the Units column
Variable rate for DVDs
Click Close when finished
Enter a Variable Consumption Rate for a Material Resource (cont.)

## Slide 8: Entering Material Resource Rates
Click the Assignment Information button
Click View
Click Task Usage
Click the DVD assignment under task 34
Select the General tab
Enter a Variable Consumption Rate for a Material Resource (cont.)

## Slide 9: Entering Material Resource Rates
You cannot edit the assignment cost directly because it is a calculated cost
Click OK when finished
Enter a Variable Consumption Rate for a Material Resource (cont.)

## Slide 10: Entering Material Resource Rates
There are two types of consumption rates
  Fixed consumption rate
  Variable consumption rate
Enter a Variable Consumption Rate for a Material Resource (cont.)

## Slide 11: Entering Material Resource Rates
Variable consumption rate — The amount of the material resource consumed is dependent upon the duration of the task
After you enter a variable consumption rate for a material resource’s assignment, Project calculates the total quantity and cost of the resource consumed based on the task’s duration
Enter a Variable Consumption Rate for a Material Resource (cont.)

## Slide 12: Entering Material Resource Rates
An advantage to using a variable rate of consumption is that as the duration of the task changes, so do the calculated amount and cost of the material resource
Enter a Variable Consumption Rate for a Material Resource (cont.)

## Slide 13: Entering Costs per Use for Resources
Click the Specify people and equipment for the project link in the Resources pane
Click Resources
Select resource 11 on the Simple Resource Sheet
Click the Resource Information button
Enter a Cost per Use for a Resource

## Slide 14: Entering Costs per Use for Resources
Select the A(Default) tab under Cost Rate Tables
Select the Costs tab
Key 100 in the first row of the Per Use Cost column
Enter a Cost per Use for a Resource (cont.)

## Slide 15: Entering Costs per Use for Resources
Select End from the Cost Accrual drop-down box
Press Tab
Enter a Cost per Use for a Resource (cont.)

## Slide 16: Entering Costs per Use for Resources
$100 maintenance fee for each use
Cost Rate Table A
Enter a Cost per Use for a Resource (cont.)

## Slide 17: Entering Costs per Use for Resources
Click Done in the Specify Resources pane
Click OK
Enter a Cost per Use for a Resource (cont.)

## Slide 18: Entering Costs per Use for Resources
Any resource can have a cost per use
This may be in place of or in addition to the costs derived from their pay rates or consumption rates
You can specify whether per-use cost should accrue at the beginning or end of the task to which it is assigned
Enter a Cost per Use for a Resource (cont.)

## Slide 19: Assigning Multiple Pay Rates
Click Resource Sheet
Click View
Click the name of resource 9
Click the Resource Information button
Assign Multiple Pay Rates for a Resource

## Slide 20: Assigning Multiple Pay Rates
Key 15h
Press Enter
Click the B tab under Cost rate tables
Click the Costs tab
Select $0.00/h directly below the Standard Rate column heading
Assign Multiple Pay Rates for a Resource (cont.)

## Slide 21: Assigning Multiple Pay Rates
Key 22.50/h in the Overtime Rate field
Press Enter
Assign Multiple Pay Rates for a Resource (cont.)

## Slide 22: Assigning Multiple Pay Rates
Cost Rate Table B
Overtime rate of $22.50/h
Click OK when finished
Assign Multiple Pay Rates for a Resource (cont.)

## Slide 23: Assigning Multiple Pay Rates
The standard pay rate (Rate Table A) is used for all of a resource’s assignments unless you specify a different rate table
Assign Multiple Pay Rates for a Resource (cont.)

## Slide 24: Assigning Multiple Pay Rates
Cost rate table — Resource pay rates that are stored on the Costs tab of the Resource Information dialog box
  For a given resource, you can enter up to five cost rates
  After you assign a resource to a task, you can specify which rate table should apply
Assign Multiple Pay Rates for a Resource (cont.)

## Slide 25: Applying Different Cost Rates
Click Go To
Click View
Click Task Usage
Click Edit
Key 6 in the ID box
Click OK
Apply a Different Cost Rate to an Assignment

## Slide 26: Apply Different Cost Rates
Under task 6, click the row heading to the left of Yan Li
Click View
Point to Table: Usage
Click Cost
Scroll the table portion of the view until the Total Cost column is visible
Apply a Different Cost Rate to an Assignment (cont.)

## Slide 27: Apply Different Cost Rates
Yan Li’s cost for task 6 is $3,700 based on his rate in Cost Table A
Apply a Different Cost Rate to an Assignment (cont.)

## Slide 28: Apply Different Cost Rates
Click the General tab
Click the Assignment Information button
Key B in the Cost rate table box
Click OK
Apply a Different Cost Rate to an Assignment (cont.)

## Slide 29: Apply Different Cost Rates
Yan Li’s cost for task 6 is $3,000 based on his rate in Cost Table B
Apply a Different Cost Rate to an Assignment (cont.)

## Slide 30: Apply Different Cost Rates
You can set up as many as five pay rates per resource
This enables you to assign different pay rates to different assignments for a given resource
Rate Table A is used by default
Apply a Different Cost Rate to an Assignment (cont.)

## Slide 31: Specifying Resource Availability
Click Resource Sheet
Click View
Click the name of resource 38
Click the Resource Information button
Click the General tab
Specify a Resource’s Availability Over Time

## Slide 32: Specifying Resource Availability
Under Resource Availability, in the first row of the Available From column, leave NA
Specify a Resource’s Availability Over Time (cont.)

## Slide 33: Specifying Resource Availability
In the Available To cell in the first row, key 4/30/08
Specify a Resource’s Availability Over Time (cont.)

## Slide 34: Specifying Resource Availability
In the Available From cell in the second row, key 5/1/08
Specify a Resource’s Availability Over Time (cont.)

## Slide 35: Specifying Resource Availability
In the Available To cell in the second row, key 5/20/08
Specify a Resource’s Availability Over Time (cont.)

## Slide 36: Specifying Resource Availability
In the Units cell in the second row, key 200%
Specify a Resource’s Availability Over Time (cont.)

## Slide 37: Specifying Resource Availability
In the Available From cell in the third row, key 5/21/08
Specify a Resource’s Availability Over Time (cont.)

## Slide 38: Specifying Resource Availability
Leave the Available To cell in the third row blank
Specify a Resource’s Availability Over Time (cont.)

## Slide 39: Specifying Resource Availability
In the Units cell in the third row, key 300% and then press Enter
Specify a Resource’s Availability Over Time (cont.)

## Slide 40: Specifying Resource Availability
Click OK to close the Resource Information dialog box
Specify a Resource’s Availability Over Time (cont.)

## Slide 41: Specifying Resource Availability
Set resource availability over time using the Resource Availability grid on the General tab of the Resource Information dialog box
A resource’s capacity to work is measured in units.
Max. Units — Maximum capacity of a resource to accomplish tasks
Specify a Resource’s Availability Over Time (cont.)

## Slide 42: Specifying Resource Availability
A resource’s capacity to work determines how much that resource can work within those hours without becoming overallocated
  Measured in units
  Limited by Max. Units value
You can set different Max. Units values to be applied over different time periods for any resource
Specify a Resource’s Availability Over Time (cont.)

## Slide 43: Resolving Overallocations Manually
Click View
Click the Show/Hide Project Guide button
Click More Views
Select Resource Allocation
Click Apply
Manually Resolve a Resource Overallocation

## Slide 44: Resolving Overallocations Manually
Leveling Gantt view in the bottom pane
Resource Usage view in the top pane
Manually Resolve a Resource Overallocation (cont.)

## Slide 45: Resolving Overallocations Manually
Select the name of resource 27
Click the Hide Subtasks button
Click the Resource Name column heading
Vertically scroll the Resource name column to see names
Manually Resolve a Resource Overallocation (cont.)

## Slide 46: Resolving Overallocations Manually
Click Edit
Click the plus sign (+) next to Greg Guzik’s name
Click Go To
Key 6/29/08 in the Date box
Click OK
Manually Resolve a Resource Overallocation (cont.)

## Slide 47: Resolving Overallocations Manually
Greg Guzik’s assignments and the corresponding task bars for 6/29/08
Manually Resolve a Resource Overallocation (cont.)

## Slide 48: Resolving Overallocations Manually
Click the Assignment Information button
In the Resource Name column, click Greg’s second assignment, Fine video edit
Click the General tab
Manually Resolve a Resource Overallocation (cont.)

## Slide 49: Resolving Overallocations Manually
Click OK
Key 50% in the Units box
Click the SmartTag Actions button
Manually Resolve a Resource Overallocation (cont.)

## Slide 50: Resolving Overallocations Manually
Select the 2nd option in the SmartTag Actions list
Manually Resolve a Resource Overallocation (cont.)

## Slide 51: Resolving Overallocations Manually
Click Change the task’s total work (person-hours) to match the units and duration in the SmartTag Actions list
Manually Resolve a Resource Overallocation (cont.)

## Slide 52: Resolving Overallocations Manually
Task is restored to its original duration and Greg’s work on the task is reduced
Manually Resolve a Resource Overallocation (cont.)

## Slide 53: Resolving Overallocations Manually
Click Change the task’s total work (person-hours) to match the units and duration in the SmartTag Actions list
Click the SmartTag Actions button
Manually Resolve a Resource Overallocation (cont.)

## Slide 54: Resolving Overallocations Manually
Click the Assignment Information button
In the Resource Name column, click Greg’s third assignment, Fine audio edit
Click the General tab
Click OK
Key 50% in the Units box
Manually Resolve a Resource Overallocation (cont.)

## Slide 55: Resolving Overallocations Manually
Click Change the task’s total work (person-hours) to match the units and duration in the SmartTag Actions list
Click the SmartTag Actions button
Manually Resolve a Resource Overallocation (cont.)

## Slide 56: Resolving Overallocations Manually
Greg Guzik is no longer overallocated – he is fully allocated on these three days
Manually Resolve a Resource Overallocation (cont.)

## Slide 57: Resolving Overallocations Manually
Allocation — A resource’s capacity to work
A resource is said to be in one of three states: underallocated, fully allocated, or overallocated
Manually Resolve a Resource Overallocation (cont.)

## Slide 58: Resolving Overallocations Manually
  Underallocated — Work assigned to the resource is less than the resource’s maximum capacity
  Fully allocated — Total work of a resource’s task assignments is exactly equal to that resource’s work capacity
  Overallocated — Resource is assigned to more work than can be done in the normal work capacity of the resource
Manually Resolve a Resource Overallocation (cont.)

## Slide 59: Resolving Overallocations Manually
To resolve an overallocation, you can
  Manually edit an assignment
  Replace the overallocated resource with another resource using the Replace button in the Assign Resources dialog box
  Reduce the value in the Units field of the Assign Resources or Assignment Information dialog box
  Allow the overallocation to remain in the schedule if it is not extreme
Manually Resolve a Resource Overallocation (cont.)

## Slide 60: Software Orientation
1
2
3
4
5
6
7
8
Microsoft Project’s Resource Leveling Dialog Box

## Slide 61: Leveling Overallocated Resources
Click Remove Split
Click Window
Click View
Click Resource Sheet
Click Tools
Click Level Resources
Use Resource Leveling to Resolve an Overallocation

## Slide 62: Leveling Overallocated Resources
Select Manual under Leveling calculations
Select Day by Day in the Look for overallocations… box
Use Resource Leveling to Resolve an Overallocation (cont.)

## Slide 63: Leveling Overallocated Resources
Select Clear leveling values before leveling
Select Level entire project under Leveling range for
Use Resource Leveling to Resolve an Overallocation (cont.)

## Slide 64: Leveling Overallocated Resources
Select Standard in the Leveling order box under Resolving overallocations
Clear the Level only within available slack check box
Use Resource Leveling to Resolve an Overallocation (cont.)

## Slide 65: Leveling Overallocated Resources
Select the Leveling can adjust individual assignments on a task check box
Select the Leveling can create splits in remaining work check box
Use Resource Leveling to Resolve an Overallocation (cont.)

## Slide 66: Leveling Overallocated Resources
Click Level Now
Use Resource Leveling to Resolve an Overallocation (cont.)

## Slide 67: Leveling Overallocated Resources
Project asks whether you want to level the entire pool or only selected resources
Click OK
Select Entire pool
Use Resource Leveling to Resolve an Overallocation (cont.)

## Slide 68: Leveling Overallocated Resources
The resources in red may still be overallocated hour by hour (or even minute by minute), but they are not overallocated day by day
Use Resource Leveling to Resolve an Overallocation (cont.)

## Slide 69: Leveling Overallocated Resources
Click More Views
Click View
Select Leveling Gantt
Click Apply
Use Resource Leveling to Resolve an Overallocation (cont.)

## Slide 70: Leveling Overallocated Resources
Click the Scroll to Task button
Select the name of task 66
Use Resource Leveling to Resolve an Overallocation (cont.)

## Slide 71: Leveling Overallocated Resources
In the Leveling Gantt view, bars on the top represent the pre-leveling values, and bars on the bottom represent values after leveling
Use Resource Leveling to Resolve an Overallocation (cont.)

## Slide 72: Leveling Overallocated Resources
Resource leveling is the process of delaying or splitting a resource’s work on a task to resolve an overallocation
Based on options you select, Project may try to resolve an overallocation by
  Delaying the start of an assignment
  Delaying the start of a task
  Splitting the work on a task
Use Resource Leveling to Resolve an Overallocation (cont.)

## Slide 73: Leveling Overallocated Resources
Resource leveling has its limits
It cannot replace the judgment of a good project manager
Use Resource Leveling to Resolve an Overallocation (cont.)

## Slide 74: Summary
Enter material resource consumption rates
Enter costs per use for resources
Assign multiple pay rates for a resource
Apply different cost rates to assignments
You Learned How to

## Slide 75: Summary
You Learned How to (cont.)
Specify resource availability at different times
Resolve resource overallocations manually
Level overallocated resources