## Slide 1: Advanced Project Plan Formatting
Lesson 14

## Slide 2: Skills Matrix
Skills | Matrix Skill
Customize the calendar view | Format bar styles for tasks in the Calendar view
Use Task IDs and WBS codes | Work with Unique ID and WBS codes

## Slide 3: Skills Matrix
Skills | Matrix Skill
Format the Network Diagram | Format items in the Network Diagram view
Customize and print reports | Create a custom report

## Slide 4: Software Orientation
First-level WBS hierarchy
Second-level WBS hierarchy
Third-level WBS hierarchy
WBS Code column represents the outline hierarchy of a project
Unique ID column represents the entry order of tasks and resources
WBS Codes and Unique IDs in the Task Sheet View

## Slide 5: Customizing the Calendar View
Click the Show/Hide Project Guide button
Click View
Click Calendar
Format Bar Styles for Tasks in the Calendar View

## Slide 6: Customizing the Calendar View
Task bars are drawn on the days for which tasks are scheduled
Format Bar Styles for Tasks in the Calendar View (cont.)

## Slide 7: Customizing the Calendar View
Click Bar Styles
Click Format
The Bar Styles dialog box appears
Format Bar Styles for Tasks in the Calendar View (cont.)

## Slide 8: Customizing the Calendar View
Click Line in the Bar type box
Click Summary in the Task type box
Click the second option in the Pattern box
Click Critical in the Task type box
Format Bar Styles for Tasks in the Calendar View (cont.)

## Slide 9: Customizing the Calendar View
Make sure that the check boxes for Shadow and Bar rounding are selected
Click Red in the Color box
Format Bar Styles for Tasks in the Calendar View (cont.)

## Slide 10: Customizing the Calendar View
Click OK to close the Bar Styles dialog box
Format Bar Styles for Tasks in the Calendar View (cont.)

## Slide 11: Customizing the Calendar View
Click Layout Now
Click Format
Move your pointer to the divider bar between the weeks of the calendar until it changes to a bar with perpendicular arrows
Format Bar Styles for Tasks in the Calendar View (cont.)

## Slide 12: Customizing the Calendar View
Position your pointer on the divider bar, then double-click to expand the Calendar row height
Format Bar Styles for Tasks in the Calendar View (cont.)

## Slide 13: Customizing the Calendar View
Click Edit
Double-click on the divider bar to expand the width of the calendar rows
Key 07/11/08 in the Date box
Click Go To
Click OK
Format Bar Styles for Tasks in the Calendar View (cont.)

## Slide 14: Customizing the Calendar View
The height of the calendar row is expanded to show all elements of the project plan
Critical task is shown as a red bar; the dotted-line bar indicates a split task
Format Bar Styles for Tasks in the Calendar View (cont.)

## Slide 15: Customizing the Calendar View
The Calendar view is one of the simplest views
It offers several formatting options
It is often used for sharing schedule information with resources or other stakeholders who are accustomed to a weekly or monthly view
Format Bar Styles for Tasks in the Calendar View (cont.)

## Slide 16: Using Task IDs and WBS Codes
Click More Views
Click View
Select Task Sheet
Click Apply
Work with Unique IDs and WBS Codes

## Slide 17: Using Task IDs and WBS Codes
Point to Table: Music Video Schedule
Click View
Click Entry
Work with Unique IDs and WBS Codes (cont.)

## Slide 18: Using Task IDs and WBS Codes
Project plan in Task Sheet view with Entry table
Work with Unique IDs and WBS Codes (cont.)

## Slide 19: Using Task IDs and WBS Codes
Click Insert
Click on the Task Name column heading
Click Column
Click Unique ID in the Field name list
Click OK
Work with Unique IDs and WBS Codes (cont.)

## Slide 20: Using Task IDs and WBS Codes
Unique ID indicates the order in which tasks were entered. Here, tasks were entered in a different order than they are currently displayed.
Unique ID column represents the entry order of tasks and resources
Work with Unique IDs and WBS Codes (cont.)

## Slide 21: Using Task IDs and WBS Codes
Click Insert
Click on the Task Name column heading
Click Column
Click WBS in the Field name list
Click OK
Work with Unique IDs and WBS Codes (cont.)

## Slide 22: Using Task IDs and WBS Codes
WBS Code column represents the outline hierarchy of a project
First-level WBS hierarchy
Second-level WBS hierarchy
Third-level WBS hierarchy
Work with Unique IDs and WBS Codes (cont.)

## Slide 23: Using Task IDs and WBS Codes
Click the Indent button
Select 7 and 8 in the Task ID column
Work with Unique IDs and WBS Codes (cont.)

## Slide 24: Using Task IDs and WBS Codes
The WBS codes now show tasks 7 and 8 at the third level of the project hierarchy
Work with Unique IDs and WBS Codes (cont.)

## Slide 25: Using Task IDs and WBS Codes
Click Edit
Select task 7
Click Cut Task
Work with Unique IDs and WBS Codes (cont.)

## Slide 26: Using Task IDs and WBS Codes
Task 7 is removed and remaining tasks are renumbered
Change Highlighting (blue shading) shows the effects of deleting the task
Work with Unique IDs and WBS Codes (cont.)

## Slide 27: Using Task IDs and WBS Codes
Click Edit
Select task 4
Click Paste
Work with Unique IDs and WBS Codes (cont.)

## Slide 28: Using Task IDs and WBS Codes
Unique ID represents the next sequential number to show when it was added to the project
Task IDs and WBS codes in the Pre-Production phase are renumbered
Work with Unique IDs and WBS Codes (cont.)

## Slide 29: Using Task IDs and WBS Codes
Click Undo 3 times
The task list is restored to its original order
Work with Unique IDs and WBS Codes (cont.)

## Slide 30: Using Task IDs and WBS Codes
Each task in a Microsoft Project project plan has a unique identifier: the Task ID
Project assigns unique identifiers to each task
When a task is inserted, moved, or deleted, Project updates the ID numbers so that they reflect the current task order
Resources have Resource IDs that behave like Task IDs
Work with Unique IDs and WBS Codes (cont.)

## Slide 31: Using Task IDs and WBS Codes
Project also tracks the order in which you enter tasks and resources
The Unique ID task and resource fields store this order
If tasks or resources are reorganized and you later need to see the entry order, refer to the Unique ID
Work with Unique IDs and WBS Codes (cont.)

## Slide 32: Using Task IDs and WBS Codes
Task ID and Unique ID don’t give information about a task’s place in the hierarchy of a project
A better way to show hierarchy is to display
    Outline numbers
    Work Breakdown Structure (WBS) codes
These are numeric representations of the outline hierarchy of a project
Work with Unique IDs and WBS Codes (cont.)

## Slide 33: Using Task IDs and WBS Codes
WBS codes — Include any combination of letters and numbers you choose
Outline numbers — Numeric only and generated by Project
Mask (appearance) — The order and number of alphabetic, numeric, and alphanumeric strings in a code and the separators between them
Work with Unique IDs and WBS Codes (cont.)

## Slide 34: Using Task IDs and WBS Codes
In complex projects, Project can handle custom outline numbers
For example
  Link different outline levels of a project plan within different levels of the organization’s structure
  Associate different outline levels of a project plan with internal cost centers or job tracking codes
Work with Unique IDs and WBS Codes (cont.)

## Slide 35: Using Task IDs and WBS Codes
You can sort, group, and filter tasks and resources by their outline numbers
You can apply up to ten levels of a custom outline number for tasks and ten for resources in a single Project file
Work with Unique IDs and WBS Codes (cont.)

## Slide 36: Formatting the Network Diagram
Click Network Diagram
Click View
Format Items in the Network Diagram View

## Slide 37: Formatting the Network Diagram
Line and arrows between nodes represent relationships between tasks
Each task is represented by a node
Format Items in the Network Diagram View (cont.)

## Slide 38: Formatting the Network Diagram
Click Box Styles
Click Format
Format Items in the Network Diagram View (cont.)

## Slide 39: Formatting the Network Diagram
Click More Templates
Format Items in the Network Diagram View (cont.)

## Slide 40: Formatting the Network Diagram
Click Copy
Select Standard in the Templates in “Network Diagram” list
Format Items in the Network Diagram View (cont.)

## Slide 41: Formatting the Network Diagram
Below Choose cell(s), click the empty cell below Duration and to the right of Resource Names
Key ‘Standard + WBS’ in the Template name box
Select WBS from the drop-down list that becomes active
Format Items in the Network Diagram View (cont.)

## Slide 42: Formatting the Network Diagram
New template name
Adds the WBS code to the standard template
Format Items in the Network Diagram View (cont.)

## Slide 43: Formatting the Network Diagram
Click Close
Click OK
In the Box Styles dialog box under Style settings for, click and drag to select Critical and Noncritical
Click Standard + WBS in the Data template box
Click OK
Format Items in the Network Diagram View (cont.)

## Slide 44: Formatting the Network Diagram
The WBS Code has been added to the Standard box style
Format Items in the Network Diagram View (cont.)

## Slide 45: Formatting the Network Diagram
Network Diagram — Standard way of representing project activities and their relationships in a flowchart format
Tasks are represented as boxes, or nodes
The relationships between tasks are drawn as lines connecting nodes
It focuses on relationships between activities rather than on durations
Format Items in the Network Diagram View (cont.)

## Slide 46: Customizing and Printing Reports
Create a Custom Report
Click Reports
Click Report
Select Custom
Click Select
Click New

## Slide 47: Customizing and Printing Reports
Create a Custom Report (cont.)
Click OK
In the Define New Report dialog box, make sure that Task is selected
In the name box, select the text that is in the box
Key Music Video Schedule

## Slide 48: Customizing and Printing Reports
Create a Custom Report (cont.)
In the Table box, click Music Video Schedule Table
In the Filter box, click Unfinished Shoots

## Slide 49: Customizing and Printing Reports
Create a Custom Report (cont.)

## Slide 50: Customizing and Printing Reports
Create a Custom Report (cont.)
Click OK
Move your mouse pointer over the report and click to zoom in
In the Custom Reports dialog box, make sure Music Video Schedule is selected
Click Preview

## Slide 51: Customizing and Printing Reports
Create a Custom Report (cont.)
Report shows uncompleted shoots, with only the details you specified

## Slide 52: Customizing and Printing Reports
Create a Custom Report (cont.)
Click Close
Click Close
Click Close

## Slide 53: Customizing and Printing Reports
Create a Custom Report (cont.)
Reports — Primary way that project managers can communicate project information to stakeholders
Reports are designed only for printing or viewing, but do not allow for data entry or manipulation

## Slide 54: Summary
Customize the Calendar view
Use Task IDs and WBS codes
Format the Network Diagram
Customize and print reports
You Learned How to