## Slide 1: Project Plan Optimization
Lesson 13

## Slide 2: Skills Matrix
Skills | Matrix Skill
Make time and date adjustments | Adjust fiscal year settings within Microsoft Project
View the project’s critical path | View the project’s critical path

## Slide 3: Skills Matrix
Skills | Matrix Skill
Delay the start of assignments | Delay the start of a resource assignment
Apply contours to assignments | Apply a contour to a resource assignment Edit a task assignment manually

## Slide 4: Skills Matrix
Skills | Matrix Skill
Optimize the project plan | Identify the project finish date and total cost Compress the project plan to pull in the project finish date

## Slide 5: Software Orientation
Use to set the first day of the week
If you are working with fiscal years, specify which month is the start of the fiscal year
These settings supply the start and end time when you enter a date but not a time
Set hours per day, hours per week, and days per month
Microsoft Project’s Calendar Tab of the Options Dialog Box

## Slide 6: Making Time and Date Adjustments
Click Options
Click the Show/Hide Project Guide button
Drag the divider bar on the Gantt Chart until the Start and Finish columns are visible
Click Tools
Adjust Fiscal Year Settings Within Microsoft Project

## Slide 7: Making Time and Date Adjustments
Select July in the Fiscal year starts in : box
Click the Calendar tab
Click OK
Adjust Fiscal Year Settings Within Microsoft Project (cont.)

## Slide 8: Making Time and Date Adjustments
Fiscal year setting displays December 30, 2008, for December 30, 2007
Date formats in fields, such as Start and Finish columns, are not affected by fiscal year settings
Adjust Fiscal Year Settings Within Microsoft Project (cont.)

## Slide 9: Making Time and Date Adjustments
Drag the divider back to the right edge of the Duration column
Click Undo
Adjust Fiscal Year Settings Within Microsoft Project (cont.)

## Slide 10: Making Time and Date Adjustments
A fiscal year is any 12 consecutive-month period defined for accounting purposes
A calendar year is the 12-month period from January to December
Using a fiscal year timescale is best if there are stakeholders who are accustomed to analyzing information in this format
Adjust Fiscal Year Settings Within Microsoft Project (cont.)

## Slide 11: Making Time and Date Adjustments
The Calendar tab of the Options dialog box is used for controlling time in Microsoft Project
Keep in mind that the Calendar tab has nothing to do with Project’s base, resource, or task calendars
The settings on the Calendar tab affect only the time conversions for task durations that you enter, such as hours in a day, but not when work can be scheduled
Adjust Fiscal Year Settings Within Microsoft Project (cont.)

## Slide 12: Making Time and Date Adjustments
The Default Start Time and Default End Time settings supply the default start and end time for task constraints or for actual start and finish dates in which you enter a date but do not include a time
Adjust Fiscal Year Settings Within Microsoft Project (cont.)

## Slide 13: Viewing the Project’s Critical Path
View the Project’s Critical Path
Click Apply
Click View
Click More Views
Select Detail Gantt

## Slide 14: Viewing the Project’s Critical Path
Click View
Point to Table: Delay
Click Entry
View the Project’s Critical Path (cont.)

## Slide 15: Viewing the Project’s Critical Path
Click OK
Click Edit
Click Go To
Key 45
View the Project’s Critical Path (cont.)

## Slide 16: Viewing the Project’s Critical Path
Non-critical tasks appear in blue
Critical tasks appear in red
Slack appears as a thin line
View the Project’s Critical Path (cont.)

## Slide 17: Viewing the Project’s Critical Path
Click View
Point to Table: Entry
Click Schedule
Drag the divider bar until all columns in the Schedule table are visible
View the Project’s Critical Path (cont.)

## Slide 18: Viewing the Project’s Critical Path
Notice free and total slack values for tasks
View the Project’s Critical Path (cont.)

## Slide 19: Viewing the Project’s Critical Path
Recall
  Free slack — Amount of time the finish date of a task can be delayed before the start of a successor task must be rescheduled
  Total slack — Amount of time the finish date on a task can be delayed before the completion of the project will be delayed
  A task can have free slack, total slack, or both
View the Project’s Critical Path (cont.)

## Slide 20: Viewing the Project’s Critical Path
Click Entire Project
Click OK
Drag the divider bar to show only the Task Name column
Click View
Click Zoom
View the Project’s Critical Path (cont.)

## Slide 21: Viewing the Project’s Critical Path
Click on the name of task 11
Click Tools
Click Options
Click the Calculation tab
View the Project’s Critical Path (cont.)

## Slide 22: Viewing the Project’s Critical Path
Select the Calculate multiple critical paths check box
Click OK
View the Project’s Critical Path (cont.)

## Slide 23: Viewing the Project’s Critical Path
Critical path within the Pre-Production phase
View the Project’s Critical Path (cont.)

## Slide 24: Viewing the Project’s Critical Path
Click View
Point to Table: Schedule
Click Entry
Drag the divider bar to the right of the Duration column
Click Undo
View the Project’s Critical Path (cont.)

## Slide 25: Viewing the Project’s Critical Path
One of the most important factors that should be monitored in any project plan is the project’s critical path
After a task on the critical path is completed, it is no longer critical
During the life of a project, the critical path will change occasionally
View the Project’s Critical Path (cont.)

## Slide 26: Viewing the Project’s Critical Path
Prior to starting actual work, the project manager must closely manage the critical path and slack
  He must know the tasks on the critical path and be able to evaluate the risks to success if any tasks are not completed as scheduled
  He must know where the slack is in the project
View the Project’s Critical Path (cont.)

## Slide 27: Delaying the Start of Assignments
Click Task Usage
Click Edit
Click Go To
Key 74
Click View
Click OK
Delay the Start of a Resource Assignment

## Slide 28: Delaying the Start of Assignments
You want to delay Luis Bonifaz’s work on this task until July 17, 2008
Delay the Start of a Resource Assignment (cont.)

## Slide 29: Delaying the Start of Assignments
Click the Assignment Information button
Click the General tab
Key 7/17/08 in the Start box
Click OK
Select the name of the resource Luis Bonifaz
Delay the Start of a Resource Assignment (cont.)

## Slide 30: Delaying the Start of Assignments
Total work for the task does not change
Delaying the start of the resource’s assignment shifts the work to the next day
Delay the Start of a Resource Assignment (cont.)

## Slide 31: Delaying the Start of Assignments
You can delay the start of work for any number of resources assigned to a task
If you need to delay the start of work for all resources on a particular task, it may be better to reschedule the start date of the task
Delay the Start of a Resource Assignment (cont.)

## Slide 32: Applying Contours to Assignments
Click OK
Click Edit
Click Go To
Key 67 in the ID box
Applying a Contour to a Resource Assignment

## Slide 33: Applying Contours to Assignments
These six resource assignments have a flat contour
Applying a Contour to a Resource Assignment (cont.)

## Slide 34: Applying Contours to Assignments
Select Greg Guzik in the Task Name column under task 67
Click the Assignment Information button
Click the General tab
Select Back Loaded in the Work contour box
Click OK
Applying a Contour to a Resource Assignment (cont.)

## Slide 35: Applying Contours to Assignments
Contour indicator matches the type of contour applied – back loaded, in this case
Point to the contour indicator to see a ToolTip
Applying a Contour to a Resource Assignment (cont.)

## Slide 36: Applying Contours to Assignments
Contour — Determines how a resource’s work on a task is scheduled over time
Predefined contours — Describe how work is distributed over time in terms of graphical patterns
Applying a Contour to a Resource Assignment (cont.)

## Slide 37: Applying Contours to Assignments
Some predefined contours include Bell, Front Loaded, Back Loaded, Double Peak, and Turtle
Keep in mind that when an assignment to a task sets the finish date of the task, the resource is called the “driving resource”
Applying a Contour to a Resource Assignment (cont.)

## Slide 38: Applying Contours to Assignments
Click OK
Click Edit
Click Go To
Key 51 in the ID box
Edit a Task Assignment Manually

## Slide 39: Applying Contours to Assignments
Press Tab
Select Ido Ben-Sachar’s 8-hour assignment for Wednesday, June 3, 2008
Key 4h
Edit a Task Assignment Manually (cont.)

## Slide 40: Applying Contours to Assignments
Key 4h
Select Ido Ben-Sachar’s assignment for Wednesday, June 4, 2008
Press Enter
Edit a Task Assignment Manually (cont.)

## Slide 41: Applying Contours to Assignments
Work values for Tuesday and Wednesday after editing
Indicator shows work has been edited
Edit a Task Assignment Manually (cont.)

## Slide 42: Optimizing the Project Plan
Click More Views
Select Detail Gantt
Click Apply
Click Project
Click View
Click Project Information
Identifying the Project Finish Date and Total Cost

## Slide 43: Optimizing the Project Plan
The Finish date is formatted in gray because you cannot directly edit it
Identifying the Project Finish Date and Total Cost (cont.)

## Slide 44: Optimizing the Project Plan
Click the Statistics button
Identifying the Project Finish Date and Total Cost (cont.)

## Slide 45: Optimizing the Project Plan
The current calculated cost is the sum of all task and resource costs in the project
Identifying the Project Finish Date and Total Cost (cont.)

## Slide 46: Optimizing the Project Plan
Optimizing — Adjusting the aspects of the project plan, such as cost, duration, and scope (or any combination of these), to achieve a desired plan result
A desired result may be a target finish date, duration, or overall cost
Identifying the Project Finish Date and Total Cost (cont.)

## Slide 47: Optimizing the Project Plan
Note that in the Project Statistics box, many of the values equal zero
  This is because you have not yet saved a baseline or entered values into the project plan
Crashing — Decreasing the project’s duration without altering the basic sequence of activities
Identifying the Project Finish Date and Total Cost (cont.)

## Slide 48: Optimizing the Project Plan
Click OK
Click View
Click Zoom
Click Reset
Compress the Project Plan to Pull in the Project Finish Date

## Slide 49: Applying Contours to Assignments
Click OK
Click Edit
Click Go To
Key 67 in the ID box
Scroll to see the Gantt bar for task 67
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 50: Applying Contours to Assignments
Task 67 has a back-loaded contour, which has lengthened its duration
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 51: Applying Contours to Assignments
Press Enter
Double-click the name of task 68
Click the Predecessors tab in the Task Information dialog box
Key –50% in the Lag field for the predecessor task 67
Click OK
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 52: Applying Contours to Assignments
Task 68 begins when 50% of task 67’s duration has elapsed
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 53: Applying Contours to Assignments
Click Insert
Click View
Click Task Usage
Click the Work column heading
Click Column
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 54: Applying Contours to Assignments
Select Overtime Work in the Field name box
Click OK
Drag the divider bar between the table and bar portions of the Gantt Chart to the right until the Work column is visible
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 55: Applying Contours to Assignments
Click OK
Click Edit
Click Go To
Key 66 in the ID box
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 56: Applying Contours to Assignments
Note the work values for the assignments on task 66
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 57: Applying Contours to Assignments
Click the Overtime Work cell for Jamie Reding on task 66
Key 10
Press Enter
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 58: Applying Contours to Assignments
Click the Overtime Work cell for Florian Voss on task 66
Key 10
Press Enter
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 59: Applying Contours to Assignments
Click the Overtime Work cell for Shu Ito on task 66
Key 10
Press Enter
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 60: Applying Contours to Assignments
Click the Overtime Work cell for Jane Clayton on task 66
Key 10
Press Enter
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 61: Applying Contours to Assignments
Click the Overtime Work cell for Bjorn Rettig on task 66
Key 5
Press Enter
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 62: Applying Contours to Assignments
Overtime work added for resource assignments on task 66
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 63: Applying Contours to Assignments
Click OK
Click Project
Click Project Information
Note the new Finish date of 7/21/08
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 64: Applying Contours to Assignments
Microsoft Project cannot automate optimization
The project manager must know the nature of the project and how it should be optimized
You may need to make trade-offs such as cutting scope, adding resources, allowing overtime, or adding lead time
Compress the Project Plan to Pull in the Project Finish Date (cont.)

## Slide 65: Summary
Make time and date adjustments
View the project’s critical path
Delay the start of assignments
You Learned How to

## Slide 66: Summary
You Learned How to (cont.)
Apply contours to assignments
Optimize the project plan