## Slide 1: Refining Your Project Plan
Lesson 4

## Slide 2: Skills Matrix
Skills | Matrix Skill
Apply a task calendar to an individual task | Apply a task calendar to an individual task
Change task types | Change scheduling formula values to change task types Change a task type using the Task Information dialog box

## Slide 3: Skills Matrix
Skills | Matrix Skill
Split a task | Split a task
Establish recurring tasks | Set up a recurring task Assign resources to a recurring task

## Slide 4: Skills Matrix
Skills | Matrix Skill
Apply task constraints | Apply a Start No Earlier Than constraint to a task
Review the project’s critical path | Review the project’s critical path
View resource allocations over time | Explore resource allocations and identify overallocated resources

## Slide 5: Software Orientation
Change Working Time dialog box with Create New Calendar dialog box displayed
Microsoft Project’s Opening Screen

## Slide 6: Applying a Task Calendar to a Task
The Create New Base Calendar dialog box is activated
Click Tools
Click Change Working Time
Click Create New Calendar
Apply a Task Calendar to an Individual Task

## Slide 7: Applying a Task Calendar to a Task
Click Make a Copy of button
Key the custom calendar name in the Name box
Select Standard from the drop-down menu
Click OK
Apply a Task Calendar to an Individual Task (cont.)

## Slide 8: Applying a Task Calendar to a Task
Click the Work Weeks tab
Click the Details button
The Details dialog box is activated
Apply a Task Calendar to an Individual Task (cont.)

## Slide 9: Applying a Task Calendar to a Task
Select the desired days
Select the desired working times button
Key the desired To and From working times
Repeat as necessary for different days and times
Apply a Task Calendar to an Individual Task (cont.)

## Slide 10: Applying a Task Calendar to a Task
Custom calendar name
Select the desired working times button
Select the desired days
Key the desired times
Apply a Task Calendar to an Individual Task (cont.)

## Slide 11: Applying a Task Calendar to a Task
Click the Scroll to Task button
Select the name of the task to which you want to apply the custom calendar
Click the Task Information button
Apply a Task Calendar to an Individual Task (cont.)

## Slide 12: Applying a Task Calendar to a Task
Select the custom calendar name from the Calendar box
Click the Advanced tab
Click the Scheduling ignores resource calendars check box
Click OK
Apply a Task Calendar to an Individual Task (cont.)

## Slide 13: Applying a Task Calendar to a Task
Advanced tab
Calendar selection box
Scheduling ignores resource calendars check box
Click OK when finished
Apply a Task Calendar to an Individual Task (cont.)

## Slide 14: Applying a Task Calendar to a Task
  A task calendar is the base calendar that is used by a single task
    Defines working and nonworking times for a task, regardless of settings in the project calendar
    Used when other base calendars are too broad or specific for the task requirements
Apply a Task Calendar to an Individual Task (cont.)

## Slide 15: Changing Task Types
Click the Make changes to the project link
Click Track on the Project Guide
On the menu bar, click Edit  Go To
Key the desired task ID and click OK
Change Scheduling Formula Values to Change Task Types

## Slide 16: Changing Task Types
Press Enter
Key the new, longer duration in the duration field
  By default, Project changes the duration and increases the work for each resource
  You want to increase the duration but keep work the same
Change Scheduling Formula Values to Change Task Types (cont.)

## Slide 17: Changing Task Types
Select the second option in the Smart Tag list
Click the Smart Tag button for the selected task
  Project adjusts the work and duration based on the Smart Tag option you selected
Change Scheduling Formula Values to Change Task Types (cont.)

## Slide 18: Changing Task Types
New duration entered
Smart Tag options list
Change Scheduling Formula Values to Change Task Types (cont.)

## Slide 19: Changing Task Types
Adjusted duration for this phase
Adjusted Scheduling Formula values
Change Scheduling Formula Values to Change Task Types (cont.)

## Slide 20: Changing Task Types
A task type determines which of the three scheduling formula variables remains the same if the other two values change
There are three task types
  Fixed units
  Fixed duration
  Fixed work
Change Scheduling Formula Values to Change Task Types (cont.)

## Slide 21: Changing Task Types
If the task type is…. | …and you change the |  | 
 | Duration | Units | Work
Fixed Duration | Project recalculates work | Project recalculates units | Project recalculates work
Fixed Units | Project recalculates work | Project recalculates duration | Project recalculates duration
Fixed Work | Project recalculates units | Project recalculates duration | Project recalculates duration
Keep in mind the effect of changing any scheduling formula variable for any task type
Change Scheduling Formula Values to Change Task Types (cont.)

## Slide 22: Changing Task Types
Key the desired task ID and click OK
On the menu bar, click Edit  Go To
Click the Task Information button
Click the Advanced tab
Select Fixed duration in the Task type box
Change a Task Type Using the Task Information Dialog Box

## Slide 23: Changing Task Types
Key the new unit(s) value(s) for the desired resource(s)
Click the Resources tab
Click OK
  Project updates the work values
  Notice the duration value did not change
Change a Task Type Using the Task Information Dialog Box (cont.)

## Slide 24: Changing Task Types
Adjusted resource units
Selected task name
Resource tab selected
Cost column new to Project 2007
Change a Task Type Using the Task Information Dialog Box (cont.)

## Slide 25: Changing Task Types
Keep in mind the difference between task type and effort-driven scheduling
  Both affect work, units, and duration values
  Effort-driven scheduling affects the schedule only when you add or remove resources from tasks
  Modifying task type affects only the resources that are assigned to the task when the change is made
Change a Task Type Using the Task Information Dialog Box (cont.)

## Slide 26: Splitting a Task
Split a Task
On the menu bar, click Edit  Go To
On the menu bar, click View  Gantt Chart
Key the desired task ID, and click OK
Click the Split Task button
Split Task button

## Slide 27: Splitting a Task
When you move the mouse pointer over the Gantt bar, the date changes
Split a Task (cont.)
The mouse pointer changes to split a task

## Slide 28: Splitting a Task
Split a Task (cont.)
Click and drag the mouse pointer until the desired Start date appears
Move (don’t click) the mouse pointer to the desired date
Release the mouse button
  Project inserts a task split
  A dotted line shows the split

## Slide 29: Splitting a Task
Split a Task (cont.)
The split is represented by a dotted line

## Slide 30: Splitting a Task
Split a Task (cont.)
A split is an interruption in a task
Keep the following in mind when splitting a task
  You can split a task into as many parts as needed
  You can drag a segment of a split task left or right to reschedule the split
  The time of the actual task split does not count in the duration of the task unless the task type is fixed duration

## Slide 31: Splitting a Task
Split a Task (cont.)
Keep the following in mind when splitting a task
  Work does not occur during a split
  If the duration of a split changes, the last segment of the task is adjusted
  If a split task is rescheduled, the whole task (including splits) is rescheduled. The pattern of segments and splits is preserved.

## Slide 32: Establishing Recurring Tasks
A recurring task is repeated at specified intervals (daily, weekly, monthly)
When you create a recurring task, Project creates a series of tasks characterized by
  Start No Earlier Than constraints
  No task relationships
  Effort-driven scheduling is turned off
Set Up a Recurring Task

## Slide 33: Establishing Recurring Tasks
Set Up a Recurring Task (cont.)
On the menu bar, click Insert  Recurring Task
Select the desired task
Key the recurring task name in the Name box
Key or select the duration

## Slide 34: Establishing Recurring Tasks
Set Up a Recurring Task (cont.)
Key or select the desired start date
Select the desired recurrence pattern
Key or select the number of occurrences or End by date
Click OK

## Slide 35: Establishing Recurring Tasks
Set Up a Recurring Task (cont.)
Select Range of recurrence parameters
Select Recurrence pattern

## Slide 36: Establishing Recurring Tasks
Set Up a Recurring Task (cont.)
Summary recurring task shows individual task occurrences
Recurring task icon

## Slide 37: Establishing Recurring Tasks
Click the Assign Resources button
Select the Summary recurring task name
Select the desired resource name(s)
Click Assign
Click Close
Assign Resources to a Recurring Task

## Slide 38: Establishing Recurring Tasks
Click the + or – signs to expand or collapse the Summary task
Recurring tasks are automatically numbered sequentially
Resource assignments for individual recurring tasks
Assign Resources to a Recurring Task (cont.)

## Slide 39: Establishing Recurring Tasks
When establishing a recurring task, keep in mind
  Always use the Assign Resources dialog box. If you enter names in the Resource Name field of the summary task, the resources will only be assigned to the summary task.
  Project will alert you if an occurrence of a recurring task will take place during nonworking time. You can choose to skip or reschedule the task.
Assign Resources to a Recurring Task (cont.)

## Slide 40: Establishing Recurring Tasks
When establishing a recurring task, keep in mind
  If you schedule a recurring task to end on a specific date, Project will suggest the current project end date. If you select the project end date, you will need to manually change it later if the project end date changes.
Assign Resources to a Recurring Task (cont.)

## Slide 41: Applying Task Constraints
Select the Set deadlines and constrain tasks link
Click Tasks on the Project Guide
Select the desired task
Click the Scroll to Task button
Apply a Start No Earlier Than Constraint to a Task

## Slide 42: Applying Task Constraints
Key or select the desired date
Select Start No Earlier Than from the drop-down box in the Deadlines and Constraints pane
Click the Done link in the Deadlines and Constraints pane
Apply a Start No Earlier Than Constraint to a Task (cont.)

## Slide 43: Applying Task Constraints
Highlighted cells show the effect of the SNET constraint
Constraint icon
Constraint drop-down box
Constraint date box
Done link
Apply a Start No Earlier Than Constraint to a Task (cont.)

## Slide 44: Applying Task Constraints
A constraint is a restriction that controls the start or finish date of a task
Apply a Start No Earlier Than Constraint to a Task (cont.)

## Slide 45: Applying Task Constraints
There are three categories of constraints
  Flexible constraint — Gives Project the flexibility to change start and finish dates of a task
  Inflexible constraint — Forces a task to begin or end on a certain date
  Semi-flexible constraint — Gives Project the flexibility to change start and finish dates within a date boundary
Apply a Start No Earlier Than Constraint to a Task (cont.)

## Slide 46: Applying Task Constraints
There are eight types of task constraints within the three categories of constraints
Constraint Category | Constraint Types | Properties
Flexible | As Soon As Possible (ASAP) | Project will schedule a task to occur as soon as it can happen. The default constraint type applied to new tasks when scheduling from the project start date.
 | As Late As Possible (ALAP) | Project will schedule a task to occur as late as it can occur. The default constraint type applied to all new tasks when scheduling from the project finish date.
Apply a Start No Earlier Than Constraint to a Task (cont.)

## Slide 47: Applying Task Constraints
There are eight types of task constraints within the three categories of constraints
Constraint Category | Constraint Types | Properties
Semi-Flexible | Start No Earlier Than (SNET) | Project will schedule a task to start on or after the specified constraint date. Use this type to make sure a task will not start before a specific date.
 | Start No Later Than (SNLT) | Project will schedule a task to start on or before the specified constraint date. Use this type to make sure a task will not start after a specific date.
 | Finish No Earlier Than (FNET) | Project will schedule a task to finish on or after the specified constraint date. Use this type to ensure a task will not finish before a specific date.
 | Finish No Later Than (FNLT) | Project will schedule a task to finish on or before the specified constraint date. Use this type to ensure that a task will not finish after a specific date.
Apply a Start No Earlier Than Constraint to a Task (cont.)

## Slide 48: Applying Task Constraints
There are eight types of task constraints within the three categories of constraints
Constraint Category | Constraint Types | Properties
Inflexible | Must Start On (MSO) | Project will schedule a task to start on the specified constraint date. Use this type to ensure that a task will start on an exact date.
 | Must Finish On (MFO) | Project will schedule a task to finish on the specified constraint date. Use this type to ensure that a task will finish on an exact date.
Apply a Start No Earlier Than Constraint to a Task (cont.)

## Slide 49: Applying Task Constraints
  If you apply inflexible or semi-flexible constraints to tasks in addition to task links, you might create negative slack
    Negative slack — Amount of time that tasks overlap due to a conflict between task relationships and constraints
  Some constraint behaviors change if you must schedule a project from a finish rather than a start date
Apply a Start No Earlier Than Constraint to a Task (cont.)

## Slide 50: Applying Task Constraints
A new feature in Project 2007 is Task Drivers
Task Drivers button
Task Drivers pane activated for task 50
The Task Drivers pane shows the factors that drive a task’s start times and help you backtrack to analyze constraints
Apply a Start No Earlier Than Constraint to a Task (cont.)

## Slide 51: Reviewing the Project’s Critical Path
Review the Project’s Critical Path
Select Detail Gantt and click Apply
Click View  More Views on the menu bar
On the menu bar, click Edit  Go To
Key the desired task ID and click OK

## Slide 52: Reviewing the Project’s Critical Path
The critical path is the series of tasks whose scheduling directly affects the project’s finish date
  The critical path usually changes as the project progresses
  Once a task on the critical path is complete, it is no longer considered critical
Review the Project’s Critical Path (cont.)

## Slide 53: Reviewing the Project’s Critical Path
Slack is the amount of time a task can be delayed without causing a delay to a task or the overall project
  Free slack is the amount of time a task can be delayed before it will delay another task
  Total slack is the amount of time a task can be delayed without delaying the project end date
Review the Project’s Critical Path (cont.)

## Slide 54: Reviewing the Project’s Critical Path
Critical tasks have no slack
Noncritical tasks have slack greater than zero
The best way to manage the overall duration of a project is via the critical path
Review the Project’s Critical Path (cont.)

## Slide 55: View Resource Allocations Over Time
Click Report on the Project Guide
Click View  Gantt Chart on the menu bar
Click the See how resources’ time is allocated link
Explore Resource Allocations and Identify Overallocated Resources

## Slide 56: View Resource Allocations Over Time
The Usage table
The Resource Usage view
The Gantt Chart view
Change Timescale link
Explore Resource Allocations/Identify Overallocated Resources (cont.)

## Slide 57: View Resource Allocations Over Time
Click the Hide Subtasks button
Click the Resource Name column heading
Click on the name of the desired resource
Click the Scroll to Task button
Explore Resource Allocations/Identify Overallocated Resources (cont.)

## Slide 58: View Resource Allocations Over Time
Click the Middle Tier tab
Click the Change Timescale link at the bottom of the Resource Allocation pane
Under Middle tier formatting in the Units box, select Months
Under Timescale options in the Show box, select One tier (Middle)
Explore Resource Allocations/Identify Overallocated Resources (cont.)

## Slide 59: View Resource Allocations Over Time
Click OK when finished to close the Timescale dialog box
Explore Resource Allocations/Identify Overallocated Resources (cont.)

## Slide 60: View Resource Allocations Over Time
Timescale shown by month
Overallocated resources shown in red
Explore Resource Allocations/Identify Overallocated Resources (cont.)

## Slide 61: View Resource Allocations Over Time
Select the name of an overallocated resource
Click the Undo button (to reverse the timescale change you just made)
Click the Scroll to Task button
Click the plus sign (+) next to the resource name to expand the individual assignment list
Explore Resource Allocations/Identify Overallocated Resources (cont.)

## Slide 62: View Resource Allocations Over Time
The individual tasks that are causing the overallocation
Individual resource assignments
Explore Resource Allocations/Identify Overallocated Resources (cont.)

## Slide 63: View Resource Allocations Over Time
Allocation is the portion of a resource’s capacity devoted to work on a specific task
A resource can be
    Underallocated
    Fully allocated
    Overallocated
Explore Resource Allocations/Identify Overallocated Resources (cont.)

## Slide 64: Summary
Apply a task calendar to an individual task
Change task types
Split a task
Establish recurring tasks
You Learned How to

## Slide 65: Summary
You Learned How to (cont.)
Apply task constraints
Review the project’s critical path
View resource allocations over time