## Slide 1: Construction Accounting and Financial Management
Fourth Edition
Chapter 07
Managing Costs
Copyright © 2020, 2013, 2009 Pearson Education, Inc. All Rights Reserved

## Slide 2: Monitoring and Controlling Process
Establish a baseline
Collect data
Assess data
Take corrective action (if needed)

## Slide 3: Material Purchases
Purchase orders approved by project manager
Supervisor has limited authority to approve small purchase orders

## Slide 4: Materials Purchases
Figure 7.1 Material Purchases

## Slide 5: Labor Costs (1 of 2)
Hard to control
Tracked by timecards
  Use electronic time cards
Must be processed quickly

## Slide 6: Labor Costs (2 of 2)
Figure 7.2 Labor

## Slide 7: Subcontracts (1 of 2)
Often requires progress payments
Hard to determine percent complete

## Slide 8: Subcontracts (2 of 2)
Figure 7.3 Subcontracts

## Slide 9: Equipment
Hard to control
Controlled like labor
  Use equipment time cards or
  Use equipment information system
Be sure equipment is returned as soon as the project is done with it

## Slide 10: Other Costs
Where possible, use purchase orders
When a purchase order has not been used, approval by project manager is required
  For example, for utility bills

## Slide 11: General Overhead Costs
Must be managed as aggressively as construction costs

## Slide 12: Job Profitability
Update weekly
  Cost to complete
  Estimated cost at completion
  Estimated profit
Include committed costs even if not tracked in the accounting system

## Slide 13: Cost Loaded Schedule
Prepare schedule
Assign cost to the tasks
Determine the weekly or monthly costs

## Slide 14: Earned Value
Measures performance with regards to
  Schedule
  Cost
Ignores items which do not have a cost
  For example, submittals

## Slide 15: Budgeted Cost of Work Scheduled (BCWS)
The expected cost of the work that is scheduled to be performed during a specific period of time

## Slide 16: Budgeted Cost of Work Performed (BCWP)
The expected cost of the work that is actually performed during a specific period of time

## Slide 17: Actual Cost of Work Performed (ACWP)
The actual cost of the work that is performed during a specific period of time
Hard to calculate in a timely matter because of lag in receiving and processing invoices

## Slide 18: Schedule Performance Index (SPI)
Measures progress of work
Results

## Slide 19: Cost Performance Index (CPI)
Measures control of budget
Results

## Slide 20: Labor Cost Performance Index (LCPI) (1 of 2)
Same as CPI except it only looks only at in-house labor
  BCLP = budgeted cost of labor performed
  ACLP = actual cost of labor performed
Measures control of in-house labor costs

## Slide 21: Labor Cost Performance Index (LCPI) (2 of 2)
Results

## Slide 22: Total Estimate Cost at Completion
Assumes CPI will not change

## Slide 23: SPI/CPI Target levels
Figure 7.6 Graphing the CPI and SPI

## Slide 24: Project Closeout Audit
Validate data
Find areas where performance was better than expected
  Learn how to repeat it
Find areas where performance was worse than expected
  Learn how to avoid it

## Slide 25: Design-Build Projects (1 of 3)
Design to budget
  Establish a budget
  Prepare cost estimates
  Determine cost variance
  Redesign (as needed)

## Slide 26: Design-Build Projects (2 of 3)
Figure 7.7 Budget for a Design-Build Project

## Slide 27: Design-Build Projects (3 of 3)
Monitoring and controlling design costs (e.g., architect and engineers’ fees)
  Use same methods as used to monitor and control construction costs

## Slide 28: Copyright