# Chapter 16 - Solutions

Problem 1:

Problem 2:

a.	Project completion time = 17 weeks

b.	Critical activities: A, B, D, F, G

Problem 3:

a.

b.	Critical path = B D F

c.	Path completion times:

A C E = 15 weeks

B D E = 14 weeks

B D F = 17 weeks

Expected project length = 17 weeks.

Problem 4:

AON Diagram:

Problem 5:

| Activity | A | B | C | D | E | F | G | H | I | J |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Expected Time | 6 | 5 | 7.33 | 7.67 | 10.17 | 4 | 5.83 | 6.33 | 8 | 3 |

Problem 6:

| Activity | A | B | C | D | E | F | G | H | I | J |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Variance | 1 | 0.444 | 1.778 | 1 | 3.361 | 0.111 | 0.694 | 1 | 1 | 0 |

Problem 7:

a. 	Path completion times:

ABDFHJ = 32 weeks

ABDGIJ = 35.5 weeks

ACEFHJ = 36.83 weeks

ACEGIJ = 40.33

Project completion time = 40.33 weeks

b.	Critical activities: A C E G I J

Problem 8:

a.	P(project ( 38) = P(critical path ( 38) = P(Z ( ) = P(Z ( -0.83) = 0.2033

b.	P(project ( 42) = P(critical path ( 42) = P(Z ( ) = P(Z ( 0.60) = 0.7257

Problem 13:

a.

| Activity | A | B | C | D | E | F | G | H |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Expected time | 10 | 10 | 5 | 8 | 7.33 | 7.17 | 8 | 3 |

b.

| Activity | A | B | C | D | E | F | G | H |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Variance | 0.44 | 4 | 0.11 | 0.44 | 1.78 | 0.25 | 1.78 | 0 |

c.	A B D F H = 38.17

A B D G H = 39

A C E F H = 32.5

A C E G H = 33.33

Expected project completion time = 39 weeks.

Problem 14:

a.	P(project ( 36) = P(critical path ( 36) = P(Z ( ) = P(Z ( -1.16) = 0.1230

b.	P(project ( 40) = P(critical path ( 40) = P(Z ( ) = P(Z ( 0.39) = 0.6517

Problem 15:

AON Diagram:

b.

| Activity | A | B | C | D | E | F | G | H | I | J | K | L |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Expected time | 8.67 | 3.33 | 6 | 7 | 15.33 | 3 | 4 | 2 | 2 | 2 | 5 | 9.17 |

c.	Path completion times:

AE = 24 weeks

ABDFGHI = 30 weeks

ABDFGHJKL = 44.17

CDFGHI = 24 weeks

CDFGHJKL = 38.17 weeks

Critical path: ABDFGHJKL

d.	Estimated project completion time = 44.17 weeks.

Problem 16:

a.	P(project ( 32) = P(critical path ( 32) = P(Z ( ) = P(Z ( -3.84) = 0

b.	Z =

1.645 =

X = 49.4 weeks.

# Text boxes

F

A

B

C

E

G

D

F

E

D

C

B

A